## Sheet1
GLOBAL GATEWAY DEVELOPMENT CORPORATION
WAP PHASE 2 COST TO COMPLETE
AS OF MAY 31, 2020
Cost to Complete as of March 22, 2020 | 2326739225.97
Add: "Prolongation Cost" | 96590368.18
Cost to Complete as of May 31, 2020* | 2423329594.15
*Exclusive of estimated "Remobilization Cost" resulting from work stoppage due to the COVID Pandemic amounting to PHP30 million.