## cost_plan
|  |  |  | Initial Cost Plan | Initial Cost Plan | Initial Cost Plan | Initial Cost Plan | Budget Transfer | Budget Transfer | Budget Transfer | Budget Transfer | Current Cost Plan | Current Cost Plan | Current Cost Plan | Current Cost Plan | Awarded Amount | Awarded Amount | Awarded Amount | Awarded Amount | Approved Change Request | Approved Change Request | Approved Change Request | Approved Change Request | Est_Chng_Req | Est_Chng_Req | Est_Chng_Req | Est_Chng_Req | Ordr_not_Plcd | Ordr_not_Plcd | Ordr_not_Plcd | Ordr_not_Plcd | Proj_Risk | Proj_Risk | Proj_Risk | Proj_Risk | Cert_Amount | Cert_Amount | Cert_Amount | Cert_Amount | Forecast | Forecast | Forecast | Forecast
Description | WP No. | Contract Package | Contractor | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total | Building C | Building D | Building E | Total
Consultants | C01 | Construction Management | TPM | - | - | -
Consultants | C02 | LEED Consultant | DEAN BARONE | 1765238.8 | 1736975.32 | 2642021.17 | 6144235.29 | -718250 | -706750 | -1075000 | -2500000 | 1046988.8 | 1030225.32 | 1567021.17 | 3644235.29 | 1765238.8 | 1736975.32 | 2642021.17 | 6144235.29 | -718250 | -706750 | -1075000 | -2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 316333.68 | 311268.82 | 473454.52 | 1101057.02 | 1046988.8 | 1030225.32 | 1567021.17 | 3644235.29 | 316333.68 | 311268.82 | 473454.52 | 1101057.02
Consultants | C03 | Architectural Services | AIDEA | 1436500 | 1413500 | 2150000 | 5000000 | 201110 | 197890 | 301000 | 700000 | 1637610 | 1611390 | 2451000 | 5700000 | 1436500 | 1413500 | 2150000 | 5000000 | 201110 | 197890 | 301000 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 257423.15 | 253301.51 | 385283.52 | 896008.18 | 2674812.45 | 2631985.66 | 4003374.01 | 9310172.12 | -779779.3 | -767294.15 | -1167090.49 | -2714163.94
Consultants | C04 | Structural Design Engineering Services | SY2 | 68952 | 67848 | 103200 | 240000 | 143650 | 141350 | 215000 | 500000 | 212602 | 209198 | 318200 | 740000 | 68952 | 67848 | 103200 | 240000 | 143650 | 141350 | 215000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12356.31 | 12158.47 | 18493.61 | 43008.39 | 68952 | 67848 | 103200 | 240000 | 156006.31 | 153508.47 | 233493.61 | 543008.39
Consultants | C05 | MEPF Design Engineering Services | (MPI) Meinhardt Philippines Inc. | 707989.28 | 696653.57 | 1059642.86 | 2464285.71 | 1581864.98 | 1556537.52 | 2367566.79 | 5505969.29 | 2289854.26 | 2253191.09 | 3427209.65 | 7970255 | 707989.28 | 696653.57 | 1059642.86 | 2464285.71 | 1581864.98 | 1556537.52 | 2367566.79 | 5505969.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 126872.84 | 124841.46 | 189889.73 | 441604.03 | 2540039.81 | 2499370.88 | 3801660.7 | 8841071.4 | -123312.71 | -121338.34 | -184561.32 | -429212.37
Consultants | C06 | Building Information Modelling (BIM) Services | ESCA | 1005550 | 989450 | 1505000 | 3500000 | 0 | 0 | 0 | 0 | 1005550 | 989450 | 1505000 | 3500000 | 1005550 | 989450 | 1505000 | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 180196.21 | 177311.06 | 269698.46 | 627205.73 | 1005550 | 989450 | 1505000 | 3500000 | 180196.21 | 177311.06 | 269698.46 | 627205.73
Consultants | C07 | Façade Design Services | LUMICON | 577473 | 568227 | 864300 | 2010000 | 27293.5 | 26856.5 | 40850 | 95000 | 604766.5 | 595083.5 | 905150 | 2105000 | 577473 | 568227 | 864300 | 2010000 | 27293.5 | 26856.5 | 40850 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 103484.11 | 101827.21 | 154883.97 | 360195.29 | 428077 | 421223 | 640700 | 1490000 | 280173.61 | 275687.71 | 419333.97 | 975195.29
Consultants | C08 | Landscape Design Services | INSPIRA | 86190 | 84810 | 129000 | 300000 | 0 | 0 | 0 | 0 | 86190 | 84810 | 129000 | 300000 | 86190 | 84810 | 129000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15445.39 | 15198.09 | 23117.01 | 53760.49 | 0 | 0 | 0 | 0 | 101635.39 | 100008.09 | 152117.01 | 353760.49
Consultants | C09 | Cost Consultant / Quantity Surveying Services | (QSI) Quantity Solutions Inc. | 6773844.48 | 6665387.52 | 10138368 | 23577600 | -2464344.48 | -2424887.52 | -3688368 | -8577600 | 4309500 | 4240500 | 6450000 | 15000000 | 6773844.48 | 6665387.52 | 10138368 | 23577600 | -2464344.48 | -2424887.52 | -3688368 | -8577600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1213884.02 | 1194448.35 | 1816812.14 | 4225144.5 | 5608096 | 5518304 | 8393600 | 19520000 | -84711.98 | -83355.65 | -126787.86 | -294855.5
Consultants | C10 | Third Party Testing and | COMMTECH | 2873000 | 2827000 | 4300000 | 10000000 | -86190 | -84810 | -129000 | -300000 | 2786810 | 2742190 | 4171000 | 9700000 | 2786810 | 2742190 | 4171000 | 9700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 514846.3 | 506603.03 | 770567.04 | 1792016.36 | 711182.42 | 699795.58 | 1064422 | 2475400 | 2590473.88 | 2548997.45 | 3877145.04 | 9016616.36
Preliminaries | 1001 | Document Control / EDMS / Project Cloud | New Forma | 861900 | 848100 | 1290000 | 3000000 | -861900 | -848100 | -1290000 | -3000000 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 |  |  |  |  | 0 | 0 | - | - | - | 0
Preliminaries | CARI | Insurances | PNX Udenna Insurance | 1980285.7 | 1948579.07 | 2963880.44 | 6892745.21 | 1006125.87 | 990016.65 | 1505861.9 | 3502004.42 | 2986411.57 | 2938595.72 | 4469742.34 | 10394749.63 | 1980285.7 | 1948579.07 | 2963880.44 | 6892745.21 | 1006125.87 | 990016.65 | 1505861.9 | 3502004.42 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2986411.57 | 2938595.72 | 4469742.34 | 10394749.63 | - | - | - | 0
Structure and General | CP01 | Structure and General Sitewide | TERP Asia | 122785926.31 | 120819983.88 | 183772879.62 | 427378789.81 | 29655994.19 | 29181167.97 | 44385929.35 | 103223091.52 | 152441920.5 | 150001151.85 | 228158808.97 | 530601881.33 | 104864500 | 103185500 | 156950000 | 365000000 | 47577420.51 | 46815651.85 | 71208808.97 | 165601881.33 | 536504.55 | 527914.5 | 802982.79 | 1867401.83 | 0 | 0 | 0 |  | 61900015.68 | 61781453.3 | 87796656.58 | 211478125.55 | 105858957.67 | 104164035.28 | 158438398.19 | 368461391.14 | 109019483.05 | 108146484.37 | 158320050.14 | 375486017.57
Structure and General | OP01 | Cement (Supply only) | Megacem & Republic | 26477942.93 | 26054000.92 | 39629361.15 | 92161305 | -3343491.38 | -3289958.28 | -5004181.32 | -11637630.98 | 23134451.55 | 22764042.64 | 34625179.83 | 80523674.02 | 26477942.93 | 26054000.92 | 39629361.15 | 92161305 | -3343491.38 | -3289958.28 | -5004181.32 | -11637630.98 | 3204.82 | 3153.51 | 4796.64 | 11154.97 | 0 | 0 | 0 | [5 empty] | 9492765.73 | 9340775.75 | 14207759.36 | 33041300.84 | 13644890.64 | 13426420.41 | 20422217.1 | 47493528.15
Structure and General | OP02 | Reinforcing Steel (OSM) | Capitol Steel | 74582968.25 | 73388810.04 | 111627832.75 | 259599611.04 | -26389004.73 | -25966486.73 | -39496247.94 | -91851739.41 | 48193963.52 | 47422323.31 | 72131584.81 | 167747871.63 | 74582968.25 | 73388810.04 | 111627832.75 | 259599611.04 | -26389004.73 | -25966486.73 | -39496247.94 | -91851739.41 | 5140.66 | 5058.35 | 7693.99 | 17892.99 | 0 | 0 | 0 | [5 empty] | 30382557.74 | 29896098.41 | 45473372.18 | 105752028.32 | 17816546.44 | 17531283.25 | 26665906.61 | 62013736.31
Façade | CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | Glazetech | 87854587.67 | 86447935.73 | 131491377.31 | 305793900.71 | -18080835.58 | -17791340.82 | -27061466.4 | -62933642.8 | 69773752.09 | 68656594.91 | 104429910.91 | 242860257.91 | 65348207.75 | 64301908.57 | 97806228.1 | 227456344.43 | 1347396.72 | 1325823.36 | 2016639.71 | 4689859.79 | 0 | 0 | 0 |  | 3604714.6 | 3546999.02 | 5395152.38 | 12546866 | 62286766.97 | 62286766.97 | 0 | 124573533.94 | 9414521.12 | 9263783.92 | 14090651.17 | 32768956.22 | 123172564.92 | 122197714 | 91127369.02 | 336497647.94
Façade | CP11A | Curtain Wall & Structural Steel (Bldg.E) | Dalkia | 64447642.47 | 63415762.36 | 96458358.03 | 224321762.87 | -8808607.11 | -8667571.28 | -13183783.7 | -30659962.09 | 55639035.36 | 54748191.08 | 83274574.33 | 193661800.78 | 53130194.64 | 52279519.75 | 79519609.1 | 184929323.48 | 221295.19 | 217752 | 331211.03 | 770258.22 | 0 | 0 | 0 |  | 3003185.4 | 2955100.98 | 4494847.62 | 10453134 | 0 | 0 | 20152285.35 | 20152285.35 | 22492339.84 | 22132211.88 | 33664135.5 | 78288687.22 | 33862335.38 | 33320160.85 | 70833817.6 | 138016313.83
Façade | CP21 | Waterproofing | HPS | 6405666.92 | 6303104.9 | 9587319.09 | 22296090.91 | -1359366.75 | -1337601.74 | -2034555.17 | -4731523.65 | 5046300.17 | 4965503.16 | 7552763.92 | 17564567.26 | 5345782.64 | 5260190.57 | 8000997.34 | 18606970.55 | -392835.57 | -386545.83 | -587954.39 | -1367335.79 | 0 | 0 | 0 |  | 143650 | 141350 | 215000 | 500000 | 352930.09 | 349884.69 | 284678.64 | 987493.41 | 2969591.8 | 2922045.26 | 4444568.3 | 10336205.36 | 2479935.35 | 2442834.18 | 3468153.28 | 8390922.81
Façade | CP30 | Building Maintenance Unit (BMU) | Vonotech | 3734900 | 3675100 | 5590000 | 13000000 | -488410 | -480590 | -731000 | -1700000 | 3246490 | 3194510 | 4859000 | 11300000 | 2959190 | 2911810 | 4429000 | 10300000 | 199960.8 | 196759.2 | 299280 | 696000 | 0 | 0 | 0 |  | 287300 | 282700 | 430000 | 1000000 | 0 | 0 | 0 | 0 | 681656.59 | 670742.49 | 1020230.89 | 2372629.97 | 2764794.21 | 2720526.71 | 4138049.11 | 9623370.03
Builders Work | CP01A | Masonry & Rendering, Metal Doors & Hardwares, Office Floor | TERP Asia | 45622230.1 | 44891766.27 | 68282488.49 | 158796484.86 | -5903547.97 | -5809025.44 | -8835800.99 | -20548374.4 | 39718682.13 | 39082740.83 | 59446687.5 | 138248110.46 | 37923600 | 37316400 | 56760000 | 132000000 | 1185266.15 | 1166288.69 | 1773979.97 | 4125534.82 | 0 | 0 | 0 |  | 1149200 | 1130800 | 1720000 | 4000000 | 11785517.72 | 11719784.98 | 15731405.88 | 39236708.58 | 7917110.27 | 7790348.32 | 11849486.3 | 27556944.89 | 44126473.61 | 43542925.35 | 64135899.55 | 151805298.51
Builders Work | OP33 | Door Hardwares | Technoinox | 3746998.26 | 3687004.55 | 5608107.38 | 13042110.19 | 193939.83 | 190834.63 | 290268.45 | 675042.91 | 3940938.09 | 3877839.18 | 5898375.83 | 13717153.1 | 3821090 | 3759910 | 5719000 | 13300000 | 138091.64 | 135880.63 | 206680.83 | 480653.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 3959181.64 | 3895790.63 | 5925680.83 | 13780653.1
Fitout | CP20 | Fit-Out Works | EE Black | 94344409.61 | 92833848.23 | 141204650.66 | 328382908.5 | -5059857.2 | -4978843.13 | -7573054.63 | -17611754.96 | 89284552.41 | 87855005.1 | 133631596.03 | 310771153.54 | 89063000 | 87637000 | 133300000 | 310000000 | -249687.73 | -245689.94 | -373705.96 | -869083.63 | -571429.85 | -562280.6 | -855255.25 | -1988965.7 | 1436500 | 1413500 | 2150000 | 5000000 | 7431172.87 | 7360045.63 | 28900545.95 | 43691764.45 | 8750149.17 | 8742992.45 | 16198337.85 | 35613423.71 | 88359406.12 | 86859582.63 | 146923246.89 | 322142235.64
MEPF | CP04 | Electrical Works | BETA | 95513731.16 | 93984447.61 | 142954766.44 | 332452945.21 | -13023347.46 | -12814828.84 | -19491957.56 | -45330133.85 | 82490383.7 | 81169618.77 | 123462808.88 | 287122811.36 | 83366702.9 | 82031907.1 | 124774390 | 290173000 | -1406793.11 | -1384268.75 | -2105537.9 | -4896599.76 | 316030 | 310970 | 3973000 | 4600000 | 0 | 0 | 0 | 0 | 6863566.69 | 6846177.85 | 9619618.49 | 23329363.03 | 24120768.97 | 23734568.01 | 36101394.56 | 83956731.54 | 65018737.5 | 64070218.19 | 100160076.04 | 229249031.73
MEPF | CP05A | Building Management System (BMS) | BETA Electromech | 13153169.03 | 12942571.82 | 19686260.64 | 45782001.48 | -7822148.14 | -7696906.64 | -11707357.12 | -27226411.9 | 5331020.89 | 5245665.18 | 7978903.52 | 18555589.58 | 4309500 | 4240500 | 6450000 | 15000000 | 15970.89 | 15715.17 | 23903.52 | 55589.58 | 0 | 0 | 500000 | 500000 | 1005550 | 989450 | 1505000 | 3500000 | 522056.65 | 520388.96 | 884742.99 | 1927188.6 | 1166739.82 | 1148058.99 | 1746251.74 | 4061050.55 | 4686337.71 | 4617995.14 | 7617394.78 | 16921727.63
MEPF | CP05B | Fire Detection & Alarm System | BETA | 8063419.94 | 7934315.4 | 12068467.01 | 28066202.35 | -2462825.44 | -2423392.8 | -3686094.46 | -8572312.7 | 5600594.5 | 5510922.6 | 8382372.55 | 19493889.65 | 4309500 | 4240500 | 6450000 | 15000000 | 439935.46 | 432891.6 | 658448.48 | 1531275.54 | 0 | 0 | 500000 | 500000 | 861900 | 848100 | 1290000 | 3000000 | 1321588.37 | 1318147.83 | 2123149.51 | 4762885.71 | 1449783.26 | 1426570.58 | 2169880.97 | 5046234.81 | 5483140.57 | 5413068.85 | 8851717.02 | 19747926.44
MEPF | CP07 | Plumbing & Sanitary Works | BETA Electromech | 16201704.69 | 15942296.96 | 24248983.7 | 56392985.36 | -4069335.16 | -4004180.47 | -6090546.88 | -14164062.5 | 12132369.53 | 11938116.49 | 18158436.82 | 42228922.86 | 11492000 | 11308000 | 17200000 | 40000000 | 220363.91 | 216835.63 | 329817.2 | 767016.74 | -28730 | -28270 | 1457000 | 1400000 | 430950 | 424050 | 645000 | 1500000 | 1728329.87 | 1723132.06 | 2549835.12 | 6001297.05 | 3663876.43 | 3605213.6 | 5483699.5 | 12752789.53 | 10179037.34 | 10038534.1 | 16697952.83 | 36915524.26
MEPF | CP08 | Fire Protection Works | BETA Electromech | 17019662.39 | 16747158.22 | 25473215.55 | 59240036.16 | -2557837.84 | -2516883.94 | -3828298.89 | -8903020.67 | 14461824.55 | 14230274.28 | 21644916.66 | 50337015.49 | 14968330 | 14728670 | 22403000 | 52100000 | -501516.62 | -493486.77 | -750616.6 | -1745619.99 | 0 | 0 | 2065967.1 | 2065967.1 | 0 | 0 | 0 | 0 | 2753830.44 | 2746997.82 | 3671411.41 | 9172239.67 | 5736611.32 | 5644761.65 | 8585948.03 | 19967321 | 11484032.5 | 11337419.41 | 18803813.88 | 41625265.78
MEPF | CP09 | Mechanical Works | BETA Electromech | 69480672.78 | 68368208.13 | 103991261.03 | 241840141.94 | -6609018.41 | -6503200.5 | -9891673.91 | -23003892.82 | 62871654.37 | 61865007.63 | 94099587.12 | 218836249.12 | 68123436.53 | 67032702.77 | 101959894.56 | 237116033.85 | -5251782.15 | -5167695.14 | -7860307.43 | -18279784.73 | 0 | 0 | 25000000 | 25000000 | 0 | 0 | 0 | 0 | 6612098.34 | 6596149.86 | 8718022.78 | 21926270.97 | 12688137.88 | 12484986.36 | 18990251.62 | 44163375.86 | 56795614.82 | 55976171.13 | 108827358.28 | 221599144.23
MEPF | CP13 | Vertical Transport System | JSEC | 52513754.71 | 51672949.73 | 78596987.56 | 182783692 | -9694223.12 | -9539007.58 | -14509279.3 | -33742510 | 42819531.59 | 42133942.15 | 64087708.26 | 149041182 | 45199789.68 | 44476089.6 | 67650224.72 | 157326104 | -2954858.09 | -2907547.45 | -4422516.46 | -10284922 | 0 | 0 | 0 |  | 574600 | 565400 | 860000 | 2000000 | 1410687.85 | 1393057.87 | 1648019.73 | 4451765.45 | 21197407.88 | 20858013.26 | 31726019.46 | 73781440.6 | 23032811.55 | 22668986.76 | 34009708.53 | 79711506.85
MEPF | CP15 | Generator Works | Power-Gen | 59984250.11 | 59023833.99 | 89778028.35 | 208786112.45 | -13107558.62 | -12897691.69 | -19617995.85 | -45623246.17 | 46876691.49 | 46126142.3 | 70160032.5 | 163162866.28 | 48888294.01 | 48105536.78 | 73170784.63 | 170164615.43 | -2011602.53 | -1979394.48 | -3010752.13 | -7001749.15 | 45968 | 45232 | 68800 | 160000 | 0 | 0 | 0 | 0 | 3565556.18 | 3544974.61 | 2647818.79 | 9758349.58 | 26173729.92 | 25754658.71 | 39174047.57 | 91102436.2 | 24314485.74 | 23961690.19 | 33702603.73 | 81978779.66
MEPF | OP12 | Power Transformer (OSM) | Gen-Tech | 9028247.04 | 8883694.53 | 13512517.32 | 31424458.89 | -1661852.06 | -1635243.91 | -2487282.92 | -5784378.89 | 7366394.98 | 7248450.62 | 11025234.4 | 25640080 | 6935444.98 | 6824400.62 | 10380234.4 | 24140080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 430950 | 424050 | 645000 | 1500000 | 387855 | 381645 | 580500 | 1350000 | 5074005.21 | 4992764.62 | 7594229.87 | 17660999.7 | 2680244.77 | 2637331 | 4011504.53 | 9329080.3
MEPF | OP13 | Lighting Fixture | Stealth Venture | 10926177.58 | 10751237.04 | 16353137.34 | 38030551.96 | -105337.19 | -103650.62 | -157657.47 | -366645.28 | 10820840.39 | 10647586.42 | 16195479.87 | 37663906.68 | 10055500 | 9894500 | 15050000 | 35000000 | 478040.39 | 470386.42 | 715479.87 | 1663906.68 | 0 | 0 | 0 | 287300 | 282700 | 430000 | 1000000 | 0 | 0 | 0 | 0 |  | 9543236.16 | 9390438.09 | 14283298.11 | 33216972.36 | 1277604.23 | 1257148.33 | 1912181.76 | 4446934.32
MEPF | OP15 | Plumbing Fixture | Lixil | 12294281.23 | 12097435.79 | 18400768.98 | 42792486 | -8188561.24 | -8057453.06 | -12255765.18 | -28501779.48 | 4105719.99 | 4039982.73 | 6145003.8 | 14290706.52 | 3217760 | 3166240 | 4816000 | 11200000 | 26059.98 | 25642.73 | 39003.8 | 90706.52 | 0 | 0 | 0 | 861900 | 848100 | 1290000 | 3000000 | 0 | 0 | 0 | 0 |  | 3081261.11 | 3031926.61 | 4611703.01 | 10724890.73 | 1024458.88 | 1008056.12 | 1533300.79 | 3565815.79
MEPF | OP18 | Fire Extinguishers | TBC | 2295213.7 | 2258464.72 | 3435231.09 | 7988909.5 | 18503.79 | 18207.52 | 27694.49 | 64405.8 | 2313717.49 | 2276672.24 | 3462925.58 | 8053315.3 | 2295213.7 | 2258464.72 | 3435231.09 | 7988909.5 | 18503.79 | 18207.52 | 27694.49 | 64405.8 | 0 | 0 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2313717.49 | 2276672.24 | 5462925.58 | 10053315.3
MEPF | OP27 | Supply and Delivery of Air Conditioning System - VRF | Daikin | 26992262.5 | 26560085.66 | 40399139.84 | 93951488 | -440199.57 | -433151.48 | -658843.78 | -1532194.83 | 26552062.93 | 26126934.18 | 39740296.06 | 92419293.17 | 22409400 | 22050600 | 33540000 | 78000000 | 2706162.93 | 2662834.18 | 4050296.06 | 9419293.17 | 0 | 0 | 0 | 1436500 | 1413500 | 2150000 | 5000000 | 0 | 0 | 0 | 0 |  | 12946831.91 | 12739538.4 | 19377437.26 | 45063807.57 | 13605231.01 | 13387395.78 | 20362858.81 | 47355485.6
ELV | CP05C | Community Distributive Antenna System (CDAS) | Cancelled | 4272268.31 | 4203864.43 | 6394275.57 | 14870408.31 | 0 | 0 | 0 | 0 | 4272268.31 | 4203864.43 | 6394275.57 | 14870408.31 | 4272268.31 | 4203864.43 | 6394275.57 | 14870408.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ELV | CP05D | Structured Cabling System & Public Address (SCS & PA) | BETA Electromech | 19625396.6 | 19311171.67 | 29373200.62 | 68309768.89 | -12086850.82 | -11893326.58 | -18090309.27 | -42070486.67 | 7538545.78 | 7417845.09 | 11282891.35 | 26239282.22 | 6607900 | 6502100 | 9890000 | 23000000 | 937319.85 | 922312.3 | 1402880.39 | 3262512.54 | 0 | 0 | 0 |  | 861900 | 848100 | 1290000 | 3000000 | 2917961.6 | 2912744.87 | 3500554.06 | 9331260.52 | 1062938.1 | 1142518.66 | 1544326.83 | 4467215.65 | 10262143.35 | 10042738.5 | 14539107.62 | 34843989.47
ELV | CP06E | Access Control, Guard Tour and | Cylix | 16800217.63 | 16531227.03 | 25144774.04 | 58476218.7 | -7382630.98 | -7264426.66 | -11049534.71 | -25696592.35 | 9417586.65 | 9266800.37 | 14095239.33 | 32779626.35 | 8044400 | 7915600 | 12040000 | 28000000 | -63313.35 | -62299.63 | -94760.67 | -220373.65 | 0 | 0 | 0 |  | 1436500 | 1413500 | 2150000 | 5000000 | 1484098.78 | 1481379.57 | 1927697.14 | 4893175.49 | 835083.91 | 835083.91 | 1129832.18 | 2800000 | 10066601.52 | 9913096.02 | 14893104.29 | 34872801.84
ELV | CP06F | Closed Circuit Television System (CCTV) | Prestige | 6810497.06 | 6701453.25 | 10193225.68 | 23705175.99 | -435023.7 | -428058.48 | -651097.09 | -1514179.27 | 6375473.36 | 6273394.77 | 9542128.59 | 22190996.72 | 6320600 | 6219400 | 9460000 | 22000000 | -88776.64 | -87355.23 | -132871.41 | -309003.28 | 0 | 0 | 0 |  | 143650 | 141350 | 215000 | 500000 | 1683074.92 | 1679986.2 | 2219791.67 | 5582852.79 | 3053000.37 | 3069839.15 | 4476036.59 | 10598876.11 | 5005547.91 | 4883541.82 | 7285883.67 | 17174973.4
ELV | CP26 | Seismic Monitoring | TBC | 258570 | 254430 | 387000 | 900000 | 0 | 0 | 0 | 0 | 258570 | 254430 | 387000 | 900000 | 258570 | 254430 | 387000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258570 | 254430 | 387000 | 900000
ELV | CP31 | Experiential Graphic Design (XGD) | TBC | 1723800 | 1696200 | 2580000 | 6000000 | 1328.79 | 1307.52 | 1988.79 | 4625.1 | 1725128.79 | 1697507.52 | 2581988.79 | 6004625.1 | 1723800 | 1696200 | 2580000 | 6000000 | 13798.17 | 13577.25 | 20651.64 | 48027.06 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1737598.17 | 1709777.25 | 2600651.64 | 6048027.06
External Works | CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | Green Enviro | 17895405.95 | 17608880.13 | 26783935.12 | 62288221.2 | -1248320.91 | -1228333.87 | -1868353.61 | -4345008.39 | 16647085.04 | 16380546.26 | 24915581.51 | 57943212.81 | 16950700 | 16679300 | 25370000 | 59000000 | -590914.96 | -581453.74 | -884418.49 | -2056787.19 | 6350.71 | 6404.82 | 5960.78 | 18716.3 | 287300 | 282700 | 430000 | 1000000 | 143650 | 141350 | 215000 | 500000 | 1610963.48 | 1610963.49 | 2678073.03 | 5900000 | 15186122.27 | 14917337.59 | 22458469.25 | 52561929.11
External Works | OP30 | Exterior Paving Tiles | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 0
Contingencies | Con | Contingencies | N/A | 14014644.7 | 13790254.29 | 20975625.55 | 48780524.54 | 131629064.9 | 129521533.76 | 197008346.36 | 458158945.01 | 145643709.6 | 143311788.04 | 217983971.91 | 506939469.55 | [8 empty] | 313038.89 | 308182.57 | 35530946.04 | 36152167.49 | 145643709.6 | 143311788.04 | 217983971.91 | 506939469.55 | 177891599.99 | 177481026.06 | 197273934.09 | 552646560.14 | 348434135.73 | 343189735.98 | 524608090.31 | 1218871338.32 | 706254663.78 | 697050124.28 | 1020024806.09 | 2423329594.15
Grand Total |  |  |  | 1008992898.19 | 992837773.47 | 1510152962.83 | 3511983634.49 | -131629064.91 | -129521533.75 | -197008346.38 | -458158945.02 | 877363833.28 | 863316239.72 | 1313144616.45 | 3053824689.47 | 850454419.58 | 836837676.35 | 1272869475.88 | 2960161571.8 | 12058459.39 | 11865389.71 | 18047815.95 | 41971665.04 | 313038.89 | 308182.58 | 35530946.05 | 38737867.49 | 18202150 | 19277150 | 32435000 | 54500000 | 177891600.03 | 177481026.07 | 197273934.09 | 552646560.13 | 348434135.71 | 343189736.01 | 524608090.29 | 1218871338.32 | 706254663.78 | 697050124.26 | 1020024806.1 | 2423329594.13