## Sheet1
| MACTAN BREAKDOWN | [6 empty] | NOTE:
WITH OSM SIMILAR TO THIS (Align with our numbers at book)
| A. Total Value of Contract including VO to date: | Php | 1278935136.96 |  |  |  |  | From Budget
| B. Total Payment Made to date : | Php |  | 596601808.33 |  |  |  | From F&C
| C. Total Cost to Complete (A-B) : | Php |  | 682333328.63
| D. Unbilled Amount | Php |  |  | 508142704.42
| D.1 Unbilled works done on site Php | Php |  |  |  | 180664196.88 |  |  | 290723731.1368
| D.2 Unbilled works to complete on site Php | Php |  |  |  | 327478507.54
| E. Balance due for payment Php | Php |  |  | 174190624.21
| F. Amount of works completed (B+D.1+E) Php | Php |  |  | 951456629.42 |  |  | 1061516163.6768 | 110059534.2568
| G. % of works completed (F/A) | Php |  |  |  |  | 74.39% | 83%
| H. Balance of works to complete (A-F) or D.2 Php | Php | 327478507.54 |  |  |  | 25.61% | 17% | 217418973.2832
KEY
ORANGE: | COMPLETED WORK
BLUE | FROM BOOK