## Note
Item | Description | Remarks
1 | Difference between WAP2-Project-Cost-Report_June-2020 & Indicative Forecast_Cost to Complete | Difference budgeted cost (Current Cost Plan) for some of the packages between the two file but with similar total cost.
2 | Difference between WAP2-Project-Cost-Report_June-2020 & Indicative Forecast_Cost to Complete | Provided information on the Indicative Forecast File is separated into buildings C,D & E while WAP-Project-Cost consider only the total.
2 | Curtain Wall & Structural Steel (Bldg.E) | Difference in Net Certfied Amount between May and June 2020 reporting
3 | Supply & Apply Waterproofing to Toilets, Doghouses & Roof Deck, Mechanical Rooms and Landscape Areas | Difference in Net Certfied Amount between May and June 2020 reporting
4 | Masonry & Rendering, Metal Doors & Hardwares, Office FloorMasonry & Rendering, Metal Doors & Hardwares, Office Floor Toppings Etc. | Difference in Net Certfied Amount between May and June 2020 reporting

## May
|  |  |  | A | B | C | D = A + B+ C | E | F | G = E + F | H | I | J = G+ H + I | K = D - J | L
Cost Centre | WP No. | Contract Package | CONTRACTOR | Initial Cost Plan | Additional Budget | Budget Transfer | Current Cost Plan | Orders Placed [Awarded] | Estimated Instruction [CRs] | Current Commitment | Orders Not Placed | Reserve ¦ Risk | Forecast Final Cost | Variance | Net Certfied Amount
0100 Consultants | C01 | Construction Management | TENMAN Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0100 Consultants | C02 | LEED Consultant | DEAN BARONE | 6144235.29 | 0 | -2500000 | 3644235.29 | 6144235.29 | -2500000 | 3644235.29 | 0 | 0 | 3644235.29 | 0 | 3644235.29
0100 Consultants | C03 | Architectural Services | AIDEA | 5000000 | 0 | 700000 | 5700000 | 5000000 | 700000 | 5700000 | 0 | 0 | 5700000 | 0 | 9310172.12
0100 Consultants | C04 | Structural Design Engineering Services | SY2 | 240000 | 0 | 500000 | 740000 | 240000 | 500000 | 740000 | 0 | 0 | 740000 | 0 | 240000
0100 Consultants | C05 | MEPF Design Engineering Services | (MPI) Meinhardt Philippines Inc. | 2464285.71 | 0 | 5505969.29 | 7970255 | 2464285.71 | 5505969.29 | 7970255 | 0 | 0 | 7970255 | 0 | 8841071.4
0100 Consultants | C06 | Building Information Modelling (BIM) Services | ESCA | 3500000 | 0 | 0 | 3500000 | 3500000 | 0 | 3500000 | 0 | 0 | 3500000 | 0 | 3500000
0100 Consultants | C07 | FaÃ§ade Design Services | LUMICON | 2010000 | 0 | 95000 | 2105000 | 2010000 | 95000 | 2105000 | 0 | 0 | 2105000 | 0 | 1490000
0100 Consultants | C08 | Landscape Design Services | INSPIRA | 300000 | 0 | 0 | 300000 | 300000 | 0 | 300000 | 0 | 0 | 300000 | 0 | 0
0100 Consultants | C09 | Cost Consultant / Quantity Surveying Services | (QSI) Quantity Solutions Inc. | 23577600 | 0 | -8577600 | 15000000 | 23577600 | -8577600 | 15000000 | 0 | 0 | 15000000 | 0 | 19520000
0100 Consultants | C10 | Third Party Testing and Commissioning | COMMTECH INC. | 10000000 | 0 | -300000 | 9700000 | 9700000 | 0 | 9700000 | 0 | 0 | 9700000 | 0 | 2475400
1000 Preliminaries | 1001 | Document Control / EDMS / Project Cloud | New Forma | 3000000 | 0 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 Preliminaries | CARI | Insurances | PNX Udenna Insurance Brokers | 6892745.21 | 0 | 3502004.42 | 10394749.63 | 6892745.21 | 3502004.42 | 10394749.63 | 0 | 0 | 10394749.63 | 0 | 10394749.63
2000 Structure & General Sitewide Prelims | CP01 | Structure and General Sitewide Prelims | TERP ASIA CONSTRUCTION CORPORATION | 427378789.81 | 0 | 103781456.46 | 531160246.27 | 365000000 | 166160246.27 | 531160246.27 | 0 | 0 | 531160246.27 | 0 | 368461391.14
2000 Structure & General Sitewide Prelims | OP01 | Cement (Supply only) | HOLCIM | 92161305 | 0 | -11466516.48 | 80694788.52 | 92161305 | -11466516.48 | 80694788.52 | 0 | 0 | 80694788.52 | 0 | 33041300.84
2000 Structure & General Sitewide Prelims | OP02 | Reinforcing Steel (OSM) | STEEL ASIA MANUFACTURING | 259599611.04 | 0 | -91180127.35 | 168419483.69 | 259599611.04 | -91180127.35 | 168419483.69 | 0 | 0 | 168419483.69 | 0 | 105752028.32
3000 Facade | CP30 | Building Maintenance / Access / BMU | VONOTEC, INC. | 13000000 | 0 | -1004000 | 11996000 | 10300000 | 696000 | 10996000 | 1000000 | 0 | 11996000 | 0 | 2372629.97
3000 Facade | CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | GLAZETECH GLASS & ALUMINUM INSTALLATION INC | 305793900.71 | 0 | -61100830.49 | 244693070.22 | 227456344.43 | 4689859.79 | 232146204.22 | 12546866 | 0 | 244693070.22 | 0 | 32768956.22
3000 Facade | CP11A | Curtain Wall & Structural Steel (Bldg.E) | DALKIA INCORPORATED | 224321762.87 | 0 | -28169047.17 | 196152715.7 | 184929323.48 | 770258.22 | 185699581.7 | 10453134 | 0 | 196152715.7 | 0 | 78288687.22
3000 Facade | CP21 | Supply & Apply Waterproofing to Toilets, Doghouses & Roof Deck, Mechanical Rooms and Landscape Areas | HIGH PERFORMANCE SOLUTIONS INC. | 22296090.91 | 0 | -4556456.15 | 17739634.76 | 18606970.55 | -1367335.79 | 17239634.76 | 500000 | 0 | 17739634.76 | 0 | 10336205.36
4000 Builders Work | CP01A | Masonry & Rendering, Metal Doors & Hardwares, Office FloorMasonry & Rendering, Metal Doors & Hardwares, Office Floor Toppings Etc. | TERP ASIA CONSTRUCTION CORPORATION | 158796484.86 | 0 | -18670950.04 | 140125534.82 | 132000000 | 4125534.82 | 136125534.82 | 4000000 | 0 | 140125534.82 | 0 | 27556944.89
4000 Builders Work | OP33 | Door Hardwares | TECHNOINOX CORPORATION | 13042110.19 | 0 | 738542.91 | 13780653.1 | 13300000 | 480653.1 | 13780653.1 | 0 | 0 | 13780653.1 | 0 | 0
5000 Fit-Out | CP20 | Interior Fit-Out Works | EE BLACK LTD | 328382908.5 | 0 | -16810571.14 | 311572337.36 | 310000000 | -3427662.64 | 306572337.36 | 5000000 | 0 | 311572337.36 | 0 | 35613423.71
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP04 | Electrical Works | BETA ELECTRIC CORPORATION | 332452945.21 | 0 | -46236955.16 | 286215990.05 | 290173000 | -3957009.95 | 286215990.05 | 0 | 0 | 286215990.05 | 0 | 83956731.54
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05A | Building Management System (BMS) | BETA ELECTRIC CORPORATION | 45782001.48 | 0 | -27226411.9 | 18555589.58 | 15000000 | 55589.58 | 15055589.58 | 3500000 | 0 | 18555589.58 | 0 | 4061050.55
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05B | Fire Detection & Alarm System (FDAS) | BETA ELECTRIC CORPORATION | 28066202.35 | 0 | -8534926.81 | 19531275.54 | 15000000 | 1531275.54 | 16531275.54 | 3000000 | 0 | 19531275.54 | 0 | 5046234.81
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP07 | Plumbing & Sanitary Works | BETA ELECTRIC CORPORATION | 56392985.36 | 0 | -14227266.32 | 42165719.04 | 40000000 | 665719.04 | 40665719.04 | 1500000 | 0 | 42165719.04 | 0 | 12752789.53
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP08 | Fire Protection Works | BETA ELECTRIC CORPORATION | 59240036.16 | 0 | -8819689.05 | 50420347.11 | 52100000 | -1679652.89 | 50420347.11 | 0 | 0 | 50420347.11 | 0 | 19967321
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP09 | Mechanical Works | BETA ELECTRIC CORPORATION | 241840141.94 | 0 | -23003892.82 | 218836249.12 | 237116033.85 | -18279784.73 | 218836249.12 | 0 | 0 | 218836249.12 | 0 | 44163375.86
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP13 | Vertical Transport System | JARDINE SCHINDLER ELEVATOR CORPORATION | 182783692 | 0 | -32409850 | 150373842 | 157326104 | -8952262 | 148373842 | 2000000 | 0 | 150373842 | 0 | 73781440.6
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP15 | Generator Works | POWERGEN INTEGRATED SOLUTIONS COMPANY, LTD | 208786112.45 | 0 | -45463246.17 | 163322866.28 | 170164615.43 | -6841749.15 | 163322866.28 | 0 | 0 | 163322866.28 | 0 | 91102436.2
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP12 | Power Transformer (OSM) | GENTEC DISTRIBUTION CORPORATION | 31424458.89 | 0 | -5784378.89 | 25640080 | 24140080 | 0 | 24140080 | 1500000 | 0 | 25640080 | 0 | 17660999.7
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP13 | Lighting Fixture | STEALTH VENTURES CORPORATION | 38030551.96 | 0 | -391450.09 | 37639101.87 | 35000000 | 1639101.87 | 36639101.87 | 1000000 | 0 | 37639101.87 | 0 | 33216972.36
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP15 | Plumbing Fixture | LIXIL PHILIPPINES | 42792486 | 0 | -28501779.48 | 14290706.52 | 11200000 | 90706.52 | 11290706.52 | 3000000 | 0 | 14290706.52 | 0 | 10724890.73
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP18 | Fire Extinguishers | *** TBC *** | 7988909.5 | 0 | 64405.8 | 8053315.3 | 7988909.5 | 64405.8 | 8053315.3 | 0 | 0 | 8053315.3 | 0 | 0
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP27 | Supply and Delivery of Air Conditioning System - VRF | DAIKIN AIRCONDITIONING PHILIPPINES INC. | 93951488 | 0 | -1532194.83 | 92419293.17 | 78000000 | 9419293.17 | 87419293.17 | 5000000 | 0 | 92419293.17 | 0 | 45063807.57
7000 Electrical Low Voltage (ELV) | CP05C | Community Distributive Antenna System (CDAS) | *** TBC *** | 14870408.31 | 0 | 0 | 14870408.31 | 14870408.31 | 0 | 14870408.31 | 0 | 0 | 14870408.31 | 0 | 0
7000 Electrical Low Voltage (ELV) | CP05D | Structured Cabling System & Public Address (SCS & PA) | BETA ELECTRIC CORPORATION | 68309768.89 | 0 | -39047256.35 | 29262512.54 | 23000000 | 3262512.54 | 26262512.54 | 3000000 | 0 | 29262512.54 | 0 | 4467215.65
7000 Electrical Low Voltage (ELV) | CP06E | Access Control, Guard Tour and Turnstile | SUBIC BAY CONSULTANCY AND ALLIED SERVICES CORPORATION | 58476218.7 | 0 | -25696592.35 | 32779626.35 | 28000000 | -220373.65 | 27779626.35 | 5000000 | 0 | 32779626.35 | 0 | 2800000
7000 Electrical Low Voltage (ELV) | CP06F | Closed Circuit Television System (CCTV) | PRESTIGE ADVANCE SYSTEMS INCORPORATED | 23705175.99 | 0 | -1514179.27 | 22190996.72 | 22000000 | -309003.28 | 21690996.72 | 500000 | 0 | 22190996.72 | 0 | 10598876.11
7000 Electrical Low Voltage (ELV) | CP26 | Seismic Monitoring | *** TBC *** | 900000 | 0 | 0 | 900000 | 900000 | 0 | 900000 | 0 | 0 | 900000 | 0 | 0
7000 Electrical Low Voltage (ELV) | CP31 | Experiential Graphic Design (XGD) | *** TBC *** | 6000000 | 0 | 48027.06 | 6048027.06 | 6000000 | 48027.06 | 6048027.06 | 0 | 0 | 6048027.06 | 0 | 0
8000 External Works | CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | GREEN ENVIROSCAPE SERVICES INC. | 62288221.2 | 0 | -4345008.39 | 57943212.81 | 59000000 | -2056787.19 | 56943212.81 | 1000000 | 0 | 57943212.81 | 0 | 5900000
8000 External Works | OP30 | Exterior Paving Tiles | GREEN ENVIROSCAPE SERVICES INC. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 Contingencies | Con | Buying Gains/ Losses | *** TBC *** | 48780524.54 | 0 | 445135770.76 | 493916295.3 | 0 | 0 | 0 | 493916295.3 |  | 493916295.3 | 0 | 0
[7 empty] | 3560764159.03 | 2960161571.8

## June
Cost Centre | WP No. | ContractPackage | CONTRACTOR | Initial Cost Plan | Additional Budget | Budget Transfer | Current Cost Plan | Orders Placed [Awarded] | Estimated Instruction [CRs] | Current Commitment | Orders Not Placed | Reserve ¦ Risk | Forecast Final Cost | Variance | Net Certfied Amount |  | Awarded_Total | Awarded_Total | Budget_Total | Budget_Total | Check_Awarded_Total | Check_Budget_Total | Diff_Awarded | Diff_Budget
0100 Consultants | C01 | Construction Management | TENMAN Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C01 | 0 | 0 | 0 | 0 | TRUE | TRUE | 0 | 0
0100 Consultants | C02 | LEED Consultant | DEAN BARONE | 6144235.29 | 0 | -2500000 | 3644235.29 | 6144235.29 | -2500000 | 3644235.29 | 0 | 0 | 3644235.29 | 0 | 3644235.29 | C02 | 6144235.29 | 6144235.29 | 3644235.29 | 3644235.29 | TRUE | TRUE | 0 | 0
0100 Consultants | C03 | Architectural Services | AIDEA | 5000000 | 0 | 700000 | 5700000 | 5000000 | 700000 | 5700000 | 0 | 0 | 5700000 | 0 | 9310172.12 | C03 | 5000000 | 5000000 | 5700000 | 5700000 | TRUE | TRUE | 0 | 0
0100 Consultants | C04 | Structural Design Engineering Services | SY2 | 240000 | 0 | 500000 | 740000 | 240000 | 500000 | 740000 | 0 | 0 | 740000 | 0 | 240000 | C04 | 240000 | 240000 | 740000 | 740000 | TRUE | TRUE | 0 | 0
0100 Consultants | C05 | MEPF Design Engineering Services | (MPI) Meinhardt Philippines Inc. | 2464285.71 | 0 | 5505969.29 | 7970255 | 2464285.71 | 5505969.29 | 7970255 | 0 | 0 | 7970255 | 0 | 8841071.4 | C05 | 2464285.71 | 2464285.71 | 7970255 | 7970255 | TRUE | TRUE | 0 | 0
0100 Consultants | C06 | Building Information Modelling (BIM) Services | ESCA | 3500000 | 0 | 0 | 3500000 | 3500000 | 0 | 3500000 | 0 | 0 | 3500000 | 0 | 3500000 | C06 | 3500000 | 3500000 | 3500000 | 3500000 | TRUE | TRUE | 0 | 0
0100 Consultants | C07 | FaÃ§ade Design Services | LUMICON | 2010000 | 0 | 95000 | 2105000 | 2010000 | 95000 | 2105000 | 0 | 0 | 2105000 | 0 | 1490000 | C07 | 2010000 | 2010000 | 2105000 | 2105000 | TRUE | TRUE | 0 | 0
0100 Consultants | C08 | Landscape Design Services | INSPIRA | 300000 | 0 | 0 | 300000 | 300000 | 0 | 300000 | 0 | 0 | 300000 | 0 | 0 | C08 | 300000 | 300000 | 300000 | 300000 | TRUE | TRUE | 0 | 0
0100 Consultants | C09 | Cost Consultant / Quantity Surveying Services | (QSI) Quantity Solutions Inc. | 23577600 | 0 | -8577600 | 15000000 | 23577600 | -8577600 | 15000000 | 0 | 0 | 15000000 | 0 | 19520000 | C09 | 23577600 | 23577600 | 15000000 | 15000000 | TRUE | TRUE | 0 | 0
0100 Consultants | C10 | Third Party Testing and Commissioning | COMMTECH INC. | 10000000 | 0 | -300000 | 9700000 | 9700000 | 0 | 9700000 | 0 | 0 | 9700000 | 0 | 2475400 | C10 | 9700000 | 9700000 | 9700000 | 9700000 | TRUE | TRUE | 0 | 0
1000 Preliminaries | 1001 | Document Control / EDMS / Project Cloud | New Forma | 3000000 | 0 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1001 |  | 0 |  | 0 | TRUE | TRUE | 0 | 0
1000 Preliminaries | CARI | Insurances | PNX Udenna Insurance Brokers | 6892745.21 | 0 | 3502004.42 | 10394749.63 | 6892745.21 | 3502004.42 | 10394749.63 | 0 | 0 | 10394749.63 | 0 | 10394749.63 | CARI | 6892745.21 | 6892745.21 | 10394749.63 | 10394749.63 | TRUE | TRUE | 0 | -1.8626e-09
2000 Structure & General Sitewide Prelims | CP01 | Structure and General Sitewide Prelims | TERP ASIA CONSTRUCTION CORPORATION | 427378789.81 | 0 | 103781456.46 | 531160246.27 | 365000000 | 166160246.27 | 531160246.27 | 0 | 0 | 531160246.27 | 0 | 368461391.14 | CP01 | 365000000 | 365000000 | 530601881.32 | 531160246.27 | TRUE | FALSE | 0 | -558364.95
2000 Structure & General Sitewide Prelims | OP01 | Cement (Supply only) | HOLCIM | 92161305 | 0 | -11466516.48 | 80694788.52 | 92161305 | -11466516.48 | 80694788.52 | 0 | 0 | 80694788.52 | 0 | 33041300.84 | OP01 | 92161305 | 92161305 | 80523674.02 | 80694788.52 | TRUE | FALSE | 0 | -171114.5
2000 Structure & General Sitewide Prelims | OP02 | Reinforcing Steel (OSM) | STEEL ASIA MANUFACTURING | 259599611.04 | 0 | -91180127.35 | 168419483.69 | 259599611.04 | -91180127.35 | 168419483.69 | 0 | 0 | 168419483.69 | 0 | 105752028.32 | OP02 | 259599611.04 | 259599611.04 | 167747871.64 | 168419483.69 | TRUE | FALSE | 2.9802e-08 | -671612.05
3000 Facade | CP30 | Building Maintenance / Access / BMU | VONOTEC, INC. | 13000000 | 0 | -1004000 | 11996000 | 10300000 | 696000 | 10996000 | 1000000 | 0 | 11996000 | 0 | 2372629.97 | CP30 | 10300000 | 10300000 | 11300000 | 11996000 | TRUE | FALSE | 0 | -696000
3000 Facade | CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | GLAZETECH GLASS & ALUMINUM INSTALLATION INC | 305793900.71 | 0 | -61100830.49 | 244693070.22 | 227456344.43 | 4689859.79 | 232146204.22 | 12546866 | 0 | 244693070.22 | 0 | 32768956.22 | CP11 | 227456344.42 | 227456344.43 | 242860257.91 | 244693070.22 | FALSE | FALSE | -0.01 | -1832812.31
3000 Facade | CP11A | Curtain Wall & Structural Steel (Bldg.E) | DALKIA INCORPORATED | 224321762.87 | 0 | -28169047.17 | 196152715.7 | 184929323.48 | 770258.22 | 185699581.7 | 10453134 | 0 | 196152715.7 | 0 | 80681651.62 | CP11A | 184929323.49 | 184929323.48 | 193661800.77 | 196152715.7 | FALSE | FALSE | 0.01 | -2490914.93
3000 Facade | CP21 | Supply & Apply Waterproofing to Toilets, Doghouses & Roof Deck, Mechanical Rooms and Landscape Areas | HIGH PERFORMANCE SOLUTIONS INC. | 22296090.91 | 0 | -4556456.15 | 17739634.76 | 18606970.55 | -1367335.79 | 17239634.76 | 500000 | 0 | 17739634.76 | 0 | 10482491.36 | CP21 | 18606970.55 | 18606970.55 | 17564567.25 | 17739634.76 | TRUE | FALSE | 0 | -175067.51
4000 Builders Work | CP01A | Masonry & Rendering, Metal Doors & Hardwares, Office FloorMasonry & Rendering, Metal Doors & Hardwares, Office Floor Toppings Etc. | TERP ASIA CONSTRUCTION CORPORATION | 158796484.86 | 0 | -18670950.04 | 140125534.82 | 132000000 | 4125534.82 | 136125534.82 | 4000000 | 0 | 140125534.82 | 0 | 28657621.68 | CP01A | 132000000 | 132000000 | 138248110.46 | 140125534.82 | TRUE | FALSE | 0 | -1877424.36
4000 Builders Work | OP33 | Door Hardwares | TECHNOINOX CORPORATION | 13042110.19 | 0 | 738542.91 | 13780653.1 | 13300000 | 480653.1 | 13780653.1 | 0 | 0 | 13780653.1 | 0 | 0 | OP33 | 13300000 | 13300000 | 13717153.1 | 13780653.1 | TRUE | FALSE | 0 | -63500
5000 Fit-Out | CP20 | Interior Fit-Out Works | EE BLACK LTD | 328382908.5 | 0 | -16810571.14 | 311572337.36 | 310000000 | -3427662.64 | 306572337.36 | 5000000 | 0 | 311572337.36 | 0 | 35613423.71 | CP20 | 310000000 | 310000000 | 310771153.54 | 311572337.36 | TRUE | FALSE | 0 | -801183.82
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP04 | Electrical Works | BETA ELECTRIC CORPORATION | 332452945.21 | 0 | -46236955.16 | 286215990.05 | 290173000 | -3957009.95 | 286215990.05 | 0 | 0 | 286215990.05 | 0 | 83956731.54 | CP04 | 290173000 | 290173000 | 287122811.35 | 286215990.05 | TRUE | FALSE | 0 | 906821.3
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05A | Building Management System (BMS) | BETA ELECTRIC CORPORATION | 45782001.48 | 0 | -27226411.9 | 18555589.58 | 15000000 | 55589.58 | 15055589.58 | 3500000 | 0 | 18555589.58 | 0 | 4061050.55 | CP05A | 15000000 | 15000000 | 18555589.59 | 18555589.58 | TRUE | FALSE | 0 | 0.01
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05B | Fire Detection & Alarm System (FDAS) | BETA ELECTRIC CORPORATION | 28066202.35 | 0 | -8534926.81 | 19531275.54 | 15000000 | 1531275.54 | 16531275.54 | 3000000 | 0 | 19531275.54 | 0 | 5046234.81 | CP05B | 15000000 | 15000000 | 19493889.65 | 19531275.54 | TRUE | FALSE | 0 | -37385.89
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP07 | Plumbing & Sanitary Works | BETA ELECTRIC CORPORATION | 56392985.36 | 0 | -14227266.32 | 42165719.04 | 40000000 | 665719.04 | 40665719.04 | 1500000 | 0 | 42165719.04 | 0 | 12752789.53 | CP07 | 40000000 | 40000000 | 42228922.84 | 42165719.04 | TRUE | FALSE | 0 | 63203.8
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP08 | Fire Protection Works | BETA ELECTRIC CORPORATION | 59240036.16 | 0 | -8819689.05 | 50420347.11 | 52100000 | -1679652.89 | 50420347.11 | 0 | 0 | 50420347.11 | 0 | 20425971.51 | CP08 | 52100000 | 52100000 | 50337015.49 | 50420347.11 | TRUE | FALSE | 0 | -83331.62
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP09 | Mechanical Works | BETA ELECTRIC CORPORATION | 241840141.94 | 0 | -23003892.82 | 218836249.12 | 237116033.85 | -18279784.73 | 218836249.12 | 0 | 0 | 218836249.12 | 0 | 44824317.45 | CP09 | 237116033.86 | 237116033.85 | 218836249.12 | 218836249.12 | FALSE | TRUE | 0.01 | 0
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP13 | Vertical Transport System | JARDINE SCHINDLER ELEVATOR CORPORATION | 182783692 | 0 | -32409850 | 150373842 | 157326104 | -8952262 | 148373842 | 2000000 | 0 | 150373842 | 0 | 73781440.6 | CP13 | 157326104 | 157326104 | 149041182 | 150373842 | TRUE | FALSE | 0 | -1332660
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP15 | Generator Works | POWERGEN INTEGRATED SOLUTIONS COMPANY, LTD | 208786112.45 | 0 | -45463246.17 | 163322866.28 | 170164615.43 | -6841749.15 | 163322866.28 | 0 | 0 | 163322866.28 | 0 | 91102436.2 | CP15 | 170164615.42 | 170164615.43 | 163162866.29 | 163322866.28 | FALSE | FALSE | -0.01 | -159999.99
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP12 | Power Transformer (OSM) | GENTEC DISTRIBUTION CORPORATION | 31424458.89 | 0 | -5784378.89 | 25640080 | 24140080 | 0 | 24140080 | 1500000 | 0 | 25640080 | 0 | 19353192.3 | OP12 | 24140080 | 24140080 | 25640080 | 25640080 | TRUE | TRUE | 0 | 0
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP13 | Lighting Fixture | STEALTH VENTURES CORPORATION | 38030551.96 | 0 | -391450.09 | 37639101.87 | 35000000 | 1639101.87 | 36639101.87 | 1000000 | 0 | 37639101.87 | 0 | 33216972.36 | OP13 | 35000000 | 35000000 | 37663906.68 | 37639101.87 | TRUE | FALSE | 0 | 24804.81
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP15 | Plumbing Fixture | LIXIL PHILIPPINES | 42792486 | 0 | -28501779.48 | 14290706.52 | 11200000 | 90706.52 | 11290706.52 | 3000000 | 0 | 14290706.52 | 0 | 10724890.73 | OP15 | 11200000 | 11200000 | 14290706.52 | 14290706.52 | TRUE | TRUE | 0 | 0
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP18 | Fire Extinguishers | *** TBC *** | 7988909.5 | 0 | 64405.8 | 8053315.3 | 7988909.5 | 64405.8 | 8053315.3 | 0 | 0 | 8053315.3 | 0 | 0 | OP18 | 7988909.51 | 7988909.5 | 8053315.31 | 8053315.3 | FALSE | FALSE | 0.01 | 0.01
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP27 | Supply and Delivery of Air Conditioning System - VRF | DAIKIN AIRCONDITIONING PHILIPPINES INC. | 93951488 | 0 | -1532194.83 | 92419293.17 | 78000000 | 9419293.17 | 87419293.17 | 5000000 | 0 | 92419293.17 | 0 | 45063807.57 | OP27 | 78000000 | 78000000 | 92419293.17 | 92419293.17 | TRUE | TRUE | 0 | 0
7000 Electrical Low Voltage (ELV) | CP05C | Community Distributive Antenna System (CDAS) | *** TBC *** | 14870408.31 | 0 | 0 | 14870408.31 | 14870408.31 | 0 | 14870408.31 | 0 | 0 | 14870408.31 | 0 | 0 | CP05C | 14870408.31 | 14870408.31 | 14870408.31 | 14870408.31 | TRUE | TRUE | -1.8626e-09 | -1.8626e-09
7000 Electrical Low Voltage (ELV) | CP05D | Structured Cabling System & Public Address (SCS & PA) | BETA ELECTRIC CORPORATION | 68309768.89 | 0 | -39047256.35 | 29262512.54 | 23000000 | 3262512.54 | 26262512.54 | 3000000 | 0 | 29262512.54 | 0 | 4467215.65 | CP05D | 23000000 | 23000000 | 26239282.22 | 29262512.54 | TRUE | FALSE | 0 | -3023230.32
7000 Electrical Low Voltage (ELV) | CP06E | Access Control, Guard Tour and Turnstile | SUBIC BAY CONSULTANCY AND ALLIED SERVICES CORPORATION | 58476218.7 | 0 | -25696592.35 | 32779626.35 | 28000000 | -220373.65 | 27779626.35 | 5000000 | 0 | 32779626.35 | 0 | 2800000 | CP06E | 28000000 | 28000000 | 32779626.35 | 32779626.35 | TRUE | TRUE | 0 | -7.4506e-09
7000 Electrical Low Voltage (ELV) | CP06F | Closed Circuit Television System (CCTV) | PRESTIGE ADVANCE SYSTEMS INCORPORATED | 23705175.99 | 0 | -1514179.27 | 22190996.72 | 22000000 | -309003.28 | 21690996.72 | 500000 | 0 | 22190996.72 | 0 | 10598876.11 | CP06F | 22000000 | 22000000 | 22190996.72 | 22190996.72 | TRUE | TRUE | 0 | 0
7000 Electrical Low Voltage (ELV) | CP26 | Seismic Monitoring | *** TBC *** | 900000 | 0 | 0 | 900000 | 900000 | 0 | 900000 | 0 | 0 | 900000 | 0 | 0 | CP26 | 900000 | 900000 | 900000 | 900000 | TRUE | TRUE | 0 | 0
7000 Electrical Low Voltage (ELV) | CP31 | Experiential Graphic Design (XGD) | *** TBC *** | 6000000 | 0 | 48027.06 | 6048027.06 | 6000000 | 48027.06 | 6048027.06 | 0 | 0 | 6048027.06 | 0 | 0 | CP31 | 6000000 | 6000000 | 6004625.1 | 6048027.06 | TRUE | FALSE | 0 | -43401.96
8000 External Works | CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | GREEN ENVIROSCAPE SERVICES INC. | 62288221.2 | 0 | -4345008.39 | 57943212.81 | 59000000 | -2056787.19 | 56943212.81 | 1000000 | 0 | 57943212.81 | 0 | 5900000 | CP17 | 59000000 | 59000000 | 57943212.81 | 57943212.81 | TRUE | TRUE | 0 | 0
8000 External Works | OP30 | Exterior Paving Tiles | GREEN ENVIROSCAPE SERVICES INC. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OP30 |  | 0 |  | 0 | TRUE | TRUE | 0 | 0
9000 Contingencies | Con | Buying Gains/ Losses | *** TBC *** | 48780524.54 | 0 | 445135770.76 | 493916295.3 | 0 | 0 | 0 | 493916295.3 |  | 493916295.3 | 0 | 0 | Con | 0 | 0 | 506939469.55 | 493916295.3 | TRUE | FALSE | 0 | 13023174.25
[16 empty] | Grand_Total | 2960161571.81 | 2960161571.8 | 3560764159 | 3560764159.03 | FALSE | FALSE

## May-June_Comp
|  |  |  | A | B | C | D = A + B+ C | E | F | G = E + F | H | I | J = G+ H + I | K = D - J | L
Cost Centre | WP No. | Contract Package | CONTRACTOR | Initial Cost Plan | Additional Budget | Budget Transfer | Current Cost Plan | Orders Placed [Awarded] | Estimated Instruction [CRs] | Current Commitment | Orders Not Placed | Reserve ¦ Risk | Forecast Final Cost | Variance | Net Certfied Amount
0100 Consultants | C01 | Construction Management | TENMAN Project Management | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C02 | LEED Consultant | DEAN BARONE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C03 | Architectural Services | AIDEA | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C04 | Structural Design Engineering Services | SY2 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C05 | MEPF Design Engineering Services | (MPI) Meinhardt Philippines Inc. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C06 | Building Information Modelling (BIM) Services | ESCA | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C07 | FaÃ§ade Design Services | LUMICON | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C08 | Landscape Design Services | INSPIRA | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C09 | Cost Consultant / Quantity Surveying Services | (QSI) Quantity Solutions Inc. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
0100 Consultants | C10 | Third Party Testing and Commissioning | COMMTECH INC. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
1000 Preliminaries | 1001 | Document Control / EDMS / Project Cloud | New Forma | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
1000 Preliminaries | CARI | Insurances | PNX Udenna Insurance Brokers | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
2000 Structure & General Sitewide Prelims | CP01 | Structure and General Sitewide Prelims | TERP ASIA CONSTRUCTION CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
2000 Structure & General Sitewide Prelims | OP01 | Cement (Supply only) | HOLCIM | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
2000 Structure & General Sitewide Prelims | OP02 | Reinforcing Steel (OSM) | STEEL ASIA MANUFACTURING | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
3000 Facade | CP30 | Building Maintenance / Access / BMU | VONOTEC, INC. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
3000 Facade | CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | GLAZETECH GLASS & ALUMINUM INSTALLATION INC | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
3000 Facade | CP11A | Curtain Wall & Structural Steel (Bldg.E) | DALKIA INCORPORATED | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
3000 Facade | CP21 | Supply & Apply Waterproofing to Toilets, Doghouses & Roof Deck, Mechanical Rooms and Landscape Areas | HIGH PERFORMANCE SOLUTIONS INC. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
4000 Builders Work | CP01A | Masonry & Rendering, Metal Doors & Hardwares, Office FloorMasonry & Rendering, Metal Doors & Hardwares, Office Floor Toppings Etc. | TERP ASIA CONSTRUCTION CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
4000 Builders Work | OP33 | Door Hardwares | TECHNOINOX CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
5000 Fit-Out | CP20 | Interior Fit-Out Works | EE BLACK LTD | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP04 | Electrical Works | BETA ELECTRIC CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05A | Building Management System (BMS) | BETA ELECTRIC CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05B | Fire Detection & Alarm System (FDAS) | BETA ELECTRIC CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP07 | Plumbing & Sanitary Works | BETA ELECTRIC CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP08 | Fire Protection Works | BETA ELECTRIC CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP09 | Mechanical Works | BETA ELECTRIC CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP13 | Vertical Transport System | JARDINE SCHINDLER ELEVATOR CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP15 | Generator Works | POWERGEN INTEGRATED SOLUTIONS COMPANY, LTD | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP12 | Power Transformer (OSM) | GENTEC DISTRIBUTION CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP13 | Lighting Fixture | STEALTH VENTURES CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP15 | Plumbing Fixture | LIXIL PHILIPPINES | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP18 | Fire Extinguishers | *** TBC *** | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP27 | Supply and Delivery of Air Conditioning System - VRF | DAIKIN AIRCONDITIONING PHILIPPINES INC. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7000 Electrical Low Voltage (ELV) | CP05C | Community Distributive Antenna System (CDAS) | *** TBC *** | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7000 Electrical Low Voltage (ELV) | CP05D | Structured Cabling System & Public Address (SCS & PA) | BETA ELECTRIC CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7000 Electrical Low Voltage (ELV) | CP06E | Access Control, Guard Tour and Turnstile | SUBIC BAY CONSULTANCY AND ALLIED SERVICES CORPORATION | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7000 Electrical Low Voltage (ELV) | CP06F | Closed Circuit Television System (CCTV) | PRESTIGE ADVANCE SYSTEMS INCORPORATED | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7000 Electrical Low Voltage (ELV) | CP26 | Seismic Monitoring | *** TBC *** | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
7000 Electrical Low Voltage (ELV) | CP31 | Experiential Graphic Design (XGD) | *** TBC *** | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
8000 External Works | CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | GREEN ENVIROSCAPE SERVICES INC. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
8000 External Works | OP30 | Exterior Paving Tiles | GREEN ENVIROSCAPE SERVICES INC. | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
9000 Contingencies | Con | Buying Gains/ Losses | *** TBC *** | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
[7 empty] | 0 | 0

## summary
Cost Centre | WP No. | ContractPackage | CONTRACTOR | Initial Cost Plan | Additional Budget | Budget Transfer | Current Cost Plan | Orders Placed [Awarded] | Estimated Instruction [CRs] | Current Commitment | Orders Not Placed | Reserve ¦ Risk | Forecast Final Cost | Variance | Net Certfied Amount | ConfirmedPayment |  | Awarded_C | Awarded_D | Awarded_E | Awarded_Total | Awarded_Total | Budget_Total | Budget_Total | Check_Awarded_Total | Check_Budget_Total | Diff_Awarded | Diff_Budget
0100 Consultants | C01 | Construction Management | TENMAN Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | C01 |  |  |  | 0 | 0 | 0 | 0 | TRUE | TRUE | 0 | 0
0100 Consultants | C02 | LEED Consultant | DEAN BARONE | 6144235.29 | 0 | -2500000 | 3644235.29 | 6144235.29 | -2500000 | 3644235.29 | 0 | 0 | 3644235.29 | 0 | 3644235.29 |  | C02 |  |  |  | 6144235.29 | 6144235.29 | 3644235.29 | 3644235.29 | TRUE | TRUE | 0 | 0
0100 Consultants | C03 | Architectural Services | AIDEA | 5000000 | 0 | 700000 | 5700000 | 5000000 | 700000 | 5700000 | 0 | 0 | 5700000 | 0 | 9310172.12 |  | C03 |  |  |  | 5000000 | 5000000 | 5700000 | 5700000 | TRUE | TRUE | 0 | 0
0100 Consultants | C04 | Structural Design Engineering Services | SY2 | 240000 | 0 | 500000 | 740000 | 240000 | 500000 | 740000 | 0 | 0 | 740000 | 0 | 240000 |  | C04 |  |  |  | 240000 | 240000 | 740000 | 740000 | TRUE | TRUE | 0 | 0
0100 Consultants | C05 | MEPF Design Engineering Services | (MPI) Meinhardt Philippines Inc. | 2464285.71 | 0 | 5505969.29 | 7970255 | 2464285.71 | 5505969.29 | 7970255 | 0 | 0 | 7970255 | 0 | 8841071.4 |  | C05 |  |  |  | 2464285.71 | 2464285.71 | 7970255 | 7970255 | TRUE | TRUE | 0 | 0
0100 Consultants | C06 | Building Information Modelling (BIM) Services | ESCA | 3500000 | 0 | 0 | 3500000 | 3500000 | 0 | 3500000 | 0 | 0 | 3500000 | 0 | 3500000 |  | C06 |  |  |  | 3500000 | 3500000 | 3500000 | 3500000 | TRUE | TRUE | 0 | 0
0100 Consultants | C07 | FaÃ§ade Design Services | LUMICON | 2010000 | 0 | 95000 | 2105000 | 2010000 | 95000 | 2105000 | 0 | 0 | 2105000 | 0 | 1490000 |  | C07 |  |  |  | 2010000 | 2010000 | 2105000 | 2105000 | TRUE | TRUE | 0 | 0
0100 Consultants | C08 | Landscape Design Services | INSPIRA | 300000 | 0 | 0 | 300000 | 300000 | 0 | 300000 | 0 | 0 | 300000 | 0 | 0 |  | C08 |  |  |  | 300000 | 300000 | 300000 | 300000 | TRUE | TRUE | 0 | 0
0100 Consultants | C09 | Cost Consultant / Quantity Surveying Services | (QSI) Quantity Solutions Inc. | 23577600 | 0 | -8577600 | 15000000 | 23577600 | -8577600 | 15000000 | 0 | 0 | 15000000 | 0 | 19520000 |  | C09 |  |  |  | 23577600 | 23577600 | 15000000 | 15000000 | TRUE | TRUE | 0 | 0
0100 Consultants | C10 | Third Party Testing and Commissioning | COMMTECH INC. | 10000000 | 0 | -300000 | 9700000 | 9700000 | 0 | 9700000 | 0 | 0 | 9700000 | 0 | 2475400 |  | C10 |  |  |  | 9700000 | 9700000 | 9700000 | 9700000 | TRUE | TRUE | 0 | 0
1000 Preliminaries | 1001 | Document Control / EDMS / Project Cloud | New Forma | 3000000 | 0 | -3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1001 |  |  |  |  | 0 |  | 0 | TRUE | TRUE | 0 | 0
1000 Preliminaries | CARI | Insurances | PNX Udenna Insurance Brokers | 6892745.21 | 0 | 3502004.42 | 10394749.63 | 6892745.21 | 3502004.42 | 10394749.63 | 0 | 0 | 10394749.63 | 0 | 10394749.63 |  | CARI |  |  |  | 6892745.21 | 6892745.21 | 10394749.63 | 10394749.63 | TRUE | TRUE | 0 | -1.8626e-09
2000 Structure & General Sitewide Prelims | CP01 | Structure and General Sitewide Prelims | TERP ASIA CONSTRUCTION CORPORATION | 427378789.81 | 0 | 103781456.46 | 531160246.27 | 365000000 | 166160246.27 | 531160246.27 | 0 | 0 | 531160246.27 | 0 | 368461391.14 |  | CP01 |  |  |  | 365000000 | 365000000 | 530601881.32 | 531160246.27 | TRUE | FALSE | 0 | -558364.95
2000 Structure & General Sitewide Prelims | OP01 | Cement (Supply only) | HOLCIM | 92161305 | 0 | -11466516.48 | 80694788.52 | 92161305 | -11466516.48 | 80694788.52 | 0 | 0 | 80694788.52 | 0 | 33041300.84 |  | OP01 |  |  |  | 92161305 | 92161305 | 80523674.02 | 80694788.52 | TRUE | FALSE | 0 | -171114.5
2000 Structure & General Sitewide Prelims | OP02 | Reinforcing Steel (OSM) | STEEL ASIA MANUFACTURING | 259599611.04 | 0 | -91180127.35 | 168419483.69 | 259599611.04 | -91180127.35 | 168419483.69 | 0 | 0 | 168419483.69 | 0 | 105752028.32 |  | OP02 |  |  |  | 259599611.04 | 259599611.04 | 167747871.64 | 168419483.69 | TRUE | FALSE | 2.9802e-08 | -671612.05
3000 Facade | CP30 | Building Maintenance / Access / BMU | VONOTEC, INC. | 13000000 | 0 | -1004000 | 11996000 | 10300000 | 696000 | 10996000 | 1000000 | 0 | 11996000 | 0 | 2372629.97 |  | CP30 |  |  |  | 10300000 | 10300000 | 11300000 | 11996000 | TRUE | FALSE | 0 | -696000
3000 Facade | CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | GLAZETECH GLASS & ALUMINUM INSTALLATION INC | 305793900.71 | 0 | -61100830.49 | 244693070.22 | 227456344.43 | 4689859.79 | 232146204.22 | 12546866 | 0 | 244693070.22 | 0 | 32768956.22 |  | CP11 |  |  |  | 227456344.42 | 227456344.43 | 242860257.91 | 244693070.22 | FALSE | FALSE | -0.01 | -1832812.31
3000 Facade | CP11A | Curtain Wall & Structural Steel (Bldg.E) | DALKIA INCORPORATED | 224321762.87 | 0 | -28169047.17 | 196152715.7 | 184929323.48 | 770258.22 | 185699581.7 | 10453134 | 0 | 196152715.7 | 0 | 80681651.62 |  | CP11A |  |  |  | 184929323.49 | 184929323.48 | 193661800.77 | 196152715.7 | FALSE | FALSE | 0.01 | -2490914.93
3000 Facade | CP21 | Supply & Apply Waterproofing to Toilets, Doghouses & Roof Deck, Mechanical Rooms and Landscape Areas | HIGH PERFORMANCE SOLUTIONS INC. | 22296090.91 | 0 | -4556456.15 | 17739634.76 | 18606970.55 | -1367335.79 | 17239634.76 | 500000 | 0 | 17739634.76 | 0 | 10482491.36 |  | CP21 |  |  |  | 18606970.55 | 18606970.55 | 17564567.25 | 17739634.76 | TRUE | FALSE | 0 | -175067.51
4000 Builders Work | CP01A | Masonry & Rendering, Metal Doors & Hardwares, Office FloorMasonry & Rendering, Metal Doors & Hardwares, Office Floor Toppings Etc. | TERP ASIA CONSTRUCTION CORPORATION | 158796484.86 | 0 | -18670950.04 | 140125534.82 | 132000000 | 4125534.82 | 136125534.82 | 4000000 | 0 | 140125534.82 | 0 | 28657621.68 |  | CP01A |  |  |  | 132000000 | 132000000 | 138248110.46 | 140125534.82 | TRUE | FALSE | 0 | -1877424.36
4000 Builders Work | OP33 | Door Hardwares | TECHNOINOX CORPORATION | 13042110.19 | 0 | 738542.91 | 13780653.1 | 13300000 | 480653.1 | 13780653.1 | 0 | 0 | 13780653.1 | 0 | 0 |  | OP33 |  |  |  | 13300000 | 13300000 | 13717153.1 | 13780653.1 | TRUE | FALSE | 0 | -63500
5000 Fit-Out | CP20 | Interior Fit-Out Works | EE BLACK LTD | 328382908.5 | 0 | -16810571.14 | 311572337.36 | 310000000 | -3427662.64 | 306572337.36 | 5000000 | 0 | 311572337.36 | 0 | 35613423.71 |  | CP20 |  |  |  | 310000000 | 310000000 | 310771153.54 | 311572337.36 | TRUE | FALSE | 0 | -801183.82
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP04 | Electrical Works | BETA ELECTRIC CORPORATION | 332452945.21 | 0 | -46236955.16 | 286215990.05 | 290173000 | -3957009.95 | 286215990.05 | 0 | 0 | 286215990.05 | 0 | 83956731.54 |  | CP04 |  |  |  | 290173000 | 290173000 | 287122811.35 | 286215990.05 | TRUE | FALSE | 0 | 906821.3
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05A | Building Management System (BMS) | BETA ELECTRIC CORPORATION | 45782001.48 | 0 | -27226411.9 | 18555589.58 | 15000000 | 55589.58 | 15055589.58 | 3500000 | 0 | 18555589.58 | 0 | 4061050.55 |  | CP05A |  |  |  | 15000000 | 15000000 | 18555589.59 | 18555589.58 | TRUE | FALSE | 0 | 0.01
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP05B | Fire Detection & Alarm System (FDAS) | BETA ELECTRIC CORPORATION | 28066202.35 | 0 | -8534926.81 | 19531275.54 | 15000000 | 1531275.54 | 16531275.54 | 3000000 | 0 | 19531275.54 | 0 | 5046234.81 |  | CP05B |  |  |  | 15000000 | 15000000 | 19493889.65 | 19531275.54 | TRUE | FALSE | 0 | -37385.89
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP07 | Plumbing & Sanitary Works | BETA ELECTRIC CORPORATION | 56392985.36 | 0 | -14227266.32 | 42165719.04 | 40000000 | 665719.04 | 40665719.04 | 1500000 | 0 | 42165719.04 | 0 | 12752789.53 |  | CP07 |  |  |  | 40000000 | 40000000 | 42228922.84 | 42165719.04 | TRUE | FALSE | 0 | 63203.8
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP08 | Fire Protection Works | BETA ELECTRIC CORPORATION | 59240036.16 | 0 | -8819689.05 | 50420347.11 | 52100000 | -1679652.89 | 50420347.11 | 0 | 0 | 50420347.11 | 0 | 20425971.51 |  | CP08 |  |  |  | 52100000 | 52100000 | 50337015.49 | 50420347.11 | TRUE | FALSE | 0 | -83331.62
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP09 | Mechanical Works | BETA ELECTRIC CORPORATION | 241840141.94 | 0 | -23003892.82 | 218836249.12 | 237116033.85 | -18279784.73 | 218836249.12 | 0 | 0 | 218836249.12 | 0 | 44824317.45 |  | CP09 |  |  |  | 237116033.86 | 237116033.85 | 218836249.12 | 218836249.12 | FALSE | TRUE | 0.01 | 0
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP13 | Vertical Transport System | JARDINE SCHINDLER ELEVATOR CORPORATION | 182783692 | 0 | -32409850 | 150373842 | 157326104 | -8952262 | 148373842 | 2000000 | 0 | 150373842 | 0 | 73781440.6 |  | CP13 |  |  |  | 157326104 | 157326104 | 149041182 | 150373842 | TRUE | FALSE | 0 | -1332660
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | CP15 | Generator Works | POWERGEN INTEGRATED SOLUTIONS COMPANY, LTD | 208786112.45 | 0 | -45463246.17 | 163322866.28 | 170164615.43 | -6841749.15 | 163322866.28 | 0 | 0 | 163322866.28 | 0 | 91102436.2 |  | CP15 |  |  |  | 170164615.42 | 170164615.43 | 163162866.29 | 163322866.28 | FALSE | FALSE | -0.01 | -159999.99
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP12 | Power Transformer (OSM) | GENTEC DISTRIBUTION CORPORATION | 31424458.89 | 0 | -5784378.89 | 25640080 | 24140080 | 0 | 24140080 | 1500000 | 0 | 25640080 | 0 | 19353192.3 |  | OP12 |  |  |  | 24140080 | 24140080 | 25640080 | 25640080 | TRUE | TRUE | 0 | 0
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP13 | Lighting Fixture | STEALTH VENTURES CORPORATION | 38030551.96 | 0 | -391450.09 | 37639101.87 | 35000000 | 1639101.87 | 36639101.87 | 1000000 | 0 | 37639101.87 | 0 | 33216972.36 |  | OP13 |  |  |  | 35000000 | 35000000 | 37663906.68 | 37639101.87 | TRUE | FALSE | 0 | 24804.81
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP15 | Plumbing Fixture | LIXIL PHILIPPINES | 42792486 | 0 | -28501779.48 | 14290706.52 | 11200000 | 90706.52 | 11290706.52 | 3000000 | 0 | 14290706.52 | 0 | 10724890.73 |  | OP15 |  |  |  | 11200000 | 11200000 | 14290706.52 | 14290706.52 | TRUE | TRUE | 0 | 0
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP18 | Fire Extinguishers | *** TBC *** | 7988909.5 | 0 | 64405.8 | 8053315.3 | 7988909.5 | 64405.8 | 8053315.3 | 0 | 0 | 8053315.3 | 0 | 0 |  | OP18 |  |  |  | 7988909.51 | 7988909.5 | 8053315.31 | 8053315.3 | FALSE | FALSE | 0.01 | 0.01
6000 Mechanical, Electrical, Plumbing & Fire (MEPF) | OP27 | Supply and Delivery of Air Conditioning System - VRF | DAIKIN AIRCONDITIONING PHILIPPINES INC. | 93951488 | 0 | -1532194.83 | 92419293.17 | 78000000 | 9419293.17 | 87419293.17 | 5000000 | 0 | 92419293.17 | 0 | 45063807.57 |  | OP27 |  |  |  | 78000000 | 78000000 | 92419293.17 | 92419293.17 | TRUE | TRUE | 0 | 0
7000 Electrical Low Voltage (ELV) | CP05C | Community Distributive Antenna System (CDAS) | *** TBC *** | 14870408.31 | 0 | 0 | 14870408.31 | 14870408.31 | 0 | 14870408.31 | 0 | 0 | 14870408.31 | 0 | 0 |  | CP05C |  |  |  | 14870408.31 | 14870408.31 | 14870408.31 | 14870408.31 | TRUE | TRUE | -1.8626e-09 | -1.8626e-09
7000 Electrical Low Voltage (ELV) | CP05D | Structured Cabling System & Public Address (SCS & PA) | BETA ELECTRIC CORPORATION | 68309768.89 | 0 | -39047256.35 | 29262512.54 | 23000000 | 3262512.54 | 26262512.54 | 3000000 | 0 | 29262512.54 | 0 | 4467215.65 |  | CP05D |  |  |  | 23000000 | 23000000 | 26239282.22 | 29262512.54 | TRUE | FALSE | 0 | -3023230.32
7000 Electrical Low Voltage (ELV) | CP06E | Access Control, Guard Tour and Turnstile | SUBIC BAY CONSULTANCY AND ALLIED SERVICES CORPORATION | 58476218.7 | 0 | -25696592.35 | 32779626.35 | 28000000 | -220373.65 | 27779626.35 | 5000000 | 0 | 32779626.35 | 0 | 2800000 |  | CP06E |  |  |  | 28000000 | 28000000 | 32779626.35 | 32779626.35 | TRUE | TRUE | 0 | -7.4506e-09
7000 Electrical Low Voltage (ELV) | CP06F | Closed Circuit Television System (CCTV) | PRESTIGE ADVANCE SYSTEMS INCORPORATED | 23705175.99 | 0 | -1514179.27 | 22190996.72 | 22000000 | -309003.28 | 21690996.72 | 500000 | 0 | 22190996.72 | 0 | 10598876.11 |  | CP06F |  |  |  | 22000000 | 22000000 | 22190996.72 | 22190996.72 | TRUE | TRUE | 0 | 0
7000 Electrical Low Voltage (ELV) | CP26 | Seismic Monitoring | *** TBC *** | 900000 | 0 | 0 | 900000 | 900000 | 0 | 900000 | 0 | 0 | 900000 | 0 | 0 |  | CP26 |  |  |  | 900000 | 900000 | 900000 | 900000 | TRUE | TRUE | 0 | 0
7000 Electrical Low Voltage (ELV) | CP31 | Experiential Graphic Design (XGD) | *** TBC *** | 6000000 | 0 | 48027.06 | 6048027.06 | 6000000 | 48027.06 | 6048027.06 | 0 | 0 | 6048027.06 | 0 | 0 |  | CP31 |  |  |  | 6000000 | 6000000 | 6004625.1 | 6048027.06 | TRUE | FALSE | 0 | -43401.96
8000 External Works | CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | GREEN ENVIROSCAPE SERVICES INC. | 62288221.2 | 0 | -4345008.39 | 57943212.81 | 59000000 | -2056787.19 | 56943212.81 | 1000000 | 0 | 57943212.81 | 0 | 5900000 |  | CP17 |  |  |  | 59000000 | 59000000 | 57943212.81 | 57943212.81 | TRUE | TRUE | 0 | 0
8000 External Works | OP30 | Exterior Paving Tiles | GREEN ENVIROSCAPE SERVICES INC. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OP30 |  |  |  |  | 0 |  | 0 | TRUE | TRUE | 0 | 0
9000 Contingencies | Con | Buying Gains/ Losses | *** TBC *** | 48780524.54 | 0 | 445135770.76 | 493916295.3 | 0 | 0 | 0 | 493916295.3 |  | 493916295.3 | 0 | 0 |  | Con |  |  |  | 0 | 0 | 506939469.55 | 493916295.3 | TRUE | FALSE | 0 | 13023174.25
[17 empty] | Grand_Total |  |  |  | 2960161571.81 | 2960161571.8 | 3560764159 | 3560764159.03 | FALSE | FALSE

## ContractPrice-CDE
Items | Main Package | Awarded_C | Awarded_D | Awarded_E | Awarded_Total | Budget_C | Budget_D | Budget_E | Budget_Total | Over_budget | NotYetAward | Approved_Payment | Cert_Amount_C | Cert_Amount_D | Cert_Amount_E | Cert_Amount_Total | Cert_Amount_Total | Certified_Progress | Certified_Diff | PercentAwarded | PercentBudget | ContractStatus | Downpayment % | Downpayment_Amt | Billing_Progress | Billing_Progress_perc | Termination_Demobilization | Termination_Supplier | Risk_Claim_Cost | Binary | Termination_Cost | Remarks
C10 | Testing & Commissioning (3rd Party) | 2786810 | 2742190 | 4171000 | 9700000 | 2786810 | 2742190 | 4171000 | 9700000 |  |  | 1825882.35 | 711182.42 | 699795.58 | 1064422 | 2475400 | 2475400 | 2475400 | 0 | 25.52% | 25.52% | No contract received | 10% | 0 |  |  |  | 649517.65 |  | 1 | 649517.65 | No contract received
CP01 | Structure and General Sitewide | 104864500 | 103185500 | 156950000 | 365000000 | 152441920.5 | 150001151.85 | 228158808.97 | 530601881.32 |  |  | 331961391.14 | 105858957.67 | 104164035.28 | 158438398.19 | 368461391.14 | 368461391.14 | 368461391.14 | 0 | 100.9% | 69.44% | Received but no signature proof | 10% | 36500000 | 295461391.14 | 80.95% |  | 36500000 |  | 1 | 36500000
CP01a | Masonry & Rendering, Metal Doors & Hardwares, Office Floor | 37923600 | 37316400 | 56760000 | 132000000 | 39718682.13 | 39082740.83 | 59446687.5 | 138248110.46 |  |  | 14356944.89 | 7917110.27 | 7790348.32 | 11849486.3 | 27556944.89 | 27556944.89 | 28657621.68 | 1100676.79 | 21.71% | 20.73% | Received but no signature proof | 10% | 13200000 | 1156944.89 | 0.8765% |  | 14300676.79 |  | 1 | 14300676.79
CP04 | Electrical Works | 83366702.9 | 82031907.1 | 124774390 | 290173000 | 82490383.7 | 81169618.77 | 123462808.88 | 287122811.35 |  |  | 53272370.2 | 24120768.97 | 23734568.01 | 36101394.56 | 83956731.54 | 83956731.54 | 83956731.54 | 0 | 28.93% | 29.24% | Received but no signature proof | 10% | 29017300 | 24255070.2 | 8.359% |  | 30684361.34 |  | 1 | 30684361.34
CP05A | Building Management System (BMS) | 4309500 | 4240500 | 6450000 | 15000000 | 5331020.89 | 5245665.18 | 7978903.52 | 18555589.59 |  |  | 2460708.24 | 1166739.82 | 1148058.99 | 1746251.74 | 4061050.55 | 4061050.55 | 4061050.55 | 0 | 27.07% | 21.89% | Received but no signature proof | 10% | 1500000 | 960708.24 | 6.405% |  | 1600342.31 |  | 1 | 1600342.31
CP05B | Fire Detection & Alarm System | 4309500 | 4240500 | 6450000 | 15000000 | 5600594.5 | 5510922.6 | 8382372.55 | 19493889.65 |  |  | 2988670.95 | 1449783.26 | 1426570.58 | 2169880.97 | 5046234.81 | 5046234.81 | 5046234.81 | 0 | 33.64% | 25.89% | Received but no signature proof | 10% | 1500000 | 1488670.95 | 9.924% |  | 2057563.86 |  | 1 | 2057563.86
CP05D | Structured Cabling System & Public Address (SCS & PA) | 6607900 | 6502100 | 9890000 | 23000000 | 7538545.78 | 7417845.09 | 11282891.35 | 26239282.22 |  |  | 1608423.5 | 1062938.1 | 1142518.66 | 1544326.83 | 4467215.65 | 3749783.59 | 4467215.65 | 717432.06 | 19.42% | 17.02% | No contract received | 10% | 0 |  |  |  | 2858792.15 |  | 1 | 2858792.15
CP06E | Access Control, Guard Tour and | 8044400 | 7915600 | 12040000 | 28000000 | 9417586.65 | 9266800.37 | 14095239.33 | 32779626.35 |  |  |  | 835083.91 | 835083.91 | 1129832.18 | 2800000 | 2800000 | 2800000 | 0 | 10% | 8.542% | Received but no signature proof | 10% | 2800000 | -2800000 | -10% |  | 2800000 |  | 1 | 2800000 | No approved payment input
CP06F | Closed Circuit Television System (CCTV) | 6320600 | 6219400 | 9460000 | 22000000 | 6375473.36 | 6273394.77 | 9542128.59 | 22190996.72 |  |  | 8398876.11 | 3053000.37 | 3069839.15 | 4476036.59 | 10598876.11 | 10598876.11 | 10598876.11 | 0 | 48.18% | 47.76% | Received but no signature proof | 10% | 2200000 | 6198876.11 | 28.18% |  | 2200000 |  | 1 | 2200000
CP07 | Plumbing & Sanitary Works | 11492000 | 11308000 | 17200000 | 40000000 | 12132369.53 | 11938116.49 | 18158436.82 | 42228922.84 |  |  | 8496687.32 | 3663876.43 | 3605213.6 | 5483699.5 | 12752789.53 | 12752789.53 | 12752789.53 | 0 | 31.88% | 30.2% | Received but no signature proof | 10% | 0 |  |  |  | 4256102.21 |  | 1 | 4256102.21
CP08 | Fire Protection Works | 14968330 | 14728670 | 22403000 | 52100000 | 14461824.55 | 14230274.28 | 21644916.66 | 50337015.49 |  |  | 14363966.02 | 5736611.32 | 5644761.65 | 8585948.03 | 19967321 | 19967321 | 20425971.51 | 458650.51 | 39.21% | 40.58% | Received but no signature proof | 10% | 0 |  |  |  | 6062005.49 |  | 1 | 6062005.49
CP09 | Mechanical Works | 68123436.53 | 67032702.77 | 101959894.56 | 237116033.86 | 62871654.37 | 61865007.63 | 94099587.12 | 218836249.12 |  |  | 20087906.25 | 12688137.88 | 12484986.36 | 18990251.62 | 44163375.86 | 44163375.86 | 44824317.45 | 660941.59 | 18.9% | 20.48% | Received but no signature proof | 10% | 33800000 | -13712093.75 | -5.783% |  | 24736411.2 |  | 1 | 24736411.2 | Contract Package = 338M, Approved payment is less than downpayment
CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | 65348207.75 | 64301908.57 | 97806228.1 | 227456344.42 | 69773752.09 | 68656594.91 | 104429910.91 | 242860257.91 |  |  | 3292727.57 | 9414521.12 | 9263783.92 | 14090651.17 | 32768956.22 | 32768956.21 | 32768956.22 | 0.01 | 14.41% | 13.49% | No contract received | 10% | 0 |  |  |  | 29476228.65 |  | 1 | 29476228.65
CP11a | Curtain Wall & Structural Steel (Bldg.E) | 53130194.64 | 52279519.75 | 79519609.1 | 184929323.49 | 55639035.36 | 54748191.08 | 83274574.33 | 193661800.77 |  |  | 59795754.87 | 22492339.84 | 22132211.88 | 33664135.5 | 78288687.22 | 78288687.22 | 80681651.62 | 2392964.4 | 43.63% | 41.66% | Received but no signature proof | 10% | 18492932.349 | 41302822.521 | 22.33% |  | 20885896.75 |  | 1 | 20885896.75
CP13 | Vertical Transport System | 45199789.68 | 44476089.6 | 67650224.72 | 157326104 | 42819531.59 | 42133942.15 | 64087708.26 | 149041182 |  |  | 26500000 | 21197407.88 | 20858013.26 | 31726019.46 | 73781440.6 | 73781440.6 | 73781440.6 | 0 | 46.9% | 49.5% | Received but no signature proof | 30% of USD (Indent) 10% of PHP (Local) | 35206933.5 | -8706933.5 | -5.534% |  | 47281440.6 |  | 1 | 47281440.6
CP15 | Generator Works | 48888294.01 | 48105536.78 | 73170784.63 | 170164615.42 | 46876691.49 | 46126142.3 | 70160032.5 | 163162866.29 |  |  | 12438540.8 | 26173729.92 | 25754658.71 | 39174047.57 | 91102436.2 | 91102436.2 | 91102436.2 | 0 | 53.54% | 55.84% | Received but no signature proof | 30% of USD (Indent) 10% of PHP (Local) | 40461085.028 | -28022544.228 | -16.47% |  | 78663895.4 |  | 1 | 78663895.4 | Approved payment is less than downpayment
CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | 16950700 | 16679300 | 25370000 | 59000000 | 16647085.04 | 16380546.26 | 24915581.51 | 57943212.81 |  |  |  | 1610963.48 | 1610963.49 | 2678073.03 | 5900000 | 5900000 | 5900000 | 0 | 10% | 10.18% | No contract received | 0% | 0 |  |  |  | 5900000 |  | 1 | 5900000
CP20 | Fit-Out Works | 89063000 | 87637000 | 133300000 | 310000000 | 89284552.41 | 87855005.1 | 133631596.03 | 310771153.54 |  |  | 4613423.71 | 8750149.17 | 8742992.45 | 16198337.85 | 35613423.71 | 33691479.47 | 35613423.71 | 1921944.24 | 11.49% | 11.46% | Received but no signature proof | 10% | 31000000 | -26386576.29 | -8.512% |  | 31000000 |  | 1 | 31000000 | Approved payment is less than downpayment
CP21 | Waterproofing | 5345782.64 | 5260190.57 | 8000997.34 | 18606970.55 | 5046300.17 | 4965503.16 | 7552763.92 | 17564567.25 |  |  | 0 | 2969591.8 | 2922045.26 | 4444568.3 | 10336205.36 | 10336205.36 | 10482491.36 | 146286 | 56.34% | 59.68% | No contract received | 10% | 0 |  |  |  | 10482491.36 |  | 1 | 10482491.36
CP30 | Building Maintenance Unit (BMU) | 2959190 | 2911810 | 4429000 | 10300000 | 3246490 | 3194510 | 4859000 | 11300000 |  |  |  | 681656.59 | 670742.49 | 1020230.89 | 2372629.97 | 2372629.97 | 2372629.97 | 0 | 23.04% | 21% | No contract received | 10% | 0 |  |  |  | 2372629.97 |  | 1 | 2372629.97
CP31 | Experiential Graphic Design (XGD) | 1723800 | 1696200 | 2580000 | 6000000 | 1725128.79 | 1697507.52 | 2581988.79 | 6004625.1 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
C01 | Construction Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 76424022.25 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% | Notarized contract received. Fee may vary as per contract. | 10% | 0 |  |  |  | -76424022.25 |  | 1 | -76424022.25 | Further details said rate will be based on calculation in Appendix 1
C02 | LEED Consultant | 1765238.8 | 1736975.32 | 2642021.17 | 6144235.29 | 1046988.8 | 1030225.32 | 1567021.17 | 3644235.29 |  |  | 2327410.81 | 1046988.8 | 1030225.32 | 1567021.17 | 3644235.29 | 3644235.29 | 3644235.29 | 0 | 59.31% | 100% | Notarized contract received | 10% | 0 |  |  |  | 1316824.48 |  | 1 | 1316824.48 | Different from Notarized Contract = 3,644,235.00
C03 | Architectural Services | 1436500 | 1413500 | 2150000 | 5000000 | 1637610 | 1611390 | 2451000 | 5700000 |  |  | 5740172.12 | 2674812.45 | 2631985.66 | 4003374.01 | 9310172.12 | 9310172.12 | 9310172.12 | 0 | 186.2% | 163.3% | Notarized contract received | 10% | 0 |  |  |  | 3570000 |  | 1 | 3570000
C04 | Structural Design Engineering Services | 68952 | 67848 | 103200 | 240000 | 212602 | 209198 | 318200 | 740000 |  |  | 240000 | 68952 | 67848 | 103200 | 240000 | 240000 | 240000 | 0 | 100% | 32.43% | Notarized contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
C05 | MEPF Design Engineering Services | 707989.28 | 696653.57 | 1059642.86 | 2464285.71 | 2289854.26 | 2253191.09 | 3427209.65 | 7970255 |  |  | 7608928.56 | 2540039.81 | 2499370.88 | 3801660.7 | 8841071.4 | 8841071.39 | 8841071.4 | 0.01 | 358.8% | 110.9% | No contract received | 10% | 0 |  |  |  | 1232142.84 |  | 1 | 1232142.84
C06 | Building Information Modelling (BIM) Services | 1005550 | 989450 | 1505000 | 3500000 | 1005550 | 989450 | 1505000 | 3500000 |  |  | 1959558.82 | 1005550 | 989450 | 1505000 | 3500000 | 3500000 | 3500000 | 0 | 100% | 100% | Notarized contract received | 10% | 0 |  |  |  | 1540441.18 |  | 1 | 1540441.18
C07 | Façade Design Services | 577473 | 568227 | 864300 | 2010000 | 604766.5 | 595083.5 | 905150 | 2105000 |  |  | 755000 | 428077 | 421223 | 640700 | 1490000 | 1490000 | 1490000 | 0 | 74.13% | 70.78% | Notarized contract received | 10% | 0 |  |  |  | 735000 |  | 1 | 735000 | Different from Notarized Contract = 875000
C08 | Landscape Design Services | 86190 | 84810 | 129000 | 300000 | 86190 | 84810 | 129000 | 300000 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% | Notarized contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
C09 | Cost Consultant / Quantity Surveying Services | 6773844.48 | 6665387.52 | 10138368 | 23577600 | 4309500 | 4240500 | 6450000 | 15000000 |  |  | 17255000 | 5608096 | 5518304 | 8393600 | 19520000 | 19520000 | 19520000 | 0 | 82.79% | 130.1% | Notarized contract received | 10% | 0 |  |  |  | 2265000 |  | 1 | 2265000 | Different from Notarized Contract = 15000000.
CARI | Insurances | 1980285.7 | 1948579.07 | 2963880.44 | 6892745.21 | 2986411.57 | 2938595.72 | 4469742.34 | 10394749.63 |  | 3502004.42 | 10394749.63 | 2986411.57 | 2938595.72 | 4469742.34 | 10394749.63 | 10394749.63 | 10394749.63 | 0 | 150.8% | 100% | Please provide information | 10% | 0 |  |  |  | 0 |  | 1 | 0
OP01 | Cement (Supply only) | 26477942.93 | 26054000.92 | 39629361.15 | 92161305 | 23134451.55 | 22764042.64 | 34625179.83 | 80523674.02 |  |  | 33041300.84 | 9492765.73 | 9340775.75 | 14207759.36 | 33041300.84 | 33041300.84 | 33041300.84 | 0 | 35.85% | 41.03% | PO Received | 10% | 0 |  |  |  | 0 |  | 1 | 0 | Approved PO = 37,720,400
OP02 | Reinforcing Steel (OSM) | 74582968.25 | 73388810.04 | 111627832.75 | 259599611.04 | 48193963.52 | 47422323.31 | 72131584.81 | 167747871.64 |  |  | 105752028.3198 | 30382557.74 | 29896098.41 | 45473372.18 | 105752028.32 | 105752028.33 | 105752028.32 | -0.01 | 40.74% | 63.04% | PO Received | 10% | 0 |  |  |  | 0.000202 |  | 1 | 0.000202 | Approved PO = 528,095,111.06
OP33 | Door Hardwares | 3821090 | 3759910 | 5719000 | 13300000 | 3940938.09 | 3877839.18 | 5898375.83 | 13717153.1 |  | 417153.1 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
OP13 | Lighting Fixture | 10055500 | 9894500 | 15050000 | 35000000 | 10820840.39 | 10647586.42 | 16195479.87 | 37663906.68 |  | 2663906.68 | 1792507.1 | 9543236.16 | 9390438.09 | 14283298.11 | 33216972.36 | 33216972.36 | 33216972.36 | 0 | 94.91% | 88.19% | No contract received | 10% | 0 |  |  |  | 31424465.26 |  | 1 | 31424465.26
OP12 | Power Transformer (OSM) | 6935444.98 | 6824400.62 | 10380234.4 | 24140080 | 7366394.98 | 7248450.62 | 11025234.4 | 25640080 |  | 1500000 | 15081218.48 | 5074005.21 | 4992764.62 | 7594229.87 | 17660999.7 | 17660999.7 | 19353192.3 | 1692192.6 | 80.17% | 75.48% | No contract received | 10% | 0 |  |  |  | 4271973.82 |  | 1 | 4271973.82
OP15 | Plumbing Fixture | 3217760 | 3166240 | 4816000 | 11200000 | 4105719.99 | 4039982.73 | 6145003.8 | 14290706.52 |  | 3090706.52 |  | 3081261.11 | 3031926.61 | 4611703.01 | 10724890.73 | 10724890.73 | 10724890.73 | 0 | 95.76% | 75.05% | PO Received | 10% | 0 |  |  |  | 10724890.73 |  | 1 | 10724890.73 | Approved PO = 528,095,111.06
OP18 | Fire Extinguishers | 2295213.7 | 2258464.72 | 3435231.09 | 7988909.51 | 2313717.49 | 2276672.24 | 3462925.58 | 8053315.31 |  | 64405.8 | 28307573.76 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | -28307573.76 |  | 1 | -28307573.76
OP27 | Supply and Delivery of Air Conditioning System - VRF | 22409400 | 22050600 | 33540000 | 78000000 | 26552062.93 | 26126934.18 | 39740296.06 | 92419293.17 |  | 14419293.17 | 24536608.28 | 12946831.91 | 12739538.4 | 19377437.26 | 45063807.57 | 45063807.57 | 45063807.57 | 0 | 57.77% | 48.76% | No contract received | 10% | 0 |  |  |  | 20527199.29 |  | 1 | 20527199.29
CP05C | Community Distributive Antenna System (CDAS) | 4272268.31 | 4203864.43 | 6394275.57 | 14870408.31 | 4272268.31 | 4203864.43 | 6394275.57 | 14870408.31 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
CP26 | Seismic Monitoring | 258570 | 254430 | 387000 | 900000 | 258570 | 254430 | 387000 | 900000 |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
Con | Contingencies | 0 | 0 | 0 | 0 | 145643709.6 | 143311788.04 | 217983971.91 | 506939469.55 |  | 506939469.55 | [7 empty] | 0 | 0% | 0% | Please provide information | 10% | 0 |  |  |  | 0 |  | 1 | 0
| Total | 850454419.58 | 836837676.35 | 1272869475.88 | 2960161571.81 | 1023007542.88 | 1006628027.76 | 1531128588.36 | 3560764159 |  | 532596939.24 | 897678352.8898 | 348434135.71 | 343189736.01 | 524608090.29 |  | 1216231962.01 | 1225323050.21 | 9091088.2 | 41.39% | 34.41% | [5 empty] | 0 | 327644697.3202 | 657676183.77 |  | 985320881.0902
Note on R8: Different from Table Typo Error
Note on R19: Different from Table Typo Error
Note on F24: 3,644,235.00
Note on F29: 875,000
Note on F31: 15,000,000

## Progress-C
Date | Week | Cum_Plan_Percent | Cum_Award_Plan | Actual_award_Percent | Cum_Actual_Value_award | Predict_percent | Predict_value | Payment_percent | Payment_to_date | Percentage
05/15/2018 | 2 | 0.8 | 6803635.3566 | 0.4 | 3401817.6783 | 0.33253 | 3401817.6783 | 1
05/30/2018 | 4 | 2 | 17009088.3916 | 0.8 | 6803635.3566 | 0.66506 | 6803635.3566
06/15/2018 | 6 | 4.8 | 40821812.1398 | 1.2 | 10205453.035 | 0.99759 | 10205453.035
06/30/2018 | 8 | 6.7 | 56980446.1119 | 1.6 | 13607270.7133 | 1.3301 | 13607270.7133
07/15/2018 | 10 | 8.5 | 72288625.6643 | 2.1 | 17859542.8112 | 1.7458 | 17859542.8112
07/30/2018 | 12 | 13.4 | 113960892.2237 | 3.7 | 31466813.5245 | 3.0759 | 31466813.5245
08/15/2018 | 14 | 17.5 | 148829523.4265 | 6.8 | 57830900.5314 | 5.653 | 57830900.5314
08/30/2018 | 16 | 22.9 | 194754062.0838 | 11.1 | 94400440.5734 | 9.2277 | 94400440.5734
09/15/2018 | 18 | 26.5 | 225370421.1887 | 13.8 | 117362709.902 | 11.4723 | 117362709.902
09/30/2018 | 20 | 29.4 | 250033599.3565 | 14.2 | 120764527.5804 | 11.8049 | 120764527.5804
10/15/2018 | 22 | 33.2 | 282350867.3006 | 16.8 | 142876342.4894 | 13.9663 | 142876342.4894
10/30/2018 | 24 | 37 | 314668135.2446 | 17.5 | 148829523.4265 | 14.5482 | 148829523.4265
11/15/2018 | 26 | 41.1 | 349536766.4474 | 18.2 | 154782704.3636 | 15.1302 | 154782704.3636
11/30/2018 | 28 | 46.7 | 397162213.9439 | 18.8 | 159885430.881 | 15.629 | 159885430.881
12/15/2018 | 30 | 54.2 | 460946295.4124 | 19.4 | 164988157.3985 | 16.1278 | 164988157.3985
12/30/2018 | 32 | 61.1 | 519627650.3634 | 19.4 | 164988157.3985 | 16.1278 | 164988157.3985
1/15/2019 | 34 | 67.2 | 571505369.9578 | 19.5 | 165838611.8181 | 16.2109 | 165838611.8181
1/30/2019 | 36 | 73.9 | 628485816.0696 | 19.9 | 169240429.4964 | 16.5434 | 169240429.4964
2/15/2019 | 38 | 80.5 | 684615807.7619 | 20.4 | 173492701.5943 | 16.9591 | 173492701.5943
2/30/2019 | 40 | 86 | 731390800.8388 | 20.6 | 175193610.4335 | 17.1253 | 175193610.4335
3/15/2019 | 42 | 92.1 | 783268520.4332 | 20.8 | 176894519.2726 | 17.2916 | 176894519.2726
3/30/2019 | 44 | 94.8 | 806230789.7618 | 21 | 178595428.1118 | 17.4579 | 178595428.1118
4/15/2019 | 46 | 96.7 | 822389423.7339 | 21.2 | 180296336.951 | 17.6241 | 180296336.951
4/30/2019 | 48 | 98.2 | 835146240.0276 | 21.2 | 180296336.951 | 17.6241 | 180296336.951
05/15/2019 | 50 | 99.4 | 845351693.0625 | 21.2 | 180296336.951 | 17.6241 | 180296336.951
05/30/2019 | 52 | 100 | 850454419.58 | 21.2 | 180296336.951 | 17.6241 | 180296336.951
06/15/2019 | 54 | 100 | 850454419.58 | 21.2 | 180296336.951 | 17.6241 | 180296336.951
06/30/2019 | 56 | 100 | 850454419.58 | 21.2 | 180296336.951 | 17.6241 | 180296336.951
07/15/2019 | 58 | 100 | 850454419.58 | 21.9 | 186249517.888 | 18.2061 | 186249517.888
07/30/2019 | 60 | 100 | 850454419.58 | 22.5 | 191352244.4055 | 18.7049 | 191352244.4055
08/15/2019 | 62 | 100 | 850454419.58 | 23.6 | 200707243.0209 | 19.6193 | 200707243.0209
08/30/2019 | 64 | 100 | 850454419.58 | 23.7 | 201557697.4405 | 19.7025 | 201557697.4405
09/15/2019 | 66 | 100 | 850454419.58 | 23.7 | 201557697.4405 | 19.7025 | 201557697.4405
09/30/2019 | 68 | 100 | 850454419.58 | 23.7 | 201557697.4405 | 19.7025 | 201557697.4405
10/15/2019 | 70 | 100 | 850454419.58 | 24.1 | 204959515.1188 | 20.035 | 204959515.1188
10/30/2019 | 72 | 100 | 850454419.58 | 24.1 | 204959515.1188 | 20.035 | 204959515.1188
11/15/2019 | 74 | 100 | 850454419.58 | 24.1 | 204959515.1188 | 20.035 | 204959515.1188
11/30/2019 | 76 | 100 | 850454419.58 | 24.1 | 204959515.1188 | 20.035 | 204959515.1188
12/15/2019 | 78 | 100 | 850454419.58 | 24.7 | 210062241.6363 | 20.5338 | 210062241.6363
12/30/2019 | 80 | 100 | 850454419.58 | 24.7 | 210062241.6363 | 20.5338 | 210062241.6363
1/15/2020 | 82 | 100 | 850454419.58 | 24.7 | 210062241.6363 | 20.5338 | 210062241.6363 | 1.7659
2020-01-30 | 84 | 100 | 850454419.58 | 26.3733 | 224293178.9239 | 22.2997 | 228127692.775
2020-02-14 | 86 | 100 | 850454419.58 | 28.0467 | 238524116.2115 | 24.0656 | 246193143.9138
2020-02-29 | 88 | 100 | 850454419.58 | 29.72 | 252755053.4992 | 25.8315 | 264258595.0525
2020-03-15 | 90 | 100 | 850454419.58 | 31.3933 | 266985990.7868 | 27.5975 | 282324046.1913
2020-03-30 | 92 | 100 | 850454419.58 | 33.0667 | 281216928.0745 | 29.3634 | 300389497.33
2020-04-15 | 94 | 100 | 850454419.58 | 34.74 | 295447865.3621 | 31.1293 | 318454948.4688
2020-04-30 | 96 | 100 | 850454419.58 | 36.4133 | 309678802.6497 | 32.8952 | 336520399.6075
2020-05-15 | 98 | 100 | 850454419.58 | 38.0867 | 323909739.9374 | 34.6611 | 354585850.7463
2020-05-30 | 100 | 100 | 850454419.58 | 39.76 | 338140677.225 | 36.427 | 372651301.885
2020-06-15 | 102 | 100 | 850454419.58 | 41.4333 | 352371614.5126 | 38.1929 | 390716753.0238
2020-06-30 | 104 | 100 | 850454419.58 | 43.1067 | 366602551.8003 | 39.9589 | 408782204.1625
2020-07-15 | 106 | 100 | 850454419.58 | 44.78 | 380833489.0879 | 41.7248 | 426847655.3013
2020-07-30 | 108 | 100 | 850454419.58 | 46.4533 | 395064426.3756 | 43.4907 | 444913106.44
2020-08-15 | 110 | 100 | 850454419.58 | 48.1267 | 409295363.6632 | 45.2566 | 462978557.5788
2020-08-30 | 112 | 100 | 850454419.58 | 49.8 | 423526300.9508 | 47.0225 | 481044008.7175
2020-09-15 | 114 | 100 | 850454419.58 | 51.4733 | 437757238.2385 | 48.7884 | 499109459.8563
2020-09-30 | 116 | 100 | 850454419.58 | 53.1467 | 451988175.5261 | 50.5544 | 517174910.995
2020-10-15 | 118 | 100 | 850454419.58 | 54.82 | 466219112.8138 | 52.3203 | 535240362.1338
2020-10-30 | 120 | 100 | 850454419.58 | 56.4933 | 480450050.1014 | 54.0862 | 553305813.2725
2020-11-15 | 122 | 100 | 850454419.58 | 58.1667 | 494680987.389 | 55.8521 | 571371264.4113
2020-11-30 | 124 | 100 | 850454419.58 | 59.84 | 508911924.6767 | 57.618 | 589436715.55
2020-12-15 | 126 | 100 | 850454419.58 | 61.5133 | 523142861.9643 | 59.3839 | 607502166.6888
2020-12-30 | 128 | 100 | 850454419.58 | 63.1867 | 537373799.2519 | 61.1499 | 625567617.8275
2021-01-15 | 130 | 100 | 850454419.58 | 64.86 | 551604736.5396 | 62.9158 | 643633068.9663
2021-01-30 | 132 | 100 | 850454419.58 | 66.5333 | 565835673.8272 | 64.6817 | 661698520.105
2021-02-15 | 134 | 100 | 850454419.58 | 68.2067 | 580066611.1149 | 66.4476 | 679763971.2438
2021-02-28 | 136 | 100 | 850454419.58 | 69.88 | 594297548.4025 | 68.2135 | 697829422.3825
2021-03-15 | 138 | 100 | 850454419.58 | 71.5533 | 608528485.6901 | 69.9794 | 715894873.5213
2021-03-30 | 140 | 100 | 850454419.58 | 73.2267 | 622759422.9778 | 71.7453 | 733960324.66
2021-04-15 | 142 | 100 | 850454419.58 | 74.9 | 636990360.2654 | 73.5113 | 752025775.7988
2021-04-30 | 144 | 100 | 850454419.58 | 76.5733 | 651221297.5531 | 75.2772 | 770091226.9375
2021-05-15 | 146 | 100 | 850454419.58 | 78.2467 | 665452234.8407 | 77.0431 | 788156678.0763
2021-05-30 | 148 | 100 | 850454419.58 | 79.92 | 679683172.1283 | 78.809 | 806222129.215
2021-06-15 | 150 | 100 | 850454419.58 | 81.5933 | 693914109.416 | 80.5749 | 824287580.3538
2021-06-30 | 152 | 100 | 850454419.58 | 83.2667 | 708145046.7036 | 82.3408 | 842353031.4925
2021-07-15 | 154 | 100 | 850454419.58 | 84.94 | 722375983.9913 | 84.1068 | 860418482.6313
2021-07-30 | 156 | 100 | 850454419.58 | 86.6133 | 736606921.2789 | 85.8727 | 878483933.77
2021-08-15 | 158 | 100 | 850454419.58 | 88.2867 | 750837858.5665 | 87.6386 | 896549384.9088
2021-08-30 | 160 | 100 | 850454419.58 | 89.96 | 765068795.8542 | 89.4045 | 914614836.0475
2021-09-15 | 162 | 100 | 850454419.58 | 91.6333 | 779299733.1418 | 91.1704 | 932680287.1863
2021-09-30 | 164 | 100 | 850454419.58 | 93.3067 | 793530670.4294 | 92.9363 | 950745738.325
2021-10-15 | 166 | 100 | 850454419.58 | 94.98 | 807761607.7171 | 94.7023 | 968811189.4638
2021-10-30 | 168 | 100 | 850454419.58 | 96.6533 | 821992545.0047 | 96.4682 | 986876640.6025
2021-11-15 | 170 | 100 | 850454419.58 | 98.3267 | 836223482.2924 | 98.2341 | 1004942091.7413
2021-11-30 | 172 | 100 | 850454419.58 | 100 | 850454419.58 | 100 | 1023007542.88

## Progress-D
Date | Week | Cum_Plan_Percent | Cum_Award_Plan | Actual_award_Percent | Cum_Actual_Value_award | Predict_percent | Predict_value | Payment_percent | Payment_to_date | Percentage
05/15/2018 | 2 | 0.8 | 6694701.4108 | 0.3 | 2510513.0291 | 0.24541 | 2470316.8581 | 1
05/30/2018 | 4 | 2 | 16736753.527 | 0.6 | 5021026.0581 | 0.49081 | 4940633.7161
06/15/2018 | 6 | 4.8 | 40168208.4648 | 1 | 8368376.7635 | 0.81802 | 8234389.5269
06/30/2018 | 8 | 6.7 | 56068124.3155 | 1.4 | 11715727.4689 | 1.1452 | 11528145.3376
07/15/2018 | 10 | 8.5 | 71131202.4898 | 2 | 16736753.527 | 1.636 | 16468779.0537
07/30/2018 | 12 | 12.4 | 103767871.8674 | 3.2 | 26778805.6432 | 2.6177 | 26350046.486
08/15/2018 | 14 | 16.5 | 138078216.5978 | 6.7 | 56068124.3155 | 5.4807 | 55170409.83
08/30/2018 | 16 | 22.3 | 186614801.8261 | 10.6 | 88704793.6931 | 8.671 | 87284528.9848
09/15/2018 | 18 | 26.5 | 221761984.2328 | 13.2 | 110462573.2782 | 10.7978 | 108693941.7546
09/30/2018 | 20 | 29.4 | 246030276.8469 | 14 | 117157274.689 | 11.4522 | 115281453.3761
10/15/2018 | 22 | 33.2 | 277830108.5482 | 15.2 | 127199326.8052 | 12.4339 | 125162720.8083
10/30/2018 | 24 | 37 | 309629940.2495 | 16.6 | 138915054.2741 | 13.5791 | 136690866.146
11/15/2018 | 26 | 41.1 | 343940284.9799 | 17.4 | 145609755.6849 | 14.2335 | 143278377.7674
11/30/2018 | 28 | 46.7 | 390803194.8555 | 17.8 | 148957106.3903 | 14.5607 | 146572133.5782
12/15/2018 | 30 | 54.2 | 453566020.5817 | 18.3 | 153141294.7721 | 14.9697 | 150689328.3416
12/30/2018 | 32 | 61.1 | 511307820.2499 | 18.3 | 153141294.7721 | 14.9697 | 150689328.3416
1/15/2019 | 34 | 67.2 | 562354918.5072 | 18.4 | 153978132.4484 | 15.0515 | 151512767.2943
1/30/2019 | 36 | 73.9 | 618423042.8227 | 18.8 | 157325483.1538 | 15.3787 | 154806523.1051
2/15/2019 | 38 | 80.5 | 673654329.4618 | 20 | 167367535.27 | 16.3603 | 164687790.5373
2/30/2019 | 40 | 86 | 719680401.661 | 20.1 | 168204372.9464 | 16.4421 | 165511229.49
3/15/2019 | 42 | 92.1 | 770727499.9184 | 20.4 | 170714885.9754 | 16.6875 | 167981546.348
3/30/2019 | 44 | 94.8 | 793322117.1798 | 20.9 | 174899074.3571 | 17.0966 | 172098741.1115
4/15/2019 | 46 | 96.7 | 809222033.0305 | 21.1 | 176572749.7099 | 17.2602 | 173745619.0168
4/30/2019 | 48 | 98.2 | 821774598.1757 | 21.1 | 176572749.7099 | 17.2602 | 173745619.0168
05/15/2019 | 50 | 99.4 | 831816650.2919 | 21.2 | 177409587.3862 | 17.342 | 174569057.9695
05/30/2019 | 52 | 100 | 836837676.35 | 21.2 | 177409587.3862 | 17.342 | 174569057.9695
06/15/2019 | 54 | 100 | 836837676.35 | 21.2 | 177409587.3862 | 17.342 | 174569057.9695
06/30/2019 | 56 | 100 | 836837676.35 | 21.2 | 177409587.3862 | 17.342 | 174569057.9695
07/15/2019 | 58 | 100 | 836837676.35 | 21.4 | 179083262.7389 | 17.5056 | 176215935.8749
07/30/2019 | 60 | 100 | 836837676.35 | 22 | 184104288.797 | 17.9964 | 181156569.591
08/15/2019 | 62 | 100 | 836837676.35 | 22.9 | 191635827.8841 | 18.7326 | 188567520.1652
08/30/2019 | 64 | 100 | 836837676.35 | 23.1 | 193309503.2369 | 18.8962 | 190214398.0706
09/15/2019 | 66 | 100 | 836837676.35 | 23.7 | 198330529.295 | 19.387 | 195155031.7867
09/30/2019 | 68 | 100 | 836837676.35 | 23.7 | 198330529.295 | 19.387 | 195155031.7867
10/15/2019 | 70 | 100 | 836837676.35 | 23.7 | 198330529.295 | 19.387 | 195155031.7867
10/30/2019 | 72 | 100 | 836837676.35 | 23.7 | 198330529.295 | 19.387 | 195155031.7867
11/15/2019 | 74 | 100 | 836837676.35 | 23.9 | 200004204.6477 | 19.5506 | 196801909.6921
11/30/2019 | 76 | 100 | 836837676.35 | 23.9 | 200004204.6477 | 19.5506 | 196801909.6921
12/15/2019 | 78 | 100 | 836837676.35 | 23.9 | 200004204.6477 | 19.5506 | 196801909.6921
12/30/2019 | 80 | 100 | 836837676.35 | 23.9 | 200004204.6477 | 19.5506 | 196801909.6921
1/15/2020 | 82 | 100 | 836837676.35 | 23.9 | 200004204.6477 | 19.5506 | 196801909.6921 | 1.7878
2020-01-30 | 84 | 100 | 836837676.35 | 25.5911 | 214156059.5744 | 21.3384 | 214798045.6491
2020-02-14 | 86 | 100 | 836837676.35 | 27.2822 | 228307914.5011 | 23.1261 | 232794181.6062
2020-02-29 | 88 | 100 | 836837676.35 | 28.9733 | 242459769.4278 | 24.9139 | 250790317.5633
2020-03-15 | 90 | 100 | 836837676.35 | 30.6644 | 256611624.3545 | 26.7017 | 268786453.5203
2020-03-30 | 92 | 100 | 836837676.35 | 32.3556 | 270763479.2812 | 28.4894 | 286782589.4774
2020-04-15 | 94 | 100 | 836837676.35 | 34.0467 | 284915334.208 | 30.2772 | 304778725.4345
2020-04-30 | 96 | 100 | 836837676.35 | 35.7378 | 299067189.1347 | 32.065 | 322774861.3915
2020-05-15 | 98 | 100 | 836837676.35 | 37.4289 | 313219044.0614 | 33.8527 | 340770997.3486
2020-05-30 | 100 | 100 | 836837676.35 | 39.12 | 327370898.9881 | 35.6405 | 358767133.3057
2020-06-15 | 102 | 100 | 836837676.35 | 40.8111 | 341522753.9148 | 37.4283 | 376763269.2627
2020-06-30 | 104 | 100 | 836837676.35 | 42.5022 | 355674608.8416 | 39.216 | 394759405.2198
2020-07-15 | 106 | 100 | 836837676.35 | 44.1933 | 369826463.7683 | 41.0038 | 412755541.1768
2020-07-30 | 108 | 100 | 836837676.35 | 45.8844 | 383978318.695 | 42.7915 | 430751677.1339
2020-08-15 | 110 | 100 | 836837676.35 | 47.5756 | 398130173.6217 | 44.5793 | 448747813.091
2020-08-30 | 112 | 100 | 836837676.35 | 49.2667 | 412282028.5484 | 46.3671 | 466743949.048
2020-09-15 | 114 | 100 | 836837676.35 | 50.9578 | 426433883.4752 | 48.1548 | 484740085.0051
2020-09-30 | 116 | 100 | 836837676.35 | 52.6489 | 440585738.4019 | 49.9426 | 502736220.9622
2020-10-15 | 118 | 100 | 836837676.35 | 54.34 | 454737593.3286 | 51.7304 | 520732356.9192
2020-10-30 | 120 | 100 | 836837676.35 | 56.0311 | 468889448.2553 | 53.5181 | 538728492.8763
2020-11-15 | 122 | 100 | 836837676.35 | 57.7222 | 483041303.182 | 55.3059 | 556724628.8334
2020-11-30 | 124 | 100 | 836837676.35 | 59.4133 | 497193158.1087 | 57.0937 | 574720764.7904
2020-12-15 | 126 | 100 | 836837676.35 | 61.1044 | 511345013.0355 | 58.8814 | 592716900.7475
2020-12-30 | 128 | 100 | 836837676.35 | 62.7956 | 525496867.9622 | 60.6692 | 610713036.7046
2021-01-15 | 130 | 100 | 836837676.35 | 64.4867 | 539648722.8889 | 62.457 | 628709172.6616
2021-01-30 | 132 | 100 | 836837676.35 | 66.1778 | 553800577.8156 | 64.2447 | 646705308.6187
2021-02-15 | 134 | 100 | 836837676.35 | 67.8689 | 567952432.7423 | 66.0325 | 664701444.5758
2021-02-28 | 136 | 100 | 836837676.35 | 69.56 | 582104287.6691 | 67.8202 | 682697580.5328
2021-03-15 | 138 | 100 | 836837676.35 | 71.2511 | 596256142.5958 | 69.608 | 700693716.4899
2021-03-30 | 140 | 100 | 836837676.35 | 72.9422 | 610407997.5225 | 71.3958 | 718689852.447
2021-04-15 | 142 | 100 | 836837676.35 | 74.6333 | 624559852.4492 | 73.1835 | 736685988.404
2021-04-30 | 144 | 100 | 836837676.35 | 76.3244 | 638711707.3759 | 74.9713 | 754682124.3611
2021-05-15 | 146 | 100 | 836837676.35 | 78.0156 | 652863562.3027 | 76.7591 | 772678260.3182
2021-05-30 | 148 | 100 | 836837676.35 | 79.7067 | 667015417.2294 | 78.5468 | 790674396.2752
2021-06-15 | 150 | 100 | 836837676.35 | 81.3978 | 681167272.1561 | 80.3346 | 808670532.2323
2021-06-30 | 152 | 100 | 836837676.35 | 83.0889 | 695319127.0828 | 82.1224 | 826666668.1893
2021-07-15 | 154 | 100 | 836837676.35 | 84.78 | 709470982.0095 | 83.9101 | 844662804.1464
2021-07-30 | 156 | 100 | 836837676.35 | 86.4711 | 723622836.9362 | 85.6979 | 862658940.1035
2021-08-15 | 158 | 100 | 836837676.35 | 88.1622 | 737774691.863 | 87.4857 | 880655076.0605
2021-08-30 | 160 | 100 | 836837676.35 | 89.8533 | 751926546.7897 | 89.2734 | 898651212.0176
2021-09-15 | 162 | 100 | 836837676.35 | 91.5444 | 766078401.7164 | 91.0612 | 916647347.9747
2021-09-30 | 164 | 100 | 836837676.35 | 93.2356 | 780230256.6431 | 92.8489 | 934643483.9317
2021-10-15 | 166 | 100 | 836837676.35 | 94.9267 | 794382111.5698 | 94.6367 | 952639619.8888
2021-10-30 | 168 | 100 | 836837676.35 | 96.6178 | 808533966.4966 | 96.4245 | 970635755.8459
2021-11-15 | 170 | 100 | 836837676.35 | 98.3089 | 822685821.4233 | 98.2122 | 988631891.8029
2021-11-30 | 172 | 100 | 836837676.35 | 100 | 836837676.35 | 100 | 1006628027.76

## Progress-E
Date | Week | Cum_Plan_Percent | Cum_Award_Plan | Actual_award_Percent | Cum_Actual_Value_award | Predict_percent | Predict_value | Payment_percent | Payment_to_date | Percentage
05/15/2018 | 2 | 0.7 | 8910086.3312 | 0.4 | 5091477.9035 | 0.33253 | 5091477.9035 | 1
05/30/2018 | 4 | 1.6 | 20365911.6141 | 0.8 | 10182955.807 | 0.66506 | 10182955.807
06/15/2018 | 6 | 2.8 | 35640345.3246 | 1.2 | 15274433.7106 | 0.99759 | 15274433.7106
06/30/2018 | 8 | 4.6 | 58551995.8905 | 1.6 | 20365911.6141 | 1.3301 | 20365911.6141
07/15/2018 | 10 | 8.5 | 108193905.4498 | 2.1 | 26730258.9935 | 1.7458 | 26730258.9935
07/30/2018 | 12 | 12.5 | 159108684.485 | 3.7 | 47096170.6076 | 3.0759 | 47096170.6076
08/15/2018 | 14 | 16.1 | 204931985.6167 | 4.9 | 62370604.3181 | 4.0735 | 62370604.3181
08/30/2018 | 16 | 20.3 | 258392503.6036 | 7.3 | 92919471.7392 | 6.0687 | 92919471.7392
09/15/2018 | 18 | 25.5 | 324581716.3494 | 8.4 | 106921035.9739 | 6.9832 | 106921035.9739
09/30/2018 | 20 | 28.4 | 361494931.1499 | 9.9 | 126014078.1121 | 8.2301 | 126014078.1121
10/15/2018 | 22 | 33.2 | 422592665.9922 | 10.7 | 136197033.9192 | 8.8952 | 136197033.9192
10/30/2018 | 24 | 37 | 470961706.0756 | 12.6 | 160381553.9609 | 10.4747 | 160381553.9609
11/15/2018 | 26 | 41.1 | 523149354.5867 | 14.2 | 180747465.575 | 11.8049 | 180747465.575
11/30/2018 | 28 | 46.7 | 594430045.236 | 15.2 | 193476160.3338 | 12.6362 | 193476160.3338
12/15/2018 | 30 | 54.2 | 689895255.927 | 15.9 | 202386246.6649 | 13.2181 | 202386246.6649
12/30/2018 | 32 | 61.1 | 777723249.7627 | 15.9 | 202386246.6649 | 13.2181 | 202386246.6649
1/15/2019 | 34 | 67.2 | 855368287.7914 | 16.4 | 208750594.0443 | 13.6338 | 208750594.0443
1/30/2019 | 36 | 73.9 | 940650542.6753 | 16.9 | 215114941.4237 | 14.0494 | 215114941.4237
2/15/2019 | 38 | 80.5 | 1024659928.0834 | 19.4 | 246936678.3207 | 16.1278 | 246936678.3207
2/30/2019 | 40 | 86 | 1094667749.2568 | 20.6 | 262211112.0313 | 17.1253 | 262211112.0313
3/15/2019 | 42 | 92.1 | 1172312787.2855 | 21.6 | 274939806.7901 | 17.9567 | 274939806.7901
3/30/2019 | 44 | 94.8 | 1206680263.1342 | 22.3 | 283849893.1212 | 18.5386 | 283849893.1212
4/15/2019 | 46 | 96.7 | 1230864783.176 | 24.6 | 313125891.0665 | 20.4507 | 313125891.0665
4/30/2019 | 48 | 98.2 | 1249957825.3142 | 25.7 | 327127455.3012 | 21.3651 | 327127455.3012
05/15/2019 | 50 | 98.9 | 1258867911.6453 | 26.9 | 342401889.0117 | 22.3627 | 342401889.0117
05/30/2019 | 52 | 100 | 1272869475.88 | 27.3 | 347493366.9152 | 22.6952 | 347493366.9152
06/15/2019 | 54 | 100 | 1272869475.88 | 28.2 | 358949192.1982 | 23.4434 | 358949192.1982
06/30/2019 | 56 | 100 | 1272869475.88 | 29 | 369132148.0052 | 24.1085 | 369132148.0052
07/15/2019 | 58 | 100 | 1272869475.88 | 29.7 | 378042234.3364 | 24.6904 | 378042234.3364
07/30/2019 | 60 | 100 | 1272869475.88 | 32.2 | 409863971.2334 | 26.7687 | 409863971.2334
08/15/2019 | 62 | 100 | 1272869475.88 | 33.1 | 421319796.5163 | 27.5169 | 421319796.5163
08/30/2019 | 64 | 100 | 1272869475.88 | 33.3 | 423865535.468 | 27.6832 | 423865535.468
09/15/2019 | 66 | 100 | 1272869475.88 | 33.6 | 427684143.8957 | 27.9326 | 427684143.8957
09/30/2019 | 68 | 100 | 1272869475.88 | 34.2 | 435321360.751 | 28.4314 | 435321360.751
10/15/2019 | 70 | 100 | 1272869475.88 | 35.4 | 450595794.4615 | 29.429 | 450595794.4615
10/30/2019 | 72 | 100 | 1272869475.88 | 37.4 | 476053183.9791 | 31.0917 | 476053183.9791
11/15/2019 | 74 | 100 | 1272869475.88 | 39.4 | 501510573.4967 | 32.7543 | 501510573.4967
11/30/2019 | 76 | 100 | 1272869475.88 | 40.8 | 519330746.159 | 33.9182 | 519330746.159
12/15/2019 | 78 | 100 | 1272869475.88 | 41.4 | 526967963.0143 | 34.417 | 526967963.0143
12/30/2019 | 80 | 100 | 1272869475.88 | 41.6 | 529513701.9661 | 34.5832 | 529513701.9661
1/15/2020 | 82 | 100 | 1272869475.88 | 41.6 | 529513701.9661 | 34.5832 | 529513701.9661 | 1.4537
2020-01-30 | 84 | 100 | 1272869475.88 | 42.8978 | 546032719.1642 | 36.0369 | 551771810.5526 | 1.2978
2020-02-14 | 86 | 100 | 1272869475.88 | 44.1956 | 562551736.3623 | 37.4906 | 574029919.1391
2020-02-29 | 88 | 100 | 1272869475.88 | 45.4933 | 579070753.5603 | 38.9443 | 596288027.7257
2020-03-15 | 90 | 100 | 1272869475.88 | 46.7911 | 595589770.7584 | 40.3981 | 618546136.3122
2020-03-30 | 92 | 100 | 1272869475.88 | 48.0889 | 612108787.9565 | 41.8518 | 640804244.8987
2020-04-15 | 94 | 100 | 1272869475.88 | 49.3867 | 628627805.1546 | 43.3055 | 663062353.4853
2020-04-30 | 96 | 100 | 1272869475.88 | 50.6844 | 645146822.3527 | 44.7592 | 685320462.0718
2020-05-15 | 98 | 100 | 1272869475.88 | 51.9822 | 661665839.5508 | 46.2129 | 707578570.6583
2020-05-30 | 100 | 100 | 1272869475.88 | 53.28 | 678184856.7489 | 47.6666 | 729836679.2449
2020-06-15 | 102 | 100 | 1272869475.88 | 54.5778 | 694703873.947 | 49.1203 | 752094787.8314
2020-06-30 | 104 | 100 | 1272869475.88 | 55.8756 | 711222891.145 | 50.574 | 774352896.4179
2020-07-15 | 106 | 100 | 1272869475.88 | 57.1733 | 727741908.3431 | 52.0277 | 796611005.0045
2020-07-30 | 108 | 100 | 1272869475.88 | 58.4711 | 744260925.5412 | 53.4814 | 818869113.591
2020-08-15 | 110 | 100 | 1272869475.88 | 59.7689 | 760779942.7393 | 54.9351 | 841127222.1775
2020-08-30 | 112 | 100 | 1272869475.88 | 61.0667 | 777298959.9374 | 56.3888 | 863385330.7641
2020-09-15 | 114 | 100 | 1272869475.88 | 62.3644 | 793817977.1355 | 57.8425 | 885643439.3506
2020-09-30 | 116 | 100 | 1272869475.88 | 63.6622 | 810336994.3336 | 59.2962 | 907901547.9371
2020-10-15 | 118 | 100 | 1272869475.88 | 64.96 | 826856011.5316 | 60.7499 | 930159656.5236
2020-10-30 | 120 | 100 | 1272869475.88 | 66.2578 | 843375028.7297 | 62.2036 | 952417765.1102
2020-11-15 | 122 | 100 | 1272869475.88 | 67.5556 | 859894045.9278 | 63.6573 | 974675873.6967
2020-11-30 | 124 | 100 | 1272869475.88 | 68.8533 | 876413063.1259 | 65.1111 | 996933982.2832
2020-12-15 | 126 | 100 | 1272869475.88 | 70.1511 | 892932080.324 | 66.5648 | 1019192090.8698
2020-12-30 | 128 | 100 | 1272869475.88 | 71.4489 | 909451097.5221 | 68.0185 | 1041450199.4563
2021-01-15 | 130 | 100 | 1272869475.88 | 72.7467 | 925970114.7202 | 69.4722 | 1063708308.0428
2021-01-30 | 132 | 100 | 1272869475.88 | 74.0444 | 942489131.9183 | 70.9259 | 1085966416.6294
2021-02-15 | 134 | 100 | 1272869475.88 | 75.3422 | 959008149.1163 | 72.3796 | 1108224525.2159
2021-02-28 | 136 | 100 | 1272869475.88 | 76.64 | 975527166.3144 | 73.8333 | 1130482633.8024
2021-03-15 | 138 | 100 | 1272869475.88 | 77.9378 | 992046183.5125 | 75.287 | 1152740742.389
2021-03-30 | 140 | 100 | 1272869475.88 | 79.2356 | 1008565200.7106 | 76.7407 | 1174998850.9755
2021-04-15 | 142 | 100 | 1272869475.88 | 80.5333 | 1025084217.9087 | 78.1944 | 1197256959.562
2021-04-30 | 144 | 100 | 1272869475.88 | 81.8311 | 1041603235.1068 | 79.6481 | 1219515068.1486
2021-05-15 | 146 | 100 | 1272869475.88 | 83.1289 | 1058122252.3049 | 81.1018 | 1241773176.7351
2021-05-30 | 148 | 100 | 1272869475.88 | 84.4267 | 1074641269.503 | 82.5555 | 1264031285.3216
2021-06-15 | 150 | 100 | 1272869475.88 | 85.7244 | 1091160286.701 | 84.0092 | 1286289393.9082
2021-06-30 | 152 | 100 | 1272869475.88 | 87.0222 | 1107679303.8991 | 85.4629 | 1308547502.4947
2021-07-15 | 154 | 100 | 1272869475.88 | 88.32 | 1124198321.0972 | 86.9166 | 1330805611.0812
2021-07-30 | 156 | 100 | 1272869475.88 | 89.6178 | 1140717338.2953 | 88.3704 | 1353063719.6677
2021-08-15 | 158 | 100 | 1272869475.88 | 90.9156 | 1157236355.4934 | 89.8241 | 1375321828.2543
2021-08-30 | 160 | 100 | 1272869475.88 | 92.2133 | 1173755372.6915 | 91.2778 | 1397579936.8408
2021-09-15 | 162 | 100 | 1272869475.88 | 93.5111 | 1190274389.8896 | 92.7315 | 1419838045.4273
2021-09-30 | 164 | 100 | 1272869475.88 | 94.8089 | 1206793407.0877 | 94.1852 | 1442096154.0139
2021-10-15 | 166 | 100 | 1272869475.88 | 96.1067 | 1223312424.2857 | 95.6389 | 1464354262.6004
2021-10-30 | 168 | 100 | 1272869475.88 | 97.4044 | 1239831441.4838 | 97.0926 | 1486612371.1869
2021-11-15 | 170 | 100 | 1272869475.88 | 98.7022 | 1256350458.6819 | 98.5463 | 1508870479.7735
2021-11-30 | 172 | 100 | 1272869475.88 | 100 | 1272869475.88 | 100 | 1531128588.36

## Progress-CDE
Date | Week | Cum_Plan_Percent | Cum_Award_Plan | Actual_award_Percent | Cum_Actual_Value_award | Predict_percent | Predict_value | Payment_percent | Payment_to_date | Percentage
05/15/2018 | 2 | 0.8 | 23681292.5745 | 0.4 | 11840646.2872 | 0.33253 | 11840646.2872 | 1
05/30/2018 | 4 | 1.9 | 56243069.8644 | 0.8 | 23681292.5745 | 0.66506 | 23681292.5745
06/15/2018 | 6 | 3.8 | 112486139.7288 | 1.2 | 35521938.8617 | 0.99759 | 35521938.8617
06/30/2018 | 8 | 5.7 | 168729209.5932 | 1.6 | 47362585.149 | 1.3301 | 47362585.149
07/15/2018 | 10 | 9.5 | 281215349.322 | 2.1 | 62163393.008 | 1.7458 | 62163393.008
07/30/2018 | 12 | 13.4 | 396661650.6225 | 3.7 | 109525978.157 | 3.0759 | 109525978.157
08/15/2018 | 14 | 17.5 | 518028275.0668 | 6.6 | 195370663.7395 | 5.4868 | 195370663.7395
08/30/2018 | 16 | 21.4 | 633474576.3673 | 9.7 | 287135672.4656 | 8.0639 | 287135672.4656
09/15/2018 | 18 | 24.3 | 719319261.9498 | 11.4 | 337458419.1863 | 9.4771 | 337458419.1863
09/30/2018 | 20 | 28.4 | 840685886.394 | 12.4 | 367060034.9044 | 10.3085 | 367060034.9044
10/15/2018 | 22 | 32 | 947251702.9792 | 14.1 | 417382781.6252 | 11.7217 | 417382781.6252
10/30/2018 | 24 | 35 | 1036056550.1335 | 15.5 | 458825043.6306 | 12.8856 | 458825043.6306
11/15/2018 | 26 | 40.1 | 1187024790.2958 | 16.5 | 488426659.3487 | 13.7169 | 488426659.3487
11/30/2018 | 28 | 45.5 | 1346873515.1736 | 17.1 | 506187628.7795 | 14.2157 | 506187628.7795
12/15/2018 | 30 | 52 | 1539284017.3412 | 17.8 | 526908759.7822 | 14.7976 | 526908759.7822
12/30/2018 | 32 | 58.7 | 1737614842.6525 | 17.8 | 526908759.7822 | 14.7976 | 526908759.7822
1/15/2019 | 34 | 65.6 | 1941865991.1074 | 18 | 532829082.9258 | 14.9639 | 532829082.9258
1/30/2019 | 36 | 72.1 | 2134276493.275 | 18.4 | 544669729.213 | 15.2964 | 544669729.213
2/15/2019 | 38 | 78.8 | 2332607318.5863 | 19.9 | 589072152.7902 | 16.5434 | 589072152.7902
2/30/2019 | 40 | 84.5 | 2501336528.1795 | 20.4 | 603872960.6492 | 16.9591 | 603872960.6492
3/15/2019 | 42 | 91.1 | 2696707191.9189 | 21.1 | 624594091.6519 | 17.541 | 624594091.6519
3/30/2019 | 44 | 94.4 | 2794392523.7886 | 21.4 | 633474576.3673 | 17.7904 | 633474576.3673
4/15/2019 | 46 | 96.6 | 2859516078.3685 | 22.4 | 663076192.0854 | 18.6217 | 663076192.0854
4/30/2019 | 48 | 98.1 | 2903918501.9456 | 22.7 | 671956676.8009 | 18.8711 | 671956676.8009
05/15/2019 | 50 | 99.3 | 2939440440.8073 | 23 | 680837161.5163 | 19.1205 | 680837161.5163
05/30/2019 | 52 | 100 | 2960161571.81 | 23.2 | 686757484.6599 | 19.2868 | 686757484.6599
06/15/2019 | 54 | 100 | 2960161571.81 | 23.5 | 695637969.3754 | 19.5362 | 695637969.3754
06/30/2019 | 56 | 100 | 2960161571.81 | 23.7 | 701558292.519 | 19.7025 | 701558292.519
07/15/2019 | 58 | 100 | 2960161571.81 | 24.2 | 716359100.378 | 20.1181 | 716359100.378
07/30/2019 | 60 | 100 | 2960161571.81 | 25.5 | 754841200.8116 | 21.1989 | 754841200.8116
08/15/2019 | 62 | 100 | 2960161571.81 | 26.5 | 784442816.5297 | 22.0302 | 784442816.5297
08/30/2019 | 64 | 100 | 2960161571.81 | 26.6 | 787402978.1015 | 22.1133 | 787402978.1015
09/15/2019 | 66 | 100 | 2960161571.81 | 26.9 | 796283462.8169 | 22.3627 | 796283462.8169
09/30/2019 | 68 | 100 | 2960161571.81 | 27.1 | 802203785.9605 | 22.529 | 802203785.9605
10/15/2019 | 70 | 100 | 2960161571.81 | 27.6 | 817004593.8196 | 22.9446 | 817004593.8196
10/30/2019 | 72 | 100 | 2960161571.81 | 28.8 | 852526532.6813 | 23.9422 | 852526532.6813
11/15/2019 | 74 | 100 | 2960161571.81 | 29.5 | 873247663.684 | 24.5242 | 873247663.684
11/30/2019 | 76 | 100 | 2960161571.81 | 30 | 888048471.543 | 24.9398 | 888048471.543
12/15/2019 | 78 | 100 | 2960161571.81 | 30.2 | 893968794.6866 | 25.1061 | 893968794.6866
12/30/2019 | 80 | 100 | 2960161571.81 | 30.2 | 893968794.6866 | 25.1061 | 893968794.6866
1/15/2020 | 82 | 100 | 2960161571.81 | 30.2 | 893968794.6866 | 25.1061 | 893968794.6866 | 1.6643
2020-01-30 | 84 | 100 | 2960161571.81 | 31.7511 | 939884189.7338 | 26.7704 | 953230913.8936 | 1.5511
2020-02-14 | 86 | 100 | 2960161571.81 | 33.3022 | 985799584.781 | 28.4347 | 1012493033.1005
2020-02-29 | 88 | 100 | 2960161571.81 | 34.8533 | 1031714979.8282 | 30.099 | 1071755152.3075
2020-03-15 | 90 | 100 | 2960161571.81 | 36.4044 | 1077630374.8754 | 31.7633 | 1131017271.5145
2020-03-30 | 92 | 100 | 2960161571.81 | 37.9556 | 1123545769.9226 | 33.4276 | 1190279390.7214
2020-04-15 | 94 | 100 | 2960161571.81 | 39.5067 | 1169461164.9697 | 35.0919 | 1249541509.9284
2020-04-30 | 96 | 100 | 2960161571.81 | 41.0578 | 1215376560.0169 | 36.7563 | 1308803629.1354
2020-05-15 | 98 | 100 | 2960161571.81 | 42.6089 | 1261291955.0641 | 38.4206 | 1368065748.3423
2020-05-30 | 100 | 100 | 2960161571.81 | 44.16 | 1307207350.1113 | 40.0849 | 1427327867.5493
2020-06-15 | 102 | 100 | 2960161571.81 | 45.7111 | 1353122745.1585 | 41.7492 | 1486589986.7563
2020-06-30 | 104 | 100 | 2960161571.81 | 47.2622 | 1399038140.2057 | 43.4135 | 1545852105.9632
2020-07-15 | 106 | 100 | 2960161571.81 | 48.8133 | 1444953535.2529 | 45.0778 | 1605114225.1702
2020-07-30 | 108 | 100 | 2960161571.81 | 50.3644 | 1490868930.3 | 46.7421 | 1664376344.3772
2020-08-15 | 110 | 100 | 2960161571.81 | 51.9156 | 1536784325.3472 | 48.4064 | 1723638463.5841
2020-08-30 | 112 | 100 | 2960161571.81 | 53.4667 | 1582699720.3944 | 50.0707 | 1782900582.7911
2020-09-15 | 114 | 100 | 2960161571.81 | 55.0178 | 1628615115.4416 | 51.735 | 1842162701.998
2020-09-30 | 116 | 100 | 2960161571.81 | 56.5689 | 1674530510.4888 | 53.3993 | 1901424821.205
2020-10-15 | 118 | 100 | 2960161571.81 | 58.12 | 1720445905.536 | 55.0637 | 1960686940.412
2020-10-30 | 120 | 100 | 2960161571.81 | 59.6711 | 1766361300.5832 | 56.728 | 2019949059.6189
2020-11-15 | 122 | 100 | 2960161571.81 | 61.2222 | 1812276695.6303 | 58.3923 | 2079211178.8259
2020-11-30 | 124 | 100 | 2960161571.81 | 62.7733 | 1858192090.6775 | 60.0566 | 2138473298.0329
2020-12-15 | 126 | 100 | 2960161571.81 | 64.3244 | 1904107485.7247 | 61.7209 | 2197735417.2398
2020-12-30 | 128 | 100 | 2960161571.81 | 65.8756 | 1950022880.7719 | 63.3852 | 2256997536.4468
2021-01-15 | 130 | 100 | 2960161571.81 | 67.4267 | 1995938275.8191 | 65.0495 | 2316259655.6538
2021-01-30 | 132 | 100 | 2960161571.81 | 68.9778 | 2041853670.8663 | 66.7138 | 2375521774.8607
2021-02-15 | 134 | 100 | 2960161571.81 | 70.5289 | 2087769065.9135 | 68.3781 | 2434783894.0677
2021-02-28 | 136 | 100 | 2960161571.81 | 72.08 | 2133684460.9607 | 70.0424 | 2494046013.2747
2021-03-15 | 138 | 100 | 2960161571.81 | 73.6311 | 2179599856.0078 | 71.7067 | 2553308132.4816
2021-03-30 | 140 | 100 | 2960161571.81 | 75.1822 | 2225515251.055 | 73.3711 | 2612570251.6886
2021-04-15 | 142 | 100 | 2960161571.81 | 76.7333 | 2271430646.1022 | 75.0354 | 2671832370.8955
2021-04-30 | 144 | 100 | 2960161571.81 | 78.2844 | 2317346041.1494 | 76.6997 | 2731094490.1025
2021-05-15 | 146 | 100 | 2960161571.81 | 79.8356 | 2363261436.1966 | 78.364 | 2790356609.3095
2021-05-30 | 148 | 100 | 2960161571.81 | 81.3867 | 2409176831.2438 | 80.0283 | 2849618728.5164
2021-06-15 | 150 | 100 | 2960161571.81 | 82.9378 | 2455092226.291 | 81.6926 | 2908880847.7234
2021-06-30 | 152 | 100 | 2960161571.81 | 84.4889 | 2501007621.3381 | 83.3569 | 2968142966.9304
2021-07-15 | 154 | 100 | 2960161571.81 | 86.04 | 2546923016.3853 | 85.0212 | 3027405086.1373
2021-07-30 | 156 | 100 | 2960161571.81 | 87.5911 | 2592838411.4325 | 86.6855 | 3086667205.3443
2021-08-15 | 158 | 100 | 2960161571.81 | 89.1422 | 2638753806.4797 | 88.3498 | 3145929324.5513
2021-08-30 | 160 | 100 | 2960161571.81 | 90.6933 | 2684669201.5269 | 90.0141 | 3205191443.7582
2021-09-15 | 162 | 100 | 2960161571.81 | 92.2444 | 2730584596.5741 | 91.6785 | 3264453562.9652
2021-09-30 | 164 | 100 | 2960161571.81 | 93.7956 | 2776499991.6213 | 93.3428 | 3323715682.1721
2021-10-15 | 166 | 100 | 2960161571.81 | 95.3467 | 2822415386.6684 | 95.0071 | 3382977801.3791
2021-10-30 | 168 | 100 | 2960161571.81 | 96.8978 | 2868330781.7156 | 96.6714 | 3442239920.5861
2021-11-15 | 170 | 100 | 2960161571.81 | 98.4489 | 2914246176.7628 | 98.3357 | 3501502039.793
2021-11-30 | 172 | 100 | 2960161571.81 | 100 | 2960161571.81 | 100 | 3560764159

## Risk0
ID | Risk_Level | Item | CP | Status | Cons | Factor | Risk | Prob | Value | Description | Remarks
1 | Project Wide | Increased Cost for Consultants contracts and payments excluding TPM cost for Building E | VARIOUS | PENDING | 10600000 | 0.9 | 9540000 | 1 | 10600000 | This will be likely due to extra meetings & site visits 20% of consultant budget.
2 | Project Wide | Possible increased in Shipping costs associated with using nominated freight forwarders | VARIOUS | PENDING |  |  |  | 1 | 0 | This is possible and quantum difficult to estimate right now. | Potentiall increase at least 10% on the price of long-lead items
3 | Project Wide | Government mandated wage increase. (Region 3) * Projected calculation for the period: NOVEMBER 2018 - NOVEMBER 2019 based on NCR Wage Increase | VARIOUS | PENDING | 28379476.37 | 1 | 28379476.37 | 1 | 28379476.37 | Note: -Updated to include labor components of Bldg D that was missed out previously - Replied to all Contractors for Labor Escalation Claim requesting for the supporting documents for assessment. - 11/15:(total awarded amount*30%)/512)*25 - Recent wage increase which was implemented in Region 3 was not applied by the Contractor only taking into account the NCR wage increase alone.
4 | Project Wide | Sutherland Changes - Consultant's Cost (BMS, FDAS, MVAC) | VARIOUS | PENDING | 2500000 | 1 | 2500000 | 1 | 2500000 | - Increased for Sep 2019 cost report as per high level estimate from QSI (Php 2.5M) - Allowance for additional cost to design changes
5 | Builder's Work | Plastering Works in Toilet claimed by TACC | CP01A | PENDING | 10500000 | 1 | 10500000 | 1 | 10500000 | - Agreed Php 10.5M, please refer to Glenson Lim email dated 12 Feb 2020 to Malcolm Ward and David Meade, CR to be raised upon receipt of details of agreed amount. Cost to be advised after meeting between GGDC and TACC -Refer to CGC-L-WAP2-TER-0030 dated 12 Nov 2019 for the letter response of GGDC on the claim of TACC
6 | MEPF | Genset - Double Handling of Genset etc due to site not ready | CP15 | PENDING | 900000 | 0.75 | 675000 | 1 | 900000 | 10/2019; risk likelihood was increased to 75% from 50% 07/2019: Reduced allowance due to Genset pull out 06/2019: CP15 to claim for Permit to Install 03/2019: Adjusted due to GGDC provision of lay-down area 01/2019: Overall Allowance covers transportation and lifting facilities. 12/2018: Possibly come early as contractor now producing even w/out payment; Allowance for Mobile Crane 100T - 700k @ 2 days; 60T - 450k for 4 days
7 | MEPF | OP12 - Double Handling of Transformer, etc due to site not ready | OP12 | PENDING | 1800000 | 0.75 | 1350000 | 1 | 1800000 | 10/2019; risk likelihood was increased to 75% from 50% '03/2019: Adjusted due to GGDC provision of slay-down area Possibly come early as contractor now producing; Allowance for Mobile Crane 60T - 450k for 4 days
8 | MEPF | CP13 - Double Handling of Lifts due to early delivery | CP13 | PENDING | 1900000 | 0.75 | 1425000 | 1 | 1900000 | 10/2019; risk likelihood was increased to 75% from 50% '03/2019: Adjusted due to GGDC provision of slay-down area 02/2019: Adjusted to reflect the revised cost but used factor 75% from previously submitted rate. 01/2019: Factored 60% from Contractor's submitted quotation (Approx Cost - 5.021M 12/2018: Minimal risk; possible to use the Owner's laydown area; Contractor to advise if laydown area can be used
9 | MEPF | Plumbing - Phase 1 Irrigation Lines not backfilled | CP07 | PENDING | 200000 | 1 | 200000 | 1 | 200000 | Allowance
10 | MEPF | Offsite Storage for MVSG & LVSG | CP04 | PENDING | 24000 | 1 | 24000 | 1 | 24000 | -BEC is still claiming for 1 month storage cost as per letter ref BEC_LET_WAP2_CP04_0061. - Allowance for Storage Facility considered for 6 months '- Cancelled, BEC instructed to deliver MVSG and LVSG at temporay carpark warehouse of GGDC, letter ref. CGC-L-WAP2-046
11 | MEPF | Interest Charge for Late Payment | CP04 | PENDING | 1879380 | 0.5 | 939690 | 1 | 1879380 | - Allowance considered for 3 months, please refer to Glenson Lim's email dated 19 Aug 2019. - Please refer to JSEC letter ref JSEC_LET_WAP2_0020 dated 02 July 2019.
12 | MEPF | CP15 - processing of Genset Permit to Install | CP15 | PENDING | 160000 | 0.75 | 120000 | 1 | 160000 | -WAP2_CR_0148 raised for costing by QSI Allowance considered , please refer to GGDC letter ref CGC-L WAP2-PIS-0004 dated 20 Aug 2019 - Please refer to quotation from Powergen dated 07 Nov 2019 (Php 160k) Missed in the original building permit
13 | MEPF | Cancelation fee and a possible cost increase USD 145,329.07 should the additional 6 Generators order not be fulfilled by December. | CP15 | PENDING | 7702440.71 | 0.34 | 2618829.8414 | 1 | 7702440.71 | Powergen informed GGDC thru their letter dated 27 December 2019 stating that Cummins UK has cancelled their order for Bldg C & D due to non payment in full and will bill them separately the cancellation charges amounting to 2.6M Php Powergen informed GGDC thru their letter dated 25 Oct 2019 attached to this letter of a possible cost claim regarding cancellation fee from Cummins. This was reiterated by TPM on 18 Nov 2019 email. On 17 Dec 2019, Ysmael of Powergen called TPM advising that they had been penalised by Cummins Philippines. G ELECTRICAL LOW VOLTAGE
14 | External_Works | Overlap in scope between the Phase 1 Landscape and Phase 2 Landscape | CP17 | PENDING | 500000 | 1 | 500000 | 1 | 500000 | Allowance
15 | Commercial | EOT Claim projected for all contractors for 17 mos for Buildings C & D as of May 2020 (excludes 3-months COVID-19 lock down except for plant by Terp like TC, alimaks, etc) | VARIOUS | PENDING | 238515875.06 | 0.74 | 176501747.5444 | 0 | 0 | Calculation based on the reduced Bldg C & D Prolongation Cost due to inactivity Updated calculation based on the latest EoT claim by Terp (CP01 and CP01A).
16 | Commercial | EOT Claim projected for all contractors for 17 mos for Buildings E as of May 2020 (excludes 3-months COVID-19 lock down, except for plant by Terp like TC, alimaks, etc) | VARIOUS | PENDING | 201536897.19 | 0.76 | 153168041.8644 | 0 | 0 | Calculation based on the reduced days of delays with reference to original completion date of CP01 ie 17 months from Oct 2018. Updated calculation based on the latest EoT claim by Terp (CP01 and CP01A)
17 | Commercial | Acceleration Cost for CSA and MEPF Contractors at Bldg E only | VARIOUS | PENDING | 16471577.2 | 0 |  | 1 | 16471577.2 | PMI for Acceleration of the Works at Building E was issued to all Contractors as of 06 Mar 2020. No cost allowance as this was not implemented due to sudden work stoppage notice from GGDC dated 18 Mar 2020. PMI needs to be superseded / cancelled.
18 | Commercial | CP & OP Orders not placed to be transferred to the Contingency (Anticipated to be spent) | VARIOUS | PENDING | -63500000 | 0 |  | 1 | -63500000 | Remaining Allowance for ONP; CR to return budget to Contingency was already carried out;ONP for CP17 included
19 | Commercial | Allowance for Future Changes - Client/ Tenant led changes | VARIOUS | PENDING | 54000000 | 0.5 | 27000000 | 1 | 54000000 | 03/2019: 50% reduction
20 | Commercial | Due to delayed payment to Contractors/ Suppliers and with equipment arriving on site or at Contractor's premises, there is potential risk for litigation | VARIOUS | PENDING |  |  |  | 1 | 0 | - Additional budget to be applied
21 | Commercial | Contractor's Restart Cost for Building C & D | VARIOUS | PENDING | 50000000 | 0.5 | 25000000 | 1 | 50000000 | - Allowance for remobilization cost
22 | Commercial | Additional TACC Labor Impact Cost due to deceleration | VARIOUS | PENDING | 20000000 | 0.5 | 10000000 | 1 | 20000000 | - Allowance for remobilization cost
23 | Commercial | Possible termination of Façade Contract for Building C & D | CP11 | PENDING | 100000000 | 1 | 100000000 | 1 | 100000000 | - Additional allowance due to inflation and retender
24 | Commercial | 2nd Extension of CARI (1st extension expires on 04 Apr 2020) | GGDC | PENDING | 4000000 | 0.75 | 3000000 | 1 | 4000000 | Contractor All Risks Insurance
25 | Commercial | Additional 3rd Party T & C Cost due different completion dates of each Buildings | VARIOUS | PENDING |  | 0.75 |  | 1 | 0 | Possible additional cost claim by Commtech due to stagerred building handover, thus there are possible mobilisation, demobilisation and remobilisation for Commtech resources.
26 | Commercial | COVID-19 regulatory cost impact | VARIOUS | PENDING | 10000000 | 0.75 | 7500000 | 1 | 10000000 | Possible cost claim by Contractors due to additional regulatory requirement to comply with the new health and safety standard, so far CP-21 (water proofing package) has intimated a probable cost claim.
27 | Commercial | Works Funded from Other Budget - Sutherland | VARIOUS | PENDING | -40393462.76 | 0.29 | -11714104.2004 | 1 | -40393462.76 | Some of the approved change request were taken by Sutherland and arrangement had been made for SGS to directly pay the contractors by issuing a Purchase Order. Cost allocation based on confirmed packages by SGS (NTP issued to Beta) Initially put under risk but shall be reflected in the project cost report as soon as finalised with SGS.
|  | Total |  |  | 657676183.77 |  | 549227681.4198 |  | 217623411.52

## Risk
ID | Risk_Level | Item | CP | Status | Cons | Factor | Risk | Prob | Value | Description | Remarks
1 | Project Wide | Increased Cost for Consultants contracts and payments excluding TPM cost for Building E | VARIOUS | PENDING | 10.6 | 0.9 | 9.54 | 1 | 10.6 | This will be likely due to extra meetings & site visits 20% of consultant budget.
2 | Project Wide | Possible increased in Shipping costs associated with using nominated freight forwarders | VARIOUS | PENDING | 0 |  |  | 1 | 0 | This is possible and quantum difficult to estimate right now. | Potentiall increase at least 10% on the price of long-lead items
3 | Project Wide | Government mandated wage increase. (Region 3) * Projected calculation for the period: NOVEMBER 2018 - NOVEMBER 2019 based on NCR Wage Increase | VARIOUS | PENDING | 28.3795 | 1 | 28.3795 | 1 | 28.3795 | Note: -Updated to include labor components of Bldg D that was missed out previously - Replied to all Contractors for Labor Escalation Claim requesting for the supporting documents for assessment. - 11/15:(total awarded amount*30%)/512)*25 - Recent wage increase which was implemented in Region 3 was not applied by the Contractor only taking into account the NCR wage increase alone.
4 | Project Wide | Sutherland Changes - Consultant's Cost (BMS, FDAS, MVAC) | VARIOUS | PENDING | 2.5 | 1 | 2.5 | 1 | 2.5 | - Increased for Sep 2019 cost report as per high level estimate from QSI (Php 2.5M) - Allowance for additional cost to design changes
5 | Builder's Work | Plastering Works in Toilet claimed by TACC | CP01A | PENDING | 10.5 | 1 | 10.5 | 1 | 10.5 | - Agreed Php 10.5M, please refer to Glenson Lim email dated 12 Feb 2020 to Malcolm Ward and David Meade, CR to be raised upon receipt of details of agreed amount. Cost to be advised after meeting between GGDC and TACC -Refer to CGC-L-WAP2-TER-0030 dated 12 Nov 2019 for the letter response of GGDC on the claim of TACC
6 | MEPF | Genset - Double Handling of Genset etc due to site not ready | CP15 | PENDING | 0.9 | 0.75 | 0.675 | 1 | 0.9 | 10/2019; risk likelihood was increased to 75% from 50% 07/2019: Reduced allowance due to Genset pull out 06/2019: CP15 to claim for Permit to Install 03/2019: Adjusted due to GGDC provision of lay-down area 01/2019: Overall Allowance covers transportation and lifting facilities. 12/2018: Possibly come early as contractor now producing even w/out payment; Allowance for Mobile Crane 100T - 700k @ 2 days; 60T - 450k for 4 days
7 | MEPF | OP12 - Double Handling of Transformer, etc due to site not ready | OP12 | PENDING | 1.8 | 0.75 | 1.35 | 1 | 1.8 | 10/2019; risk likelihood was increased to 75% from 50% '03/2019: Adjusted due to GGDC provision of slay-down area Possibly come early as contractor now producing; Allowance for Mobile Crane 60T - 450k for 4 days
8 | MEPF | CP13 - Double Handling of Lifts due to early delivery | CP13 | PENDING | 1.9 | 0.75 | 1.425 | 1 | 1.9 | 10/2019; risk likelihood was increased to 75% from 50% '03/2019: Adjusted due to GGDC provision of slay-down area 02/2019: Adjusted to reflect the revised cost but used factor 75% from previously submitted rate. 01/2019: Factored 60% from Contractor's submitted quotation (Approx Cost - 5.021M 12/2018: Minimal risk; possible to use the Owner's laydown area; Contractor to advise if laydown area can be used
9 | MEPF | Plumbing - Phase 1 Irrigation Lines not backfilled | CP07 | PENDING | 0.2 | 1 | 0.2 | 1 | 0.2 | Allowance
10 | MEPF | Offsite Storage for MVSG & LVSG | CP04 | PENDING | 0.024 | 1 | 0.024 | 1 | 0.024 | -BEC is still claiming for 1 month storage cost as per letter ref BEC_LET_WAP2_CP04_0061. - Allowance for Storage Facility considered for 6 months '- Cancelled, BEC instructed to deliver MVSG and LVSG at temporay carpark warehouse of GGDC, letter ref. CGC-L-WAP2-046
11 | MEPF | Interest Charge for Late Payment | CP04 | PENDING | 1.8794 | 0.5 | 0.93969 | 1 | 1.8794 | - Allowance considered for 3 months, please refer to Glenson Lim's email dated 19 Aug 2019. - Please refer to JSEC letter ref JSEC_LET_WAP2_0020 dated 02 July 2019.
12 | MEPF | CP15 - processing of Genset Permit to Install | CP15 | PENDING | 0.16 | 0.75 | 0.12 | 1 | 0.16 | -WAP2_CR_0148 raised for costing by QSI Allowance considered , please refer to GGDC letter ref CGC-L WAP2-PIS-0004 dated 20 Aug 2019 - Please refer to quotation from Powergen dated 07 Nov 2019 (Php 160k) Missed in the original building permit
13 | MEPF | Cancelation fee and a possible cost increase USD 145,329.07 should the additional 6 Generators order not be fulfilled by December. | CP15 | PENDING | 7.7024 | 0.34 | 2.6188 | 1 | 7.7024 | Powergen informed GGDC thru their letter dated 27 December 2019 stating that Cummins UK has cancelled their order for Bldg C & D due to non payment in full and will bill them separately the cancellation charges amounting to 2.6M Php Powergen informed GGDC thru their letter dated 25 Oct 2019 attached to this letter of a possible cost claim regarding cancellation fee from Cummins. This was reiterated by TPM on 18 Nov 2019 email. On 17 Dec 2019, Ysmael of Powergen called TPM advising that they had been penalised by Cummins Philippines. G ELECTRICAL LOW VOLTAGE
14 | External_Works | Overlap in scope between the Phase 1 Landscape and Phase 2 Landscape | CP17 | PENDING | 0.5 | 1 | 0.5 | 1 | 0.5 | Allowance
15 | Commercial | EOT Claim projected for all contractors for 17 mos for Buildings C & D as of May 2020 (excludes 3-months COVID-19 lock down except for plant by Terp like TC, alimaks, etc) | VARIOUS | PENDING | 238.5159 | 0.74 | 176.5017 | 0 | 0 | Calculation based on the reduced Bldg C & D Prolongation Cost due to inactivity Updated calculation based on the latest EoT claim by Terp (CP01 and CP01A).
16 | Commercial | EOT Claim projected for all contractors for 17 mos for Buildings E as of May 2020 (excludes 3-months COVID-19 lock down, except for plant by Terp like TC, alimaks, etc) | VARIOUS | PENDING | 201.5369 | 0.76 | 153.168 | 0 | 0 | Calculation based on the reduced days of delays with reference to original completion date of CP01 ie 17 months from Oct 2018. Updated calculation based on the latest EoT claim by Terp (CP01 and CP01A)
17 | Commercial | Acceleration Cost for CSA and MEPF Contractors at Bldg E only | VARIOUS | PENDING | 16.4716 | 0 |  | 1 | 16.4716 | PMI for Acceleration of the Works at Building E was issued to all Contractors as of 06 Mar 2020. No cost allowance as this was not implemented due to sudden work stoppage notice from GGDC dated 18 Mar 2020. PMI needs to be superseded / cancelled.
18 | Commercial | CP & OP Orders not placed to be transferred to the Contingency (Anticipated to be spent) | VARIOUS | PENDING | -63.5 | 0 |  | 1 | -63.5 | Remaining Allowance for ONP; CR to return budget to Contingency was already carried out;ONP for CP17 included
19 | Commercial | Allowance for Future Changes - Client/ Tenant led changes | VARIOUS | PENDING | 54 | 0.5 | 27 | 1 | 54 | 03/2019: 50% reduction
20 | Commercial | Due to delayed payment to Contractors/ Suppliers and with equipment arriving on site or at Contractor's premises, there is potential risk for litigation | VARIOUS | PENDING | 0 |  |  | 1 | 0 | - Additional budget to be applied
21 | Commercial | Contractor's Restart Cost for Building C & D | VARIOUS | PENDING | 50 | 0.5 | 25 | 1 | 50 | - Allowance for remobilization cost
22 | Commercial | Additional TACC Labor Impact Cost due to deceleration | VARIOUS | PENDING | 20 | 0.5 | 10 | 1 | 20 | - Allowance for remobilization cost
23 | Commercial | Possible termination of Façade Contract for Building C & D | CP11 | PENDING | 100 | 1 | 100 | 1 | 100 | - Additional allowance due to inflation and retender
24 | Commercial | 2nd Extension of CARI (1st extension expires on 04 Apr 2020) | GGDC | PENDING | 4 | 0.75 | 3 | 1 | 4 | Contractor All Risks Insurance
25 | Commercial | Additional 3rd Party T & C Cost due different completion dates of each Buildings | VARIOUS | PENDING | 0 | 0.75 |  | 1 | 0 | Possible additional cost claim by Commtech due to stagerred building handover, thus there are possible mobilisation, demobilisation and remobilisation for Commtech resources.
26 | Commercial | COVID-19 regulatory cost impact | VARIOUS | PENDING | 10 | 0.75 | 7.5 | 1 | 10 | Possible cost claim by Contractors due to additional regulatory requirement to comply with the new health and safety standard, so far CP-21 (water proofing package) has intimated a probable cost claim.
27 | Commercial | Works Funded from Other Budget - Sutherland | VARIOUS | PENDING | -40.3935 | 0.29 | -11.7141 | 1 | -40.3935 | Some of the approved change request were taken by Sutherland and arrangement had been made for SGS to directly pay the contractors by issuing a Purchase Order. Cost allocation based on confirmed packages by SGS (NTP issued to Beta) Initially put under risk but shall be reflected in the project cost report as soon as finalised with SGS.
|  | Total |  |  | 657.6762 |  | 549.2277 |  | 217.6234

## Tonghop1
Items | Main Package | Awarded_C | Awarded_D | Awarded_E | Awarded_Total | Budget_C | Budget_D | Budget_E | Budget_Total | NotYetAward | Approved_Payment | Cert_Amount_C | Cert_Amount_D | Cert_Amount_E | Cert_Amount_Total | Certified_Jan2020 | Certified_Progress | Certified_Diff | PercentAwarded | PercentBudget | ContractStatus | Downpayment % | Downpayment_Amt | Billing_Progress | Billing_Progress_perc | Termination_Demobilization | Termination_Supplier | Risk_Claim_Cost | Binary | Termination_Cost | Remarks
C10 | Testing & Commissioning (3rd Party) | 2.7868 | 2.7422 | 4.171 | 9.7 | 2.7868 | 2.7422 | 4.171 | 9.7 | 0 | 1.8259 | 0.71118 | 0.6998 | 1.0644 | 2.4754 | 2.4754 | 2.4754 | 0 | 25.52% | 25.52% |  | 10% | 0 |  |  |  | 0.64952 |  | 1 | 0.64952 | No contract received
CP01 | Structure and General Sitewide | 104.8645 | 103.1855 | 156.95 | 365 | 152.4419 | 150.0012 | 228.1588 | 530.6019 | 0 | 331.9614 | 105.859 | 104.164 | 158.4384 | 368.4614 | 368.4614 | 368.4614 | 0 | 100.9% | 69.44% | Received but no signature proof | 10% | 36500000 | -36499668.0386 | -9999909% |  | 36.5 |  | 1 | 36.5
CP01a | Masonry & Rendering, Metal Doors & Hardwares, Office Floor | 37.9236 | 37.3164 | 56.76 | 132 | 39.7187 | 39.0827 | 59.4467 | 138.2481 | 0 | 14.3569 | 7.9171 | 7.7903 | 11.8495 | 27.5569 | 27.5569 | 28.6576 | 1.1007 | 21.71% | 20.73% | Received but no signature proof | 10% | 13200000 | -13199985.6431 | -9999989% |  | 14.3007 |  | 1 | 14.3007
CP04 | Electrical Works | 83.3667 | 82.0319 | 124.7744 | 290.173 | 82.4904 | 81.1696 | 123.4628 | 287.1228 | 0 | 53.2724 | 24.1208 | 23.7346 | 36.1014 | 83.9567 | 83.9567 | 83.9567 | 0 | 28.93% | 29.24% | Received but no signature proof | 10% | 29017300 | -29017246.7276 | -9999982% |  | 30.6844 |  | 1 | 30.6844
CP05A | Building Management System (BMS) | 4.3095 | 4.2405 | 6.45 | 15 | 5.331 | 5.2457 | 7.9789 | 18.5556 | 0 | 2.4607 | 1.1667 | 1.1481 | 1.7463 | 4.0611 | 4.0611 | 4.0611 | 0 | 27.07% | 21.89% | Received but no signature proof | 10% | 1500000 | -1499997.5393 | -9999984% |  | 1.6003 |  | 1 | 1.6003
CP05B | Fire Detection & Alarm System | 4.3095 | 4.2405 | 6.45 | 15 | 5.6006 | 5.5109 | 8.3824 | 19.4939 | 0 | 2.9887 | 1.4498 | 1.4266 | 2.1699 | 5.0462 | 5.0462 | 5.0462 | 0 | 33.64% | 25.89% | Received but no signature proof | 10% | 1500000 | -1499997.0113 | -9999980% |  | 2.0576 |  | 1 | 2.0576
CP05D | Structured Cabling System & Public Address (SCS & PA) | 6.6079 | 6.5021 | 9.89 | 23 | 7.5385 | 7.4178 | 11.2829 | 26.2393 | 0 | 1.6084 | 1.0629 | 1.1425 | 1.5443 | 4.4672 | 3.7498 | 4.4672 | 0.71743 | 19.42% | 17.02% | No contract received | 10% | 0 |  |  |  | 2.8588 |  | 1 | 2.8588
CP06E | Access Control, Guard Tour and | 8.0444 | 7.9156 | 12.04 | 28 | 9.4176 | 9.2668 | 14.0952 | 32.7796 | 0 | 0 | 0.83508 | 0.83508 | 1.1298 | 2.8 | 2.8 | 2.8 | 0 | 10% | 8.542% | Received but no signature proof | 10% | 2800000 | -2800000 | -10000000% |  | 2.8 |  | 1 | 2.8 | No approved payment input
CP06F | Closed Circuit Television System (CCTV) | 6.3206 | 6.2194 | 9.46 | 22 | 6.3755 | 6.2734 | 9.5421 | 22.191 | 0 | 8.3989 | 3.053 | 3.0698 | 4.476 | 10.5989 | 10.5989 | 10.5989 | 0 | 48.18% | 47.76% | Received but no signature proof | 10% | 2200000 | -2199991.6011 | -9999962% |  | 2.2 |  | 1 | 2.2
CP07 | Plumbing & Sanitary Works | 11.492 | 11.308 | 17.2 | 40 | 12.1324 | 11.9381 | 18.1584 | 42.2289 | 0 | 8.4967 | 3.6639 | 3.6052 | 5.4837 | 12.7528 | 12.7528 | 12.7528 | 0 | 31.88% | 30.2% | Received but no signature proof | 10% | 0 |  |  |  | 4.2561 |  | 1 | 4.2561
CP08 | Fire Protection Works | 14.9683 | 14.7287 | 22.403 | 52.1 | 14.4618 | 14.2303 | 21.6449 | 50.337 | 0 | 14.364 | 5.7366 | 5.6448 | 8.5859 | 19.9673 | 19.9673 | 20.426 | 0.45865 | 39.21% | 40.58% | Received but no signature proof | 10% | 0 |  |  |  | 6.062 |  | 1 | 6.062
CP09 | Mechanical Works | 68.1234 | 67.0327 | 101.9599 | 237.116 | 62.8717 | 61.865 | 94.0996 | 218.8362 | 0 | 20.0879 | 12.6881 | 12.485 | 18.9903 | 44.1634 | 44.1634 | 44.8243 | 0.66094 | 18.9% | 20.48% | Received but no signature proof | 10% | 33800000 | -33799979.9121 | -14254616% |  | 24.7364 |  | 1 | 24.7364 | Contract Package = 338M, Approved payment is less than downpayment
CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | 65.3482 | 64.3019 | 97.8062 | 227.4563 | 69.7738 | 68.6566 | 104.4299 | 242.8603 | 0 | 3.2927 | 9.4145 | 9.2638 | 14.0907 | 32.769 | 32.769 | 32.769 | 1e-08 | 14.41% | 13.49% | No contract received | 10% | 0 |  |  |  | 29.4762 |  | 1 | 29.4762
CP11a | Curtain Wall & Structural Steel (Bldg.E) | 53.1302 | 52.2795 | 79.5196 | 184.9293 | 55.639 | 54.7482 | 83.2746 | 193.6618 | 0 | 59.7958 | 22.4923 | 22.1322 | 33.6641 | 78.2887 | 78.2887 | 80.6817 | 2.393 | 43.63% | 41.66% | Received but no signature proof | 10% | 18492932.349 | -18492872.5532 | -9999968% |  | 20.8859 |  | 1 | 20.8859
CP13 | Vertical Transport System | 45.1998 | 44.4761 | 67.6502 | 157.3261 | 42.8195 | 42.1339 | 64.0877 | 149.0412 | 0 | 26.5 | 21.1974 | 20.858 | 31.726 | 73.7814 | 73.7814 | 73.7814 | 0 | 46.9% | 49.5% | Received but no signature proof | 30% of USD (Indent) 10% of PHP (Local) | 35206933.5 | -35206907 | -22378300% |  | 47.2814 |  | 1 | 47.2814
CP15 | Generator Works | 48.8883 | 48.1055 | 73.1708 | 170.1646 | 46.8767 | 46.1261 | 70.16 | 163.1629 | 0 | 12.4385 | 26.1737 | 25.7547 | 39.174 | 91.1024 | 91.1024 | 91.1024 | 0 | 53.54% | 55.84% | Received but no signature proof | 30% of USD (Indent) 10% of PHP (Local) | 40461085.028 | -40461072.5895 | -23777606% |  | 78.6639 |  | 1 | 78.6639 | Approved payment is less than downpayment
CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | 16.9507 | 16.6793 | 25.37 | 59 | 16.6471 | 16.3805 | 24.9156 | 57.9432 | 0 | 0 | 1.611 | 1.611 | 2.6781 | 5.9 | 5.9 | 5.9 | 0 | 10% | 10.18% | No contract received | 0% | 0 |  |  |  | 5.9 |  | 1 | 5.9
CP20 | Fit-Out Works | 89.063 | 87.637 | 133.3 | 310 | 89.2846 | 87.855 | 133.6316 | 310.7712 | 0 | 4.6134 | 8.7501 | 8.743 | 16.1983 | 35.6134 | 33.6915 | 35.6134 | 1.9219 | 11.49% | 11.46% | Received but no signature proof | 10% | 31000000 | -30999995.3866 | -9999999% |  | 31 |  | 1 | 31 | Approved payment is less than downpayment
CP21 | Waterproofing | 5.3458 | 5.2602 | 8.001 | 18.607 | 5.0463 | 4.9655 | 7.5528 | 17.5646 | 0 | 0 | 2.9696 | 2.922 | 4.4446 | 10.3362 | 10.3362 | 10.4825 | 0.14629 | 56.34% | 59.68% | No contract received | 10% | 0 |  |  |  | 10.4825 |  | 1 | 10.4825
CP30 | Building Maintenance Unit (BMU) | 2.9592 | 2.9118 | 4.429 | 10.3 | 3.2465 | 3.1945 | 4.859 | 11.3 | 0 | 0 | 0.68166 | 0.67074 | 1.0202 | 2.3726 | 2.3726 | 2.3726 | 0 | 23.04% | 21% | No contract received | 10% | 0 |  |  |  | 2.3726 |  | 1 | 2.3726
CP31 | Experiential Graphic Design (XGD) | 1.7238 | 1.6962 | 2.58 | 6 | 1.7251 | 1.6975 | 2.582 | 6.0046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
C01 | Construction Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | -76.424 |  | 1 | -76.424
C02 | LEED Consultant | 1.7652 | 1.737 | 2.642 | 6.1442 | 1.047 | 1.0302 | 1.567 | 3.6442 | 0 | 2.3274 | 1.047 | 1.0302 | 1.567 | 3.6442 | 3.6442 | 3.6442 | 0 | 59.31% | 100% | No contract received | 10% | 0 |  |  |  | 1.3168 |  | 1 | 1.3168
C03 | Architectural Services | 1.4365 | 1.4135 | 2.15 | 5 | 1.6376 | 1.6114 | 2.451 | 5.7 | 0 | 5.7402 | 2.6748 | 2.632 | 4.0034 | 9.3102 | 9.3102 | 9.3102 | 0 | 186.2% | 163.3% | No contract received | 10% | 0 |  |  |  | 3.57 |  | 1 | 3.57
C04 | Structural Design Engineering Services | 0.068952 | 0.067848 | 0.1032 | 0.24 | 0.2126 | 0.2092 | 0.3182 | 0.74 | 0 | 0.24 | 0.068952 | 0.067848 | 0.1032 | 0.24 | 0.24 | 0.24 | 0 | 100% | 32.43% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
C05 | MEPF Design Engineering Services | 0.70799 | 0.69665 | 1.0596 | 2.4643 | 2.2899 | 2.2532 | 3.4272 | 7.9703 | 0 | 7.6089 | 2.54 | 2.4994 | 3.8017 | 8.8411 | 8.8411 | 8.8411 | 1e-08 | 358.8% | 110.9% | No contract received | 10% | 0 |  |  |  | 1.2321 |  | 1 | 1.2321
C06 | Building Information Modelling (BIM) Services | 1.0055 | 0.98945 | 1.505 | 3.5 | 1.0055 | 0.98945 | 1.505 | 3.5 | 0 | 1.9596 | 1.0055 | 0.98945 | 1.505 | 3.5 | 3.5 | 3.5 | 0 | 100% | 100% | No contract received | 10% | 0 |  |  |  | 1.5404 |  | 1 | 1.5404
C07 | Façade Design Services | 0.57747 | 0.56823 | 0.8643 | 2.01 | 0.60477 | 0.59508 | 0.90515 | 2.105 | 0 | 0.755 | 0.42808 | 0.42122 | 0.6407 | 1.49 | 1.49 | 1.49 | 0 | 74.13% | 70.78% | No contract received | 10% | 0 |  |  |  | 0.735 |  | 1 | 0.735
C08 | Landscape Design Services | 0.08619 | 0.08481 | 0.129 | 0.3 | 0.08619 | 0.08481 | 0.129 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
C09 | Cost Consultant / Quantity Surveying Services | 6.7738 | 6.6654 | 10.1384 | 23.5776 | 4.3095 | 4.2405 | 6.45 | 15 | 0 | 17.255 | 5.6081 | 5.5183 | 8.3936 | 19.52 | 19.52 | 19.52 | 0 | 82.79% | 130.1% | No contract received | 10% | 0 |  |  |  | 2.265 |  | 1 | 2.265
CARI | Insurances | 1.9803 | 1.9486 | 2.9639 | 6.8927 | 2.9864 | 2.9386 | 4.4697 | 10.3947 | 3.502 | 10.3947 | 2.9864 | 2.9386 | 4.4697 | 10.3947 | 10.3947 | 10.3947 | 0 | 150.8% | 100% | Please provide information | 10% | 0 |  |  |  | 0 |  | 1 | 0
OP01 | Cement (Supply only) | 26.4779 | 26.054 | 39.6294 | 92.1613 | 23.1345 | 22.764 | 34.6252 | 80.5237 | 0 | 33.0413 | 9.4928 | 9.3408 | 14.2078 | 33.0413 | 33.0413 | 33.0413 | 0 | 35.85% | 41.03% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
OP02 | Reinforcing Steel (OSM) | 74.583 | 73.3888 | 111.6278 | 259.5996 | 48.194 | 47.4223 | 72.1316 | 167.7479 | 0 | 105.752 | 30.3826 | 29.8961 | 45.4734 | 105.752 | 105.752 | 105.752 | -1e-08 | 40.74% | 63.04% | No contract received | 10% | 0 |  |  |  | 2.02e-10 |  | 1 | 2.02e-10
OP33 | Door Hardwares | 3.8211 | 3.7599 | 5.719 | 13.3 | 3.9409 | 3.8778 | 5.8984 | 13.7172 | 0.41715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
OP13 | Lighting Fixture | 10.0555 | 9.8945 | 15.05 | 35 | 10.8208 | 10.6476 | 16.1955 | 37.6639 | 2.6639 | 1.7925 | 9.5432 | 9.3904 | 14.2833 | 33.217 | 33.217 | 33.217 | 0 | 94.91% | 88.19% | No contract received | 10% | 0 |  |  |  | 31.4245 |  | 1 | 31.4245
OP12 | Power Transformer (OSM) | 6.9354 | 6.8244 | 10.3802 | 24.1401 | 7.3664 | 7.2485 | 11.0252 | 25.6401 | 1.5 | 15.0812 | 5.074 | 4.9928 | 7.5942 | 17.661 | 17.661 | 19.3532 | 1.6922 | 80.17% | 75.48% | No contract received | 10% | 0 |  |  |  | 4.272 |  | 1 | 4.272
OP15 | Plumbing Fixture | 3.2178 | 3.1662 | 4.816 | 11.2 | 4.1057 | 4.04 | 6.145 | 14.2907 | 3.0907 | 0 | 3.0813 | 3.0319 | 4.6117 | 10.7249 | 10.7249 | 10.7249 | 0 | 95.76% | 75.05% | No contract received | 10% | 0 |  |  |  | 10.7249 |  | 1 | 10.7249
OP18 | Fire Extinguishers | 2.2952 | 2.2585 | 3.4352 | 7.9889 | 2.3137 | 2.2767 | 3.4629 | 8.0533 | 0.064406 | 28.3076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | -28.3076 |  | 1 | -28.3076
OP27 | Supply and Delivery of Air Conditioning System - VRF | 22.4094 | 22.0506 | 33.54 | 78 | 26.5521 | 26.1269 | 39.7403 | 92.4193 | 14.4193 | 24.5366 | 12.9468 | 12.7395 | 19.3774 | 45.0638 | 45.0638 | 45.0638 | 0 | 57.77% | 48.76% | No contract received | 10% | 0 |  |  |  | 20.5272 |  | 1 | 20.5272
CP05C | Community Distributive Antenna System (CDAS) | 4.2723 | 4.2039 | 6.3943 | 14.8704 | 4.2723 | 4.2039 | 6.3943 | 14.8704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
CP26 | Seismic Monitoring | 0.25857 | 0.25443 | 0.387 | 0.9 | 0.25857 | 0.25443 | 0.387 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | No contract received | 10% | 0 |  |  |  | 0 |  | 1 | 0
Con | Contingencies | 0 | 0 | 0 | 0 | 145.6437 | 143.3118 | 217.984 | 506.9395 | 506.9395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Please provide information | 10% | 0 |  |  |  | 0 |  | 1 | 0
| Total | 850.4544 | 836.8377 | 1272.8695 | 2960.1616 | 1023.0075 | 1006.628 | 1531.1286 | 3560.7642 | 532.5969 | 897.6784 | 348.4341 | 343.1897 | 524.6081 |  | 1216.232 | 1225.3231 | 9.0911 | 41.39% | 34.41% | [5 empty] | 0 | 327.6447 | 657.6762 |  | 985.3209
Note on Q8: Different from Table Typo Error
Note on Q19: Different from Table Typo Error

## Tonghop2
No. | Description | Cost Report (June 2020) | S-curve | Remark
1 | Awarded | 2960161571.81 | 2960161571.81
| Un-awarded | 104090311.296 | 121216642.9246 | PM/CM services
| Progress | 1225323050.21 | 939884189.7338 | Scenarios
2 | To completion 1 | 1838928832.896 | 2141494025.0008 | without risks
3 | Potential VOs
| Min | 217623411.52 | 217623411.52
| Max | 657676183.77 | 657676183.77
4 | Unpaid WIP | 327644697.3202 | 42205836.844
5 | To Completion 2 |  |  | With potential VOs
| Min | 2384196941.7362 | 2401323273.3648 | and unpaid WIP
| Max | 2824249713.9862 | 2841376045.6148
6 | To Completion 3 |  |  | With probabilistic
| Min | 2622616635.9098 | 2641455600.7013 | risks (10%)
| Max | 3106674685.3848 | 3125513650.1763
7 | Contingencies
| Budgeted | 506939469.55 | 506939469.55
| Saving | 93663117.64 | 93663117.64
| Total | 600602587.19 | 600602587.19
| Notes: | Min | 3539133953.5911
| 5 = 2 + 3 + 4 | Max | 4023192003.0661
6 = 5 x 1.1

## Tonghop2_Table
No. | Description | Cost Report (June 2020) | S-curve | Remark
1 | Awarded | 2960161571.81 | 2960161571.81
| Un-awarded | 104090311.296 | 121216642.9246 | PM/CM services
| Progress | 1225323050.21 | 939884189.7338 | Scenarios
2 | To completion 1 | 1838928832.896 | 2141494025.0008 | without risks
3 | Potential VOs
| Min | 217623411.52 | 217623411.52
| Max | 657676183.77 | 657676183.77
4 | Unpaid WIP | 327644697.3202 | 42205836.844
5 | To Completion 2 |  |  | With potential VOs
| Min | 2384196941.7362 | 2401323273.3648 | and unpaid WIP
| Max | 2824249713.9862 | 2841376045.6148
6 | To Completion 3 |  |  | With probabilistic
| Min | 2622616635.9098 | 2641455600.7013 | risks (10%)
| Max | 3106674685.3848 | 3125513650.1763
7 | Contingencies
| Budgeted | 506939469.55 | 506939469.55
| Saving | 93663117.64 | 93663117.64
| Total | 600602587.19 | 600602587.19
Notes:
5 = 2 + 3 + 4
6 = 5 x 1.1

## Contract-Sum
Items | Main Package | Awarded_Total (in M PhP) | Budget_Total (in M PhP)
C10 | Testing & Commissioning (3rd Party) | 9.7 | 9.7
CP01 | Structure and General Sitewide | 365 | 530.6019
CP01a | Masonry & Rendering, Metal Doors & Hardwares, Office Floor | 132 | 138.2481
CP04 | Electrical Works | 290.173 | 287.1228
CP05A | Building Management System (BMS) | 15 | 18.5556
CP05B | Fire Detection & Alarm System | 15 | 19.4939
CP05D | Structured Cabling System & Public Address (SCS & PA) | 23 | 26.2393
CP06E | Access Control, Guard Tour and | 28 | 32.7796
CP06F | Closed Circuit Television System (CCTV) | 22 | 22.191
CP07 | Plumbing & Sanitary Works | 40 | 42.2289
CP08 | Fire Protection Works | 52.1 | 50.337
CP09 | Mechanical Works | 237.116 | 218.8362
CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | 227.4563 | 242.8603
CP11a | Curtain Wall & Structural Steel (Bldg.E) | 184.9293 | 193.6618
CP13 | Vertical Transport System | 157.3261 | 149.0412
CP15 | Generator Works | 170.1646 | 163.1629
CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | 59 | 57.9432
CP20 | Fit-Out Works | 310 | 310.7712
CP21 | Waterproofing | 18.607 | 17.5646
CP30 | Building Maintenance Unit (BMU) | 10.3 | 11.3
CP31 | Experiential Graphic Design (XGD) | 6 | 6.0046
C01 | Construction Management | 0 | 0
C02 | LEED Consultant | 6.1442 | 3.6442
C03 | Architectural Services | 5 | 5.7
C04 | Structural Design Engineering Services | 0.24 | 0.74
C05 | MEPF Design Engineering Services | 2.4643 | 7.9703
C06 | Building Information Modelling (BIM) Services | 3.5 | 3.5
C07 | Façade Design Services | 2.01 | 2.105
C08 | Landscape Design Services | 0.3 | 0.3
C09 | Cost Consultant / Quantity Surveying Services | 23.5776 | 15
CARI | Insurances | 6.8927 | 10.3947
OP01 | Cement (Supply only) | 92.1613 | 80.5237
OP02 | Reinforcing Steel (OSM) | 259.5996 | 167.7479
OP33 | Door Hardwares | 13.3 | 13.7172
OP13 | Lighting Fixture | 35 | 37.6639
OP12 | Power Transformer (OSM) | 24.1401 | 25.6401
OP15 | Plumbing Fixture | 11.2 | 14.2907
OP18 | Fire Extinguishers | 7.9889 | 8.0533
OP27 | Supply and Delivery of Air Conditioning System - VRF | 78 | 92.4193
CP05C | Community Distributive Antenna System (CDAS) | 14.8704 | 14.8704
CP26 | Seismic Monitoring | 0.9 | 0.9
Con | Contingencies | 0 | 506.9395
| Total | 2960.1616 | 3560.7642

## Contract-Sum-Append
Project Name: Project Hope - TDD of West Aeropark Buildings
Subject: WAP2 Contract Packages
Items | Main Package | Awarded_C (in M PhP) | Awarded_D (in M PhP) | Awarded_E (in M PhP) | Awarded_Total (in M PhP) | Budget_C (in M PhP) | Budget_D (in M PhP) | Budget_E (in M PhP) | Budget_Total (in M PhP)
C10 | Testing & Commissioning (3rd Party) | 2.7868 | 2.7422 | 4.171 | 9.7 | 2.7868 | 2.7422 | 4.171 | 9.7
CP01 | Structure and General Sitewide | 104.8645 | 103.1855 | 156.95 | 365 | 152.4419 | 150.0012 | 228.1588 | 530.6019
CP01a | Masonry & Rendering, Metal Doors & Hardwares, Office Floor | 37.9236 | 37.3164 | 56.76 | 132 | 39.7187 | 39.0827 | 59.4467 | 138.2481
CP04 | Electrical Works | 83.3667 | 82.0319 | 124.7744 | 290.173 | 82.4904 | 81.1696 | 123.4628 | 287.1228
CP05A | Building Management System (BMS) | 4.3095 | 4.2405 | 6.45 | 15 | 5.331 | 5.2457 | 7.9789 | 18.5556
CP05B | Fire Detection & Alarm System | 4.3095 | 4.2405 | 6.45 | 15 | 5.6006 | 5.5109 | 8.3824 | 19.4939
CP05D | Structured Cabling System & Public Address (SCS & PA) | 6.6079 | 6.5021 | 9.89 | 23 | 7.5385 | 7.4178 | 11.2829 | 26.2393
CP06E | Access Control, Guard Tour and | 8.0444 | 7.9156 | 12.04 | 28 | 9.4176 | 9.2668 | 14.0952 | 32.7796
CP06F | Closed Circuit Television System (CCTV) | 6.3206 | 6.2194 | 9.46 | 22 | 6.3755 | 6.2734 | 9.5421 | 22.191
CP07 | Plumbing & Sanitary Works | 11.492 | 11.308 | 17.2 | 40 | 12.1324 | 11.9381 | 18.1584 | 42.2289
CP08 | Fire Protection Works | 14.9683 | 14.7287 | 22.403 | 52.1 | 14.4618 | 14.2303 | 21.6449 | 50.337
CP09 | Mechanical Works | 68.1234 | 67.0327 | 101.9599 | 237.116 | 62.8717 | 61.865 | 94.0996 | 218.8362
CP11 | Curtain Wall & Structural Steel (Bldg.C&D) | 65.3482 | 64.3019 | 97.8062 | 227.4563 | 69.7738 | 68.6566 | 104.4299 | 242.8603
CP11a | Curtain Wall & Structural Steel (Bldg.E) | 53.1302 | 52.2795 | 79.5196 | 184.9293 | 55.639 | 54.7482 | 83.2746 | 193.6618
CP13 | Vertical Transport System | 45.1998 | 44.4761 | 67.6502 | 157.3261 | 42.8195 | 42.1339 | 64.0877 | 149.0412
CP15 | Generator Works | 48.8883 | 48.1055 | 73.1708 | 170.1646 | 46.8767 | 46.1261 | 70.16 | 163.1629
CP17 | Landscape (Softscape, Hardscape & Exterior Tiles) | 16.9507 | 16.6793 | 25.37 | 59 | 16.6471 | 16.3805 | 24.9156 | 57.9432
CP20 | Fit-Out Works | 89.063 | 87.637 | 133.3 | 310 | 89.2846 | 87.855 | 133.6316 | 310.7712
CP21 | Waterproofing | 5.3458 | 5.2602 | 8.001 | 18.607 | 5.0463 | 4.9655 | 7.5528 | 17.5646
CP30 | Building Maintenance Unit (BMU) | 2.9592 | 2.9118 | 4.429 | 10.3 | 3.2465 | 3.1945 | 4.859 | 11.3
CP31 | Experiential Graphic Design (XGD) | 1.7238 | 1.6962 | 2.58 | 6 | 1.7251 | 1.6975 | 2.582 | 6.0046
C01 | Construction Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C02 | LEED Consultant | 1.7652 | 1.737 | 2.642 | 6.1442 | 1.047 | 1.0302 | 1.567 | 3.6442
C03 | Architectural Services | 1.4365 | 1.4135 | 2.15 | 5 | 1.6376 | 1.6114 | 2.451 | 5.7
C04 | Structural Design Engineering Services | 0.068952 | 0.067848 | 0.1032 | 0.24 | 0.2126 | 0.2092 | 0.3182 | 0.74
C05 | MEPF Design Engineering Services | 0.70799 | 0.69665 | 1.0596 | 2.4643 | 2.2899 | 2.2532 | 3.4272 | 7.9703
C06 | Building Information Modelling (BIM) Services | 1.0055 | 0.98945 | 1.505 | 3.5 | 1.0055 | 0.98945 | 1.505 | 3.5
C07 | Façade Design Services | 0.57747 | 0.56823 | 0.8643 | 2.01 | 0.60477 | 0.59508 | 0.90515 | 2.105
C08 | Landscape Design Services | 0.08619 | 0.08481 | 0.129 | 0.3 | 0.08619 | 0.08481 | 0.129 | 0.3
C09 | Cost Consultant / Quantity Surveying Services | 6.7738 | 6.6654 | 10.1384 | 23.5776 | 4.3095 | 4.2405 | 6.45 | 15
CARI | Insurances | 1.9803 | 1.9486 | 2.9639 | 6.8927 | 2.9864 | 2.9386 | 4.4697 | 10.3947
OP01 | Cement (Supply only) | 26.4779 | 26.054 | 39.6294 | 92.1613 | 23.1345 | 22.764 | 34.6252 | 80.5237
OP02 | Reinforcing Steel (OSM) | 74.583 | 73.3888 | 111.6278 | 259.5996 | 48.194 | 47.4223 | 72.1316 | 167.7479
OP33 | Door Hardwares | 3.8211 | 3.7599 | 5.719 | 13.3 | 3.9409 | 3.8778 | 5.8984 | 13.7172
OP13 | Lighting Fixture | 10.0555 | 9.8945 | 15.05 | 35 | 10.8208 | 10.6476 | 16.1955 | 37.6639
OP12 | Power Transformer (OSM) | 6.9354 | 6.8244 | 10.3802 | 24.1401 | 7.3664 | 7.2485 | 11.0252 | 25.6401
OP15 | Plumbing Fixture | 3.2178 | 3.1662 | 4.816 | 11.2 | 4.1057 | 4.04 | 6.145 | 14.2907
OP18 | Fire Extinguishers | 2.2952 | 2.2585 | 3.4352 | 7.9889 | 2.3137 | 2.2767 | 3.4629 | 8.0533
OP27 | Supply and Delivery of Air Conditioning System - VRF | 22.4094 | 22.0506 | 33.54 | 78 | 26.5521 | 26.1269 | 39.7403 | 92.4193
CP05C | Community Distributive Antenna System (CDAS) | 4.2723 | 4.2039 | 6.3943 | 14.8704 | 4.2723 | 4.2039 | 6.3943 | 14.8704
CP26 | Seismic Monitoring | 0.25857 | 0.25443 | 0.387 | 0.9 | 0.25857 | 0.25443 | 0.387 | 0.9
Con | Contingencies | 0 | 0 | 0 | 0 | 145.6437 | 143.3118 | 217.984 | 506.9395
| Total | 850.4544 | 836.8377 | 1272.8695 | 2960.1616 | 1023.0075 | 1006.628 | 1531.1286 | 3560.7642

## Risk_Report
Project Name: Project Hope - TDD of West Aeropark Buildings
Subject: RISK AND POTENTIAL VARIATION ORDER (MILLIONS PESO)
ID | Risk_Level | Item | CP | Status | Cons | Factor | Risk | Prob | Value | Description
1 | Project Wide | Increased Cost for Consultants contracts and payments excluding TPM cost for Building E | VARIOUS | PENDING | 10.6 | 0.9 | 9.54 | 1 | 10.6 | This will be likely due to extra meetings & site visits 20% of consultant budget.
2 | Project Wide | Possible increased in Shipping costs associated with using nominated freight forwarders | VARIOUS | PENDING | 0 |  |  | 1 | 0 | This is possible and quantum difficult to estimate right now.
3 | Project Wide | Government mandated wage increase. (Region 3) * Projected calculation for the period: NOVEMBER 2018 - NOVEMBER 2019 based on NCR Wage Increase | VARIOUS | PENDING | 28.3795 | 1 | 28.3795 | 1 | 28.3795 | Note: -Updated to include labor components of Bldg D that was missed out previously - Replied to all Contractors for Labor Escalation Claim requesting for the supporting documents for assessment. - 11/15:(total awarded amount*30%)/512)*25 - Recent wage increase which was implemented in Region 3 was not applied by the Contractor only taking into account the NCR wage increase alone.
4 | Project Wide | Sutherland Changes - Consultant's Cost (BMS, FDAS, MVAC) | VARIOUS | PENDING | 2.5 | 1 | 2.5 | 1 | 2.5 | - Increased for Sep 2019 cost report as per high level estimate from QSI (Php 2.5M) - Allowance for additional cost to design changes
5 | Builder's Work | Plastering Works in Toilet claimed by TACC | CP01A | PENDING | 10.5 | 1 | 10.5 | 1 | 10.5 | - Agreed Php 10.5M, please refer to Glenson Lim email dated 12 Feb 2020 to Malcolm Ward and David Meade, CR to be raised upon receipt of details of agreed amount. Cost to be advised after meeting between GGDC and TACC -Refer to CGC-L-WAP2-TER-0030 dated 12 Nov 2019 for the letter response of GGDC on the claim of TACC
6 | MEPF | Genset - Double Handling of Genset etc due to site not ready | CP15 | PENDING | 0.9 | 0.75 | 0.675 | 1 | 0.9 | 10/2019; risk likelihood was increased to 75% from 50% 07/2019: Reduced allowance due to Genset pull out 06/2019: CP15 to claim for Permit to Install 03/2019: Adjusted due to GGDC provision of lay-down area 01/2019: Overall Allowance covers transportation and lifting facilities. 12/2018: Possibly come early as contractor now producing even w/out payment; Allowance for Mobile Crane 100T - 700k @ 2 days; 60T - 450k for 4 days
7 | MEPF | OP12 - Double Handling of Transformer, etc due to site not ready | OP12 | PENDING | 1.8 | 0.75 | 1.35 | 1 | 1.8 | 10/2019; risk likelihood was increased to 75% from 50% '03/2019: Adjusted due to GGDC provision of slay-down area Possibly come early as contractor now producing; Allowance for Mobile Crane 60T - 450k for 4 days
8 | MEPF | CP13 - Double Handling of Lifts due to early delivery | CP13 | PENDING | 1.9 | 0.75 | 1.425 | 1 | 1.9 | 10/2019; risk likelihood was increased to 75% from 50% '03/2019: Adjusted due to GGDC provision of slay-down area 02/2019: Adjusted to reflect the revised cost but used factor 75% from previously submitted rate. 01/2019: Factored 60% from Contractor's submitted quotation (Approx Cost - 5.021M 12/2018: Minimal risk; possible to use the Owner's laydown area; Contractor to advise if laydown area can be used
9 | MEPF | Plumbing - Phase 1 Irrigation Lines not backfilled | CP07 | PENDING | 0.2 | 1 | 0.2 | 1 | 0.2 | Allowance
10 | MEPF | Offsite Storage for MVSG & LVSG | CP04 | PENDING | 0.024 | 1 | 0.024 | 1 | 0.024 | -BEC is still claiming for 1 month storage cost as per letter ref BEC_LET_WAP2_CP04_0061. - Allowance for Storage Facility considered for 6 months '- Cancelled, BEC instructed to deliver MVSG and LVSG at temporay carpark warehouse of GGDC, letter ref. CGC-L-WAP2-046
11 | MEPF | Interest Charge for Late Payment | CP04 | PENDING | 1.8794 | 0.5 | 0.93969 | 1 | 1.8794 | - Allowance considered for 3 months, please refer to Glenson Lim's email dated 19 Aug 2019. - Please refer to JSEC letter ref JSEC_LET_WAP2_0020 dated 02 July 2019.
12 | MEPF | CP15 - processing of Genset Permit to Install | CP15 | PENDING | 0.16 | 0.75 | 0.12 | 1 | 0.16 | -WAP2_CR_0148 raised for costing by QSI Allowance considered , please refer to GGDC letter ref CGC-L WAP2-PIS-0004 dated 20 Aug 2019 - Please refer to quotation from Powergen dated 07 Nov 2019 (Php 160k) Missed in the original building permit
13 | MEPF | Cancelation fee and a possible cost increase USD 145,329.07 should the additional 6 Generators order not be fulfilled by December. | CP15 | PENDING | 7.7024 | 0.34 | 2.6188 | 1 | 7.7024 | Powergen informed GGDC thru their letter dated 27 December 2019 stating that Cummins UK has cancelled their order for Bldg C & D due to non payment in full and will bill them separately the cancellation charges amounting to 2.6M Php Powergen informed GGDC thru their letter dated 25 Oct 2019 attached to this letter of a possible cost claim regarding cancellation fee from Cummins. This was reiterated by TPM on 18 Nov 2019 email. On 17 Dec 2019, Ysmael of Powergen called TPM advising that they had been penalised by Cummins Philippines. G ELECTRICAL LOW VOLTAGE
14 | External_Works | Overlap in scope between the Phase 1 Landscape and Phase 2 Landscape | CP17 | PENDING | 0.5 | 1 | 0.5 | 1 | 0.5 | Allowance
15 | Commercial | EOT Claim projected for all contractors for 17 mos for Buildings C & D as of May 2020 (excludes 3-months COVID-19 lock down except for plant by Terp like TC, alimaks, etc) | VARIOUS | PENDING | 238.5159 | 0.74 | 176.5017 | 0 | 0 | Calculation based on the reduced Bldg C & D Prolongation Cost due to inactivity Updated calculation based on the latest EoT claim by Terp (CP01 and CP01A).
16 | Commercial | EOT Claim projected for all contractors for 17 mos for Buildings E as of May 2020 (excludes 3-months COVID-19 lock down, except for plant by Terp like TC, alimaks, etc) | VARIOUS | PENDING | 201.5369 | 0.76 | 153.168 | 0 | 0 | Calculation based on the reduced days of delays with reference to original completion date of CP01 ie 17 months from Oct 2018. Updated calculation based on the latest EoT claim by Terp (CP01 and CP01A)
17 | Commercial | Acceleration Cost for CSA and MEPF Contractors at Bldg E only | VARIOUS | PENDING | 16.4716 | 0 |  | 1 | 16.4716 | PMI for Acceleration of the Works at Building E was issued to all Contractors as of 06 Mar 2020. No cost allowance as this was not implemented due to sudden work stoppage notice from GGDC dated 18 Mar 2020. PMI needs to be superseded / cancelled.
18 | Commercial | CP & OP Orders not placed to be transferred to the Contingency (Anticipated to be spent) | VARIOUS | PENDING | -63.5 | 0 |  | 1 | -63.5 | Remaining Allowance for ONP; CR to return budget to Contingency was already carried out;ONP for CP17 included
19 | Commercial | Allowance for Future Changes - Client/ Tenant led changes | VARIOUS | PENDING | 54 | 0.5 | 27 | 1 | 54 | 03/2019: 50% reduction
20 | Commercial | Due to delayed payment to Contractors/ Suppliers and with equipment arriving on site or at Contractor's premises, there is potential risk for litigation | VARIOUS | PENDING | 0 |  |  | 1 | 0 | - Additional budget to be applied
21 | Commercial | Contractor's Restart Cost for Building C & D | VARIOUS | PENDING | 50 | 0.5 | 25 | 1 | 50 | - Allowance for remobilization cost
22 | Commercial | Additional TACC Labor Impact Cost due to deceleration | VARIOUS | PENDING | 20 | 0.5 | 10 | 1 | 20 | - Allowance for remobilization cost
23 | Commercial | Possible termination of Façade Contract for Building C & D | CP11 | PENDING | 100 | 1 | 100 | 1 | 100 | - Additional allowance due to inflation and retender
24 | Commercial | 2nd Extension of CARI (1st extension expires on 04 Apr 2020) | GGDC | PENDING | 4 | 0.75 | 3 | 1 | 4 | Contractor All Risks Insurance
25 | Commercial | Additional 3rd Party T & C Cost due different completion dates of each Buildings | VARIOUS | PENDING | 0 | 0.75 |  | 1 | 0 | Possible additional cost claim by Commtech due to stagerred building handover, thus there are possible mobilisation, demobilisation and remobilisation for Commtech resources.
26 | Commercial | COVID-19 regulatory cost impact | VARIOUS | PENDING | 10 | 0.75 | 7.5 | 1 | 10 | Possible cost claim by Contractors due to additional regulatory requirement to comply with the new health and safety standard, so far CP-21 (water proofing package) has intimated a probable cost claim.
27 | Commercial | Works Funded from Other Budget - Sutherland | VARIOUS | PENDING | -40.3935 | 0.29 | -11.7141 | 1 | -40.3935 | Some of the approved change request were taken by Sutherland and arrangement had been made for SGS to directly pay the contractors by issuing a Purchase Order. Cost allocation based on confirmed packages by SGS (NTP issued to Beta) Initially put under risk but shall be reflected in the project cost report as soon as finalised with SGS.
|  | Total |  |  | 657.6762 |  | 549.2277 |  | 217.6234